## Tracker&Invoice
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 60% | 30% | 10%
D-001 | التصاميم التفصيلية وتصاميم المرحلة الثالثة Stage 3 Design Package | 1 | 1 | عدد | 2840000 | 2840000 | Submittal 1 | Submittal 2 | HCIS Approval
| TRACKER #01 | [5 empty] | 60%
| INVOICE #01 | [5 empty] | 1704000
| TRACKER #03 | [6 empty] | 30%
| INVOICE #03 | [6 empty] | 852000
| TRACKER #05 | [7 empty] | 10%
| INVOICE #05 | [7 empty] | 284000
| Overall Completion INVOICE | [5 empty] | 2840000
| Overall Completion | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 60% |  | 40%
D-002 | الهندسة والتصميم IFC, Shop drawings and Stage 4 drawings | 1 | 1 | عدد | 2630000 | 2630000 | Shop Drawings |  | AS BUILT
[7 empty] | 80% | 20%
| TRACKER #05 | [5 empty] | 26.4
| INVOICE #05 | [5 empty] | 126240
| TRACKER #06 | [5 empty] | 68
| INVOICE #06 | [5 empty] | 325163.6364
| TRACKER #07 | [5 empty] | 100
| INVOICE #07 | [5 empty] | 478181.8182
| TRACKER #08 | [5 empty] | 10
| INVOICE #08 | [5 empty] | 47818.1818
| TRACKER #10 | [5 empty] | 16
| INVOICE #10 | [5 empty] | 76509.0909
| TRACKER #11 | [5 empty] | 7
| INVOICE #11 | [5 empty] | 33472.7273
| TRACKER #12 | [5 empty] | 8
| INVOICE #12 | [5 empty] | 38254.5455
| TRACKER #14 | [5 empty] | 5.6
| INVOICE #14 | [5 empty] | 26778.1723
| TRACKER #15 | [5 empty] | 18
| INVOICE #15 | [5 empty] | 86072.7273
| TRACKER #20 | [5 empty] | 5
| INVOICE #20 | [5 empty] | 23909.0909
| TRACKER #26 | [6 empty] | 264
| INVOICE #26 | [6 empty] | 315600
| Overall Completion TRACKER | [5 empty] | 264 | 264
| Overall Completion INVOICE | [5 empty] | 1262400.0004 | 315600
| ToT.Overall Completion INVOICE | [5 empty] | 1578000.0004
| Overall Completion | [5 empty] | 60%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 90% | 10%
D-003 | تدريب المشغلين وموظفي الصيانة Training of Operators and Maintenance Personnel | 1 | 1 | عدد | 110000 | 110000 | Training | Handover Manual & Documentation
TRACKER #00
INVOICE #00
| Overall Completion TRACKER | [5 empty] | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-001 | محمول شبكة مركزي مع جميع الكابلات ذات الصلة والملحقات والأجهزة التمهيدية وأجهزة الشبكة Central Redundant Network Core Switch with all related cabling, accessories, prepherals and network devices | 4 | 4 | عدد | 130000 | 520000 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 4
| INVOICE #13 | [5 empty] | 364000
| TRACKER #25 | [6 empty] | 4
| INVOICE #25 | [6 empty] | 31200
| TRACKER #28 | [7 empty] | 4 | 3 | 3
| INVOICE #28 | [7 empty] | 10400 | 3900 | 3900
| TRACKER #32 | [8 empty] | 1 | 1
| INVOICE #32 | [8 empty] | 1300 | 1300
| Overall Completion TRACKER | [5 empty] | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 364000 | 31200 | 10400 | 5200 | 5200 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 364000
| Tot.implementation | [5 empty] | 52000
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 416000
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-002 | محول شبكة جيجابايت مع جميع الكابلات ذات الصلة والملحقات والأجهزة التمهيدية وأجهزة الشبكة Gigabit Network Switch with all related cabling, accessories, prepherals and network devices | 10 | 10 | عدد | 19600 | 196000 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 3
| INVOICE #13 | [5 empty] | 41160
| TRACKER #15 | [5 empty] | 7
| INVOICE #15 | [5 empty] | 96040
| TRACKER #25 | [6 empty] | 10
| INVOICE #25 | [6 empty] | 11760
| TRACKER #28 | [5 empty] | -5 |  | 2
| INVOICE #28 | [5 empty] | -68600 |  | 784
| TRACKER #29 | [6 empty] | -5
| INVOICE #29 | [6 empty] | -5880
| TRACKER #32 | [7 empty] | 3 | 5 | 5
| INVOICE #32 | [7 empty] | 1176 | 980 | 980
| Overall Completion TRACKER | [5 empty] | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 68600 | 5880 | 1960 | 980 | 980 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 68600
| Tot.implementation | [5 empty] | 9800
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 78400
| Overall Completion percentage | [5 empty] | 40%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [5 empty] | T&C / Configuration |  | Handover
BQ-003 | كابينة المعدات الميدانية بما في ذلك جميع إمدادات الطاقة وكابلات الطاقة والبيانات إلى FEC وجميع المعدات الأمنية والمفاتيح الصناعية ولوحات التصحيح و CBs و TB وجميع الملحقات الكهربائية والاتصالات ذات الصلة وجميع الأعمال اللازمة لإكمال البند. Field Equipment cabinets including all power supplies, power and data cabling to the FEC and all security equipment, Industrial switches, patch panels, CBs, TBs, and all related electrical and communications accessories and all necessary work to complete the item. | 66 | 61 | عدد | 23700 | 1445700 |  | Civil Works | FEC inst'n | Component Installation | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 40% | 20% | 15% | 10% | 10% | 5% | 90% | 10%
| TRACKER #20 | [6 empty] | 23
| INVOICE #20 | [6 empty] | 54510
| TRACKER #21 | [6 empty] | 2
| INVOICE #21 | [6 empty] | 4740
| TRACKER #24 | [5 empty] | 60 | 6
| INVOICE #24 | [5 empty] | 782100 | 14220
| TRACKER #25 | [5 empty] | 1 |  |  | 50
| INVOICE #25 | [5 empty] | 13035 |  |  | 44437.5
| TRACKER #26 | [6 empty] | 15 | 46 |  | 46
| INVOICE #26 | [6 empty] | 35550 | 54510 |  | 27255
| TRACKER #27 | [6 empty] | 1 | 1 | 6 | 1
| INVOICE #27 | [6 empty] | 2370 | 1185 | 5332.5 | 592.5
| TRACKER #28 | [6 empty] | 9 | 6
| INVOICE #28 | [6 empty] | 21330 | 7110
| TRACKER #29 | [9 empty] | 3 | 50 | 47
| INVOICE #29 | [9 empty] | 1777.5 | 29625 | 13923.75
| TRACKER #30 | [8 empty] | 5 | 2
| INVOICE #30 | [8 empty] | 4443.75 | 1185
| TRACKER #31 | [6 empty] | 2 | 5 |  | 1
| INVOICE #31 | [6 empty] | 4740 | 5925 |  | 592.5
| TRACKER #32 | [9 empty] | 4 | 7 | 10
| INVOICE #32 | [9 empty] | 2370 | 4147.5 | 2962.5
| TRACKER #33 | [6 empty] | 1 | 1 |  | 2 | 2 | 2
| INVOICE #33 | [6 empty] | 2370 | 1185 |  | 1185 | 1185 | 592.5
| Overall Completion TRACKER | [5 empty] | 61 | 59 | 59 | 61 | 59 | 59 | 59 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 795135 | 139830 | 69915 | 54213.75 | 34957.5 | 34957.5 | 17478.75 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 795135
| Tot.implementation | [5 empty] | 351352.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1146487.5
| Overall Completion percentage | [5 empty] | 79.3%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 20% |  |  |  |  | 60% | [6 empty] | 10% |  | 10%
[7 empty] | Procurement |  |  |  |  | CONSTRUCTION | [6 empty] | T&C / Configuration |  | Handover
BQ-004 | توريد وتركيب واختبار جميع أعمال الألياف الضوئية للشبكة الرئيسية والتوزيع (بما في ذلك جميع كابلات Fo ، الملحقات ، OSP ، معدات شبكة توزيع الألياف ، الخزائن ، الرفوف ، لوحات التصحيح ، توزيع الطاقة ، حفر الخنادق ، أعمال الحفر ، الأعمال المدنية ، التركيب ، الإنهاء ، الاختبار والتشغيل) وجميع الأعمال اللازمة لإكمال البند | 9953 | 14655 | م.ط | 320 | 4689600 | FIBER OPTIC | RACKS | PATCH PANEL | ACCESSORIES | MARKING (WARNING TAPE AND POST) | Civil Works | Configure | Install Devices | Racking & Stacking | Patching & Cabling | Termination | Testing & Commissioning | RFI / Config. | Acceptance
[7 empty] | 80% | 5% | 5% | 3% | 7% | 40% | 15% | 10% | 20% | 5% | 5% | 5% | 90% | 10%
| TRACKER #13 | [5 empty] | 8868
| INVOICE #13 | [5 empty] | 454041.6
| TRACKER #19 | [10 empty] | 2000
| INVOICE #19 | [10 empty] | 153600
| TRACKER #20 | [10 empty] | 500
| INVOICE #20 | [10 empty] | 38400
| TRACKER #23 | [10 empty] | 440
| INVOICE #23 | [10 empty] | 33792
| TRACKER #24 | [10 empty] | 3500 | 5000
| INVOICE #24 | [10 empty] | 268800 | 144000
| TRACKER #25 | [10 empty] | 1756.5 | 4000 |  | 4500
| INVOICE #25 | [10 empty] | 134899.2 | 115200 |  | 172800
| TRACKER #26 | [5 empty] | 1085 | 9953 | 4976.5 | 4976.5 | 4976.5 | 1756.5 | 953 | 5000 | 500
| INVOICE #26 | [5 empty] | 55552 | 31849.6 | 15924.8 | 9554.88 | 22294.72 | 134899.2 | 27446.4 | 96000 | 19200
| TRACKER #27 | [5 empty] | 4702 | 4702 | 9678.5 | 9678.5 | 2351 | 3702 |  | 2327.5 | 2327.5
| INVOICE #27 | [5 empty] | 240742.4 | 15046.4 | 30971.2 | 18582.72 | 10532.48 | 284313.6 |  | 44688 | 89376
| TRACKER #28 | [12 empty] | 2625.5 | 2625.5 | 9953 | 9953
| INVOICE #28 | [12 empty] | 50409.6 | 100819.2 | 95548.8 | 95548.8
| TRACKER #29 | [10 empty] | 700 | 2500 | 2500 | 2500 | 2500 | 2500 | 9953
| INVOICE #29 | [10 empty] | 53760 | 72000 | 48000 | 96000 | 24000 | 24000 | 95548.8
| TRACKER #30 | [11 empty] | 1518 | 1518 | 1518 | 1518
| INVOICE #30 | [11 empty] | 43718.4 | 29145.6 | 58291.2 | 14572.8
| TRACKER #32 | [15 empty] | 1518 | 4018
| INVOICE #32 | [15 empty] | 14572.8 | 38572.8
| TRACKER #33 | [11 empty] | 384 | 384 | 384 | 384 | 384 | 384 | 14355 | 14355
| INVOICE #33 | [11 empty] | 11059.2 | 7372.8 | 14745.6 | 3686.4 | 3686.4 | 3686.4 | 413424 | 45936
| Overall Completion TRACKER | [5 empty] | 14655 | 14655 | 14655 | 14655 | 7327.5 | 14355 | 14355 | 14355 | 14355 | 14355 | 14355 | 14355 | 14355 | 14355 | 0
| Overall Completion INVOICE | [5 empty] | 750336 | 46896 | 46896 | 28137.6 | 32827.2 | 1102464 | 413424 | 275616 | 551232 | 137808 | 137808 | 137808 | 413424 | 45936 | 0
| Tot.Procument | [5 empty] | 905092.8
| Tot.implementation | [5 empty] | 2756160
| Tot(T&C / Configuration+Handover) | [5 empty] | 459360
| ToT.Overall Completion INVOICE | [5 empty] | 4120612.8
| Overall Completion percentage | [5 empty] | 87.87%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-005 to BQ-058 | لاغي | 1 | -1 | عدد | 5219395 | -5219395 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-059 | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺩﺍﺧﻠﻳﺔ ﻋﻠﻰ ﺷﻛﻝ ﻗﺑﺔ ( CIDX ) Internal Fixed Mini Dome Camera | 1 | 1 | عدد | 2600 | 2600 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 1
| INVOICE #13 | [5 empty] | 1430
| TRACKER #25 | [6 empty] | 1 |  | 1
| INVOICE #25 | [6 empty] | 325 |  | 65
| TRACKER #27 | [9 empty] | 1
| INVOICE #27 | [9 empty] | 65
| TRACKER #28 | [7 empty] | 1 |  |  | 1
| INVOICE #28 | [7 empty] | 130 |  |  | 65
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1430 | 325 | 130 | 65 | 65 | 65 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1430
| Tot.implementation | [5 empty] | 650
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 2080
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-060 | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ ( CEFX ) External Fixed Camera | 2 | 2 | عدد | 3200 | 6400 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 2
| INVOICE #13 | [5 empty] | 3520
| TRACKER #25 | [6 empty] | 1 |  | 1
| INVOICE #25 | [6 empty] | 400 |  | 80
| TRACKER #27 | [9 empty] | 1
| INVOICE #27 | [9 empty] | 80
| TRACKER #28 | [6 empty] | 1 | 2 | 1 | 1 | 2
| INVOICE #28 | [6 empty] | 400 | 320 | 80 | 80 | 160
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 3520 | 800 | 320 | 160 | 160 | 160 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 3520
| Tot.implementation | [5 empty] | 1600
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 5120
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-061 | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | 14 | 14 | عدد | 2900 | 40600 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #12 | [5 empty] | 14
| INVOICE #12 | [5 empty] | 22330
| TRACKER #25 | [6 empty] | 14 |  | 14
| INVOICE #25 | [6 empty] | 5075 |  | 1015
| TRACKER #27 | [9 empty] | 14
| INVOICE #27 | [9 empty] | 1015
| TRACKER #28 | [7 empty] | 14 |  |  | 14
| INVOICE #28 | [7 empty] | 2030 |  |  | 1015
| Overall Completion TRACKER | [5 empty] | 14 | 14 | 14 | 14 | 14 | 14 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 22330 | 5075 | 2030 | 1015 | 1015 | 1015 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 22330
| Tot.implementation | [5 empty] | 10150
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 32480
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-062 | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intecom Call Panel | 1 | 1 | عدد | 4950 | 4950 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 |  | 1
| INVOICE #27 | [5 empty] | 2722.5 |  | 247.5
| TRACKER #28 | [6 empty] | 1 |  | 1 | 1
| INVOICE #28 | [6 empty] | 742.5 |  | 123.75 | 123.75
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 2722.5 | 742.5 | 247.5 | 123.75 | 123.75 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 2722.5
| Tot.implementation | [5 empty] | 1237.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 3960
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-063 | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | 14 | 14 | عدد | 3160 | 44240 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 14
| INVOICE #13 | [5 empty] | 24332
| TRACKER #25 | [6 empty] | 14 |  | 14
| INVOICE #25 | [6 empty] | 6636 |  | 1106
| TRACKER #30 | [7 empty] | 14 |  | 14
| INVOICE #30 | [7 empty] | 2212 |  | 1106
| Overall Completion TRACKER | [5 empty] | 14 | 14 | 14 | 14 | 14 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 24332 | 6636 | 2212 | 1106 | 1106 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 24332
| Tot.implementation | [5 empty] | 11060
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 35392
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-064 | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Generic Electric Lock | 7 | 7 | عدد | 1200 | 8400 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 7
| INVOICE #14 | [5 empty] | 4620
| TRACKER #25 | [6 empty] | 7 |  | 7
| INVOICE #25 | [6 empty] | 1260 |  | 210
| TRACKER #30 | [7 empty] | 7 |  | 7
| INVOICE #30 | [7 empty] | 420 |  | 210
| Overall Completion TRACKER | [5 empty] | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 4620 | 1260 | 420 | 210 | 210 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 4620
| Tot.implementation | [5 empty] | 2100
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 6720
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-065 | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) Emergency Break Glass Unit | 7 | 7 | عدد | 240 | 1680 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 7
| INVOICE #14 | [5 empty] | 924
| TRACKER #25 | [6 empty] | 7 |  | 7
| INVOICE #25 | [6 empty] | 252 |  | 42
| TRACKER #30 | [7 empty] | 7 |  | 7
| INVOICE #30 | [7 empty] | 84 |  | 42
| Overall Completion TRACKER | [5 empty] | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 924 | 252 | 84 | 42 | 42 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 924
| Tot.implementation | [5 empty] | 420
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1344
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | B.Q QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-066 | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | 9 | 9 | عدد | 190 | 1710 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 9
| INVOICE #14 | [5 empty] | 940.5
| TRACKER #25 | [6 empty] | 7.02 |  | 7.02
| INVOICE #25 | [6 empty] | 200.07 |  | 33.345
| TRACKER #27 | [6 empty] | 1.98 |  | 1.98
| INVOICE #27 | [6 empty] | 56.43 |  | 9.405
| TRACKER #30 | [7 empty] | 9 |  | 9
| INVOICE #30 | [7 empty] | 85.5 |  | 42.75
| Overall Completion TRACKER | [5 empty] | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 940.5 | 256.5 | 85.5 | 42.75 | 42.75 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 940.5
| Tot.implementation | [5 empty] | 427.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1368
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | B.Q QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-067 | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required | 1 | 1 | عدد | 97600 | 97600 |  | Cabinet / Rack | UPS Installation | Batteries Installation | Cabling & Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 30% | 30% | 20% | 10% | 10% | 90% | 10%
| TRACKER #26 | [5 empty] | 1
| INVOICE #26 | [5 empty] | 68320
| TRACKER #29 | [6 empty] | 1 | 1 | 1 | 1
| INVOICE #29 | [6 empty] | 2928 | 2928 | 1952 | 976
| TRACKER #31 | [10 empty] | 1
| INVOICE #31 | [10 empty] | 976
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 68320 | 2928 | 2928 | 1952 | 976 | 976 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 68320
| Tot.implementation | [5 empty] | 9760
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 78080
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-068 | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻠﻧﻅﺎﻡ ﺍﻻﻣﻧﻲ ISS Work Station | 3 | 3 | عدد | 6200 | 18600 |  | Workstation Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #16 | [5 empty] | 3
| INVOICE #16 | [5 empty] | 13020
| TRACKER #28 | [6 empty] | 3 |  | 3
| INVOICE #28 | [6 empty] | 930 |  | 372
| TRACKER #30 | [7 empty] | 3 |  | 3
| INVOICE #30 | [7 empty] | 372 |  | 186
| Overall Completion TRACKER | [5 empty] | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 13020 | 930 | 372 | 372 | 186 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 13020
| Tot.implementation | [5 empty] | 1860
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 14880
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-069 | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺭﺋﻳﺳﻳﺔ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intercom Master Unit | 3 | 3 | عدد | 5600 | 16800 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 3
| INVOICE #13 | [5 empty] | 9240
| TRACKER #27 | [7 empty] | 3
| INVOICE #27 | [7 empty] | 840
| TRACKER #28 | [6 empty] | 3 |  | 3 | 3
| INVOICE #28 | [6 empty] | 2520 |  | 420 | 420
| Overall Completion TRACKER | [5 empty] | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 9240 | 2520 | 840 | 420 | 420 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 9240
| Tot.implementation | [5 empty] | 4200
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 13440
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-070 | ﻟﻭﺣﺔ ﻣﻔﺎﺗﻳﺢ ﺍﻟﺩﻭﺍﺋﺭ ﺍﻟﺗﻠﻔﺯﻳﻭﻧﻳﺔ ﺍﻟﻣﻐﻠﻘﺔ ( CTKB ) CCTV Keyboard | 3 | 3 | عدد | 1850 | 5550 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #26 | [5 empty] | 3
| INVOICE #26 | [5 empty] | 3885
| TRACKER #28 | [6 empty] | 3 |  | 3
| INVOICE #28 | [6 empty] | 333 |  | 55.5
| TRACKER #32 | [7 empty] | 3 |  | 3
| INVOICE #32 | [7 empty] | 111 |  | 55.5
| Overall Completion TRACKER | [5 empty] | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 3885 | 333 | 111 | 55.5 | 55.5 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 3885
| Tot.implementation | [5 empty] | 555
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 4440
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-071 | ﻫﺎﺗﻑ ( TEL ) Telephone | 2 | 2 | عدد | 2300 | 4600 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 2 |  | 2
| INVOICE #27 | [5 empty] | 3220 |  | 92
| TRACKER #28 | [6 empty] | 2 |  | 2 | 2
| INVOICE #28 | [6 empty] | 276 |  | 46 | 46
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 3220 | 276 | 92 | 46 | 46 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 3220
| Tot.implementation | [5 empty] | 460
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 3680
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-072 | ﺍﻟﺧﻁ ﺍﻟﺳﺎﺧﻥ Hot Line | 2 | 2 | عدد | 2300 | 4600 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 2 |  | 2
| INVOICE #27 | [5 empty] | 3220 |  | 92
| TRACKER #28 | [6 empty] | 2 |  | 2 | 2
| INVOICE #28 | [6 empty] | 276 |  | 46 | 46
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 3220 | 276 | 92 | 46 | 46 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 3220
| Tot.implementation | [5 empty] | 460
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 3680
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-073 | ﺭﺍﺩﻳﻭ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ ( HHR ) Hand Held Radio | 2 | 2 | عدد | 3800 | 7600 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
TRACKER #00
INVOICE #00
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-074 | ﻋﻣﻭﺩ ﺛﺎﺑﺕ ﻟﻣﻧﻊ ﺩﺧﻭﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ - ﺗﺻﻧﻳﻑ -ASTM M50-P1 Crash Rated Static Bollard (ASTM M50-P1 Rated) | 15 | 14 | عدد | 5900 | 82600 |  | Excavation | Foundation Casting | Bollard Installation | Backfilling | RFI / Config. | Acceptance
[8 empty] | 20% | 10% | 60% | 10% | 90% | 10%
| TRACKER #17 | [5 empty] | 14
| INVOICE #17 | [5 empty] | 45430
| TRACKER #19 | [6 empty] | 14 | 14 | 14 | 14
| INVOICE #19 | [6 empty] | 4130 | 2065 | 12390 | 2065
| TRACKER #29 | [10 empty] | 14 | 14
| INVOICE #29 | [10 empty] | 7434 | 826
| TRACKER #30 | [12 empty] | 14
| INVOICE #30 | [12 empty] | 8260
| Overall Completion TRACKER | [5 empty] | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
| Overall Completion INVOICE | [5 empty] | 45430 | 4130 | 2065 | 12390 | 2065 | 7434 | 826 | 8260
| Tot.Procument | [5 empty] | 45430
| Tot.implementation | [5 empty] | 20650
| Tot(T&C / Configuration+Handover) | [5 empty] | 16520
| ToT.Overall Completion INVOICE | [5 empty] | 82600
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  | T&C / Configuration |  | Handover
BQ-075 | ﺑﺎﺏ ﺣﺩﻳﺩﻱ ﻣﻔﺻﻠﻲ ﺫﻭ ﺩﺭﻓﺔ ﻭﺍﺣﺩﺓ ﻣﺗﻭﺍﻓﻖ ﻣﻊ SLSD ) SEC-09 ) | 1 | 1 | عدد | 28500 | 28500 |  | Door sub frames | Door & frames | RFI / Config. | Acceptance
[8 empty] | 40% | 60% | 90% | 10%
| TRACKER #17 | [5 empty] | 1
| INVOICE #17 | [5 empty] | 15675
| TRACKER #18 | [6 empty] | 1 | 1
| INVOICE #18 | [6 empty] | 2850 | 4275
| TRACKER #27 | [8 empty] | 1 | 1
| INVOICE #27 | [8 empty] | 2565 | 285
| TRACKER #28 | [8 empty] | 1 | 1
| INVOICE #28 | [8 empty] | 2565 | 285
| TRACKER #29 | [8 empty] | -1 | -1
| INVOICE #29 | [8 empty] | -2565 | -285
| TRACKER #30 | [10 empty] | 1
| INVOICE #30 | [10 empty] | 2850
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 15675 | 2850 | 4275 | 2565 | 285 | 2850
| Tot.Procument | [5 empty] | 15675
| Tot.implementation | [5 empty] | 7125
| Tot(T&C / Configuration+Handover) | [5 empty] | 5700
| ToT.Overall Completion INVOICE | [5 empty] | 28500
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  | T&C / Configuration |  | Handover
BQ-076 | ﺑﺎﺏ ﺣﺩﻳﺩﻱ ﻣﻔﺻﻠﻲ ﺫﻭ ﺩﺭﻓﺗﻳﻥ ﻣﺗﻭﺍﻓﻖ ﻣﻊ DLSD ) SEC-09 ) Double Leaf Steal Door (compliant with SEC 09 "Doors") | 2 | 2 | عدد | 11355 | 22710 |  | Door sub frames | Door & frames | RFI / Config. | Acceptance
[8 empty] | 40% | 60% | 90% | 10%
| TRACKER #17 | [5 empty] | 2
| INVOICE #17 | [5 empty] | 12490.5
| TRACKER #18 | [6 empty] | 2 | 2
| INVOICE #18 | [6 empty] | 2271 | 3406.5
| TRACKER #27 | [8 empty] | 2 | 2
| INVOICE #27 | [8 empty] | 2043.9 | 227.1
| TRACKER #28 | [8 empty] | 2 | 2
| INVOICE #28 | [8 empty] | 2043.9 | 227.1
| TRACKER #29 | [8 empty] | -2 | -2
| INVOICE #29 | [8 empty] | -2043.9 | -227.1
| TRACKER #30 | [10 empty] | 2
| INVOICE #30 | [10 empty] | 2271
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2
| Overall Completion INVOICE | [5 empty] | 12490.5 | 2271 | 3406.5 | 2043.9 | 227.1 | 2271
| Tot.Procument | [5 empty] | 12490.5
| Tot.implementation | [5 empty] | 5677.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 4542
| ToT.Overall Completion INVOICE | [5 empty] | 22710
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-077 | ﺯﺭ ﺇﻧﺫﺍﺭ ﺍﻟﻁﻭﺍﺭﺉ ( EAB ) Emergency Alarm Button | 1 | 1 | عدد | 220 | 220 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 1
| INVOICE #14 | [5 empty] | 154
| TRACKER #32 | [6 empty] | 1 | 1 | 1 | 1
| INVOICE #32 | [6 empty] | 13.2 | 4.4 | 2.2 | 2.2
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 154 | 13.2 | 4.4 | 2.2 | 2.2 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 154
| Tot.implementation | [5 empty] | 22
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 176
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% |  |  |  | 65% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement |  |  |  | Construction of Scc | [5 empty] | T&C / Configuration |  | Handover
BQ-078 | يشمل إنشاء مبنى جديد لمركز التحكم الأمني ​​، كل ما يلزم من أعمال مدنية وإنشائية و MEP والكهربائية والمعمارية والإضاءة وتكييف الهواء والأثاث ونظام الحماية من الحرائق والاتصالات والعمل وما إلى ذلك وجميع الأعمال اللازمة المطلوبة لإكمال هذا العنصر. Construction of new security control center building include, all necessary Civil, structural, MEP, Electrical, architectural, lighting, AC, furniture , fire protection system, communication, work etc. and all necessary work required to complete this item. | 1 | 1 | عدد | 2890000 | 2890000 | Substructure & Concrete | Super Structure | Construction of Ballistic Wall | Finishing | Stacking | Excavation | Substructure & Concrete | Super structure | Construction of Ballistic Wall | Finishing | RFI / Config. | Acceptance
[7 empty] | 20% | 30% | 10% | 40% | 3% | 10% | 25% | 20% | 10% | 32% | 90% | 10%
TRACKER #06
| INVOICE #06 | [9 empty] | 277078.75
| TRACKER #08 | [9 empty] | 1 | 1 | 1
| INVOICE #08 | [9 empty] | 56355 | 187850 | 192546.25
| TRACKER #11 | [5 empty] | 1 | 1 | [5 empty] | 1
| INVOICE #11 | [5 empty] | 86700 | 130050 | [5 empty] | 375700
| TRACKER #13 | [7 empty] | 1 | [5 empty] | 1
| INVOICE #13 | [7 empty] | 43350 | [5 empty] | 187850
| TRACKER #14 | [8 empty] | 1 | [5 empty] | 1
| INVOICE #14 | [8 empty] | 24709.5 | [5 empty] | 107074.5
TRACKER #17
| INVOICE #17 | [8 empty] | 10837.5 | [5 empty] | 28177.5
TRACKER #18
| INVOICE #18 | [14 empty] | 18785
TRACKER #20
| INVOICE #20 | [8 empty] | 8670 | [5 empty] | 18785
TRACKER #21
| INVOICE #21 | [8 empty] | 8670 | [5 empty] | 37570
TRACKER #22
| INVOICE #22 | [8 empty] | 6502.5 | [5 empty] | 28177.5
TRACKER #23
| INVOICE #23 | [8 empty] | 23842.5 | [5 empty] | 80775.5
TRACKER #24
| INVOICE #24 | [8 empty] | 17340 | [5 empty] | 60112
TRACKER #25
| INVOICE #25 | [8 empty] | 13005 | [5 empty] | 33813
TRACKER #26
| INVOICE #26 | [8 empty] | 33813 | [5 empty] | 84532.5
| TRACKER #27 | [15 empty] | 0.5 | 0.5
| INVOICE #27 | [8 empty] | 26010 | [5 empty] | 69504.5 | 130050 | 14450
| TRACKER #28 | [15 empty] | 0.25 | 0.25
| INVOICE #28 | [15 empty] | 65025 | 7225
| TRACKER #29 | [15 empty] | 0.15 | 0.15
| INVOICE #29 | [15 empty] | 39015 | 4335
| TRACKER #31 | [17 empty] | 1
| INVOICE #31 | [17 empty] | 289000
| TRACKER #32 | [15 empty] | 0.05 | 0.05
| INVOICE #32 | [14 empty] | 33813 | 13005 | 1445
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.95 | 0.95 | 1
| Overall Completion INVOICE | [5 empty] | 86700 | 130050 | 43350 | 173400 | 333433.75 | 187850 | 192546.25 | 375700 | 187850 | 601120 | 247095 | 27455 | 289000
| Tot.Procument | [5 empty] | 433500
| Tot.implementation | [5 empty] | 1878500
| Tot(T&C / Configuration+Handover) | [5 empty] | 563550
| Overall Completion | [5 empty] | 2875550
| Overall Completion Percentage | [5 empty] | 99.5%
| DESCRIPTION Breakdown of Procument finshing Scc Building =40% | [7 empty] | DESCRIPTION Breakdown of Constructiom finshing Scc Building =32%
| Roof insulation and Toilet | 10% |  | 25% | 10837.5 | TRACKER #14 |  |  | Roof insulation and Toilet |  |  | 10% | 25% | 46962.5 | TRACKER #14
| Plumbing foundation |  |  | 15% | 6502.5 | TRACKER #17 |  |  | Plumbing foundation |  |  |  | 15% | 28177.5 | TRACKER #21
| Electrical foundation |  |  | 15% | 6502.5 | (TRACKER #14)*40% |  |  | Electrical foundation |  |  |  | 15% | 28177.5 | (TRACKER #14)*40% |  | (TRACKER #26)*60%
| Hvac foundation |  |  | 15% | 6502.5 | TRACKER #21 |  |  | Hvac foundation |  |  |  | 15% | 28177.5 | TRACKER #17
| Security foundation |  |  | 15% | 6502.5 | (TRACKER #14)*40% |  |  | Security foundation |  |  |  | 15% | 28177.5 | (TRACKER #14)*40% |  | (TRACKER #26)*60%
| Fire alarm foundation |  |  | 15% | 6502.5 | TRACKER #23 |  |  | Fire alarm foundation |  |  |  | 15% | 28177.5 | TRACKER #23
| Interior plastering | 10% |  | 10% | 4335 | TRACKER #20 |  |  | Interior plastering |  |  | 10% | 10% | 18785 | TRACKER #20
| Exterior plastering |  |  | 10% | 4335 | TRACKER #14 |  |  | Exterior plastering |  |  |  | 10% | 18785 | TRACKER #14
| Ceiling |  |  | 10% | 4335 | TRACKER #23 |  |  | Ceiling |  |  |  | 10% | 18785 | TRACKER #23
| Interior paint |  |  | 10% | 4335 | TRACKER #24 |  |  | Interior paint |  |  |  | 10% | 18785 | TRACKER #24
| Exterior paint |  |  | 10% | 4335 | TRACKER #14 |  |  | Exterior paint |  |  |  | 10% | 18785 | TRACKER #14
| Doors and Windows |  |  | 10% | 4335 | TRACKER #17 |  |  | Doors and Windows |  |  |  | 10% | 18785 | TRACKER #18
| Tiles |  |  | 10% | 4335 | TRACKER #20 |  |  | Tiles |  |  |  | 10% | 18785 | TRACKER #21
| Epoxy |  |  | 10% | 4335 | TRACKER #27 |  |  | Epoxy |  |  |  | 10% | 18785 | TRACKER #27
| Raised floor |  |  | 10% | 4335 | TRACKER #24 |  |  | Raised floor |  |  |  | 10% | 18785 | TRACKER #24
| Kerbstone and interlock |  |  | 10% | 4335 | TRACKER #21 |  |  | Kerbstone and interlock |  |  |  | 10% | 18785 | TRACKER #21
| Handrail | 20% |  | 10% | 8670 | TRACKER #24 |  |  | Handrail |  |  | 12% | 10% | 22542 | TRACKER #24
| plumbing finishing |  |  | 15% | 13005 | TRACKER #23 |  |  | plumbing finishing |  |  |  | 15% | 33813 | TRACKER #23
| Electrical finishing |  |  | 15% | 13005 | TRACKER #26 |  |  | Electrical finishing |  |  |  | 15% | 33813 | (TRACKER #26)*75% |  | (TRACKER #27)*25%
| Hvac finishing |  |  | 15% | 13005 | TRACKER #27 |  |  | Hvac finishing |  |  |  | 15% | 33813 | TRACKER #27
| Security finishing |  |  | 15% | 13005 | TRACKER #25 |  |  | Security finishing |  |  |  | 15% | 33813 | TRACKER #25
| Fire alarm finishing |  |  | 15% | 13005 | TRACKER #26 |  |  | Fire alarm finishing |  |  |  | 15% | 33813 | (TRACKER #26)*75% |  | (TRACKER #27)*25%
| Building furniture |  |  | 15% | 13005 | TRACKER #27 |  |  | Building furniture |  |  |  | 15% | 33813 | TRACKER #32
| Total | 40% |  |  | 173400 |  |  |  | Total |  |  | 32% |  | 601120
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-079 | ﺷﺎﺷﺔ ﺟﺩﺍﺭﻳﺔ (ﻓﻳﺩﻳﻭ ﻭﻭﻝ) Operator Dual Screens | 3 | 4 | عدد | 7300 | 29200 |  | Screen's Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #25 | [5 empty] | 3
| INVOICE #25 | [5 empty] | 12045
| TRACKER #28 | [6 empty] | 3 |  | 3 | 3
| INVOICE #28 | [6 empty] | 2737.5 |  | 547.5 | 547.5
| TRACKER #30 | [5 empty] | 1 | 1 | 4 | 1 | 1 | 4
| INVOICE #30 | [5 empty] | 4015 | 912.5 | 1460 | 182.5 | 182.5 | 730
| Overall Completion TRACKER | [5 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 16060 | 3650 | 1460 | 730 | 730 | 730 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 16060
| Tot.implementation | [5 empty] | 7300
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 23360
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-080 | شاشة جدارية ونظام المراقبة بما في ذلك جميع حوامل الشاشات ، وأجهزة التحكم ، وعصا التحكم ، ولوحات مفاتيح الدوائر التلفزيونية المغلقة ، وما إلى ذلك ... (كمية العناصر بناءً على تصميم المقاول وفقًا لـ HCIS) ، Video Wall and monitoring System including all screens brackets, Controllers, Joysticks, CCTV keyboards, etc... (QTY of items based on contractor's design as per HCIS), | 1 | 1 | عدد | 126400 | 126400 |  | Video wall Mounting | Components Installation | Patching & Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #15 | [5 empty] | 1
| INVOICE #15 | [5 empty] | 69520
| TRACKER #30 | [6 empty] | 1 | 1
| INVOICE #30 | [6 empty] | 15800 | 6320
| TRACKER #33 | [8 empty] | 1 | 1 | 1
| INVOICE #33 | [8 empty] | 3160 | 3160 | 3160
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 69520 | 15800 | 6320 | 3160 | 3160 | 3160 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 69520
| Tot.implementation | [5 empty] | 31600
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 101120
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 60% | 20% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-081 | الخوادم والبرمجيات لإدارة ﺍﻟﻧﻅﺎﻡ ﺍﻷﻣﻧﻲ المركزي Fully redundant Central SMS (servers & software) | 1 | 1 | عدد | 1116400 | 1116400 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #15 | [5 empty] | 1
| INVOICE #15 | [5 empty] | 669840
| TRACKER #25 | [6 empty] | 1
| INVOICE #25 | [6 empty] | 133968
| TRACKER #33 | [8 empty] | 1
| INVOICE #33 | [8 empty] | 22328
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 669840 | 133968 | 0 | 22328 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 669840
| Tot.implementation | [5 empty] | 156296
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 826136
| Overall Completion percentage | [5 empty] | 74%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 60% | 20% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-082 | الخوادم والبرمجيات ﻟﻧﻅﺎﻡ ﺍﻟﺩﺍﺭﺍﺕ ﺍﻟﺗﻠﻔﻳﺯﻳﻭﻧﺔ ﺍﻟﻣﻐﻠﻘﺔ ﺍﻟﻣﺭﻛﺯﻱ Fully redundant Central CCTV (servers & software) | 1 | 1 | عدد | 835200 | 835200 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #15 | [5 empty] | 1
| INVOICE #15 | [5 empty] | 501120
| TRACKER #25 | [6 empty] | 1
| INVOICE #25 | [6 empty] | 100224
| TRACKER #33 | [8 empty] | 1
| INVOICE #33 | [8 empty] | 16704
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 501120 | 100224 | 0 | 16704 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 501120
| Tot.implementation | [5 empty] | 116928
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 618048
| Overall Completion percentage | [5 empty] | 74%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 60% | 20% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-083 | الخوادم والبرمجيات ﻟﻧﻅﺎﻡ ﺍﻟﺗﺣﻛﻡ ﻓﻲ ﺍﻟﺩﺧﻭﻝ ﺍﻟﻣﺭﻛﺯﻱ Fully redundant Central ACS (servers & software) | 1 | 1 | عدد | 498000 | 498000 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #15 | [5 empty] | 1
| INVOICE #15 | [5 empty] | 298800
| TRACKER #25 | [6 empty] | 1
| INVOICE #25 | [6 empty] | 59760
| TRACKER #33 | [8 empty] | 1
| INVOICE #33 | [8 empty] | 9960
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 298800 | 59760 | 0 | 9960 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 298800
| Tot.implementation | [5 empty] | 69720
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 368520
| Overall Completion percentage | [5 empty] | 74%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 60% | 20% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-084 | الخوادم والبرمجيات ﻟﻧﻅﺎﻡ ﺍﻧﺫﺍﺭ ﺍﻻﺧﺗﺭﺍﻕ ﺍﻟﻣﺣﻳﻁﻲ ﺍﻟﻣﺭﻛﺯﻱ Fully redundant Central PIDS (servers & software) | 1 | 1 | عدد | 376500 | 376500 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #15 | [5 empty] | 1
| INVOICE #15 | [5 empty] | 225900
| TRACKER #25 | [6 empty] | 1
| INVOICE #25 | [6 empty] | 45180
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 225900 | 45180 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 225900
| Tot.implementation | [5 empty] | 45180
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 271080
| Overall Completion percentage | [5 empty] | 72%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [5 empty] | T&C / Configuration |  | Handover
BQ-085 | نظام تسجيل فيديو مكرر بالكامل ( أجهزة وبرامج ) وفقًا لمتطلبات تسجيل HCIS Fully redundant Video Recording system (Hardware & Software) as per HCIS recording requirements | 1 | 1 | عدد | 532000 | 532000 |  | Rack installations | Servers Installation | Configuration | Cabling & Patching | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 15% | 50% | 10% | 10% | 10% | 5% | 90% | 10%
| TRACKER #15 | [5 empty] | 1
| INVOICE #15 | [5 empty] | 292600
| TRACKER #25 | [6 empty] | 1 | 1
| INVOICE #25 | [6 empty] | 19950 | 66500
| TRACKER #33 | [9 empty] | 1 | 1 | 1
| INVOICE #33 | [9 empty] | 13300 | 13300 | 6650
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 292600 | 19950 | 66500 | 0 | 13300 | 13300 | 6650 | 0 | 0
| Tot.Procument | [5 empty] | 292600
| Tot.implementation | [5 empty] | 113050
| Tot(T&C / Configuration+Handover) | [5 empty] | 1
| ToT.Overall Completion INVOICE | [5 empty] | 405651
| Overall Completion percentage | [5 empty] | 76.25%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-086 | ﺳﻳﺎﺝ ﻣﺿﺎﺩ ﻟﻸﻓﺭﺍﺩ ﺍﻟﻔﺋﺔ 1 Category 1 Anti-personnel Fence | 8868 | 10421 | م.ط | 1480 | 15423080 |  | Excavation | Shuttering & Rebar | Beam Casting | Panels | Concertina | RFI / Config. | Acceptance |  | 8024.17
[8 empty] | 20% | 25% | 25% | 25% | 5% | 90% | 10%
| TRACKER #02 | [5 empty] | 4650
| INVOICE #02 | [5 empty] | 3785100
| TRACKER #03 | [5 empty] | 2602
| INVOICE #03 | [5 empty] | 2118028
| TRACKER #04 | [5 empty] | 973
| INVOICE #04 | [5 empty] | 792022
| TRACKER #06 | [5 empty] | 9
| INVOICE #06 | [5 empty] | 7326
| TRACKER #10 | [6 empty] | 950 | 710 | 710 | 500
| INVOICE #10 | [6 empty] | 70300 | 65675 | 65675 | 46250
| TRACKER #11 | [5 empty] | 620.7689 | 850 | 1090 | 1090 | 290
| INVOICE #11 | [5 empty] | 505305.9172 | 62900 | 100825 | 100825 | 26825
| TRACKER #12 | [6 empty] | 1140 | 1030 | 1030 | 1050
| INVOICE #12 | [6 empty] | 84360 | 95275 | 95275 | 97125
| TRACKER #13 | [6 empty] | 690 | 557 | 557 | 785 | 850
| INVOICE #13 | [6 empty] | 51060 | 51522.5 | 51522.5 | 72612.5 | 15725
| TRACKER #14 | [6 empty] | 1094 | 1090 | 850 | 875
| INVOICE #14 | [6 empty] | 80956 | 100825 | 78625 | 80937.5
| TRACKER #15 | [6 empty] | 850 | 900 | 900 | 842
| INVOICE #15 | [6 empty] | 62900 | 83250 | 83250 | 77885
| TRACKER #16 | [6 empty] | 307 | 504 | 744 | 1510
| INVOICE #16 | [6 empty] | 22718 | 46620 | 68820 | 139675
| TRACKER #17 | [6 empty] | 300 | 300 | 300 | 200
| INVOICE #17 | [6 empty] | 22200 | 27750 | 27750 | 18500
| TRACKER #18 | [6 empty] | 71 | 71 | 71 | 171 | 700
| INVOICE #18 | [6 empty] | 5254 | 6567.5 | 6567.5 | 15817.5 | 12950
| TRACKER #19 | [6 empty] | 147 | 147 | 147
| INVOICE #19 | [6 empty] | 10878 | 13597.5 | 13597.5
| TRACKER #21 | [6 empty] | 54 | 54 | 54 | 96
| INVOICE #21 | [6 empty] | 3996 | 4995 | 4995 | 8880
| TRACKER #22 | [6 empty] | 988 | 988 | 988 | 391
| INVOICE #22 | [6 empty] | 73112 | 91390 | 91390 | 36167.5
| TRACKER #23 | [6 empty] | 642 | 642 | 642 | 672
| INVOICE #23 | [6 empty] | 47508 | 59385 | 59385 | 62160
| TRACKER #24 | [6 empty] | 252 | 252 | 252 | 750
| INVOICE #24 | [6 empty] | 18648 | 23310 | 23310 | 69375
| TRACKER #25 | [9 empty] | 203
| INVOICE #25 | [9 empty] | 18777.5
| TRACKER #26 | [5 empty] | 13.2311
| INVOICE #26 | [5 empty] | 10770.0828
| TRACKER #27 | [5 empty] | 1469 | 1428 | 1428 | 1428 | 1100 | 4400 | 4543 | 4543
| INVOICE #27 | [5 empty] | 1195766 | 105672 | 132090 | 132090 | 101750 | 81400 | 605127.6 | 67236.4
| TRACKER #28 | [6 empty] | 248 | 248 | 248 | 525.14
| INVOICE #28 | [6 empty] | 18352 | 22940 | 22940 | 48575.45
| TRACKER #30 | [13 empty] | 4543
| INVOICE #30 | [13 empty] | 672364
| TRACKER #32 | [9 empty] | 50.86
| INVOICE #32 | [9 empty] | 4704.55
| TRACKER #33 | [6 empty] | 280 | 280 | 280 | 280
| INVOICE #33 | [6 empty] | 20720 | 25900 | 25900 | 25900
| Overall Completion TRACKER | [5 empty] | 10337 | 10291 | 10291 | 10291 | 10291 | 5950 | 4543 | 4543 | 4543
| Overall Completion INVOICE | [5 empty] | 8414318 | 761534 | 951917.5 | 951917.5 | 951917.5 | 110075 | 605127.6 | 67236.4 | 672364
| Tot.Procument | [5 empty] | 8414318
| Tot.implementation | [5 empty] | 3727361.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 1344728
| ToT.Overall Completion INVOICE | [5 empty] | 13486407.5
| Overall Completion percentage | [5 empty] | 87.44%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-087 | Anti Vehcile Barrier حاجز مضاد المركبات | 3136 | 4396 | م.ط | 1120 | 4923520 |  | Excavation | Casting Foundations | AVB post Instl. | Beam/Rope Installation | BF & Compaction | RFI / Config. | Acceptance
[8 empty] | 25% | 15% | 25% | 25% | 10% | 90% | 10%
| TRACKER #03 | [5 empty] | 2239
| INVOICE #03 | [5 empty] | 1379224
| TRACKER #06 | [5 empty] | 897
| INVOICE #06 | [5 empty] | 552552
| TRACKER #17 | [6 empty] | 462 | 462 | 462 |  | 462
| INVOICE #17 | [6 empty] | 32340 | 19404 | 32340 |  | 12936
| TRACKER #18 | [6 empty] | 490 | 250 | 250 |  | 250
| INVOICE #18 | [6 empty] | 34300 | 10500 | 17500 |  | 7000
| TRACKER #19 | [7 empty] | 20 | 20 |  | 20
| INVOICE #19 | [7 empty] | 840 | 1400 |  | 560
| TRACKER #20 | [6 empty] | 162
| INVOICE #20 | [6 empty] | 11340
| TRACKER #21 | [6 empty] | 618 | 1000 | 1000
| INVOICE #21 | [6 empty] | 43260 | 42000 | 70000
| TRACKER #22 | [6 empty] | 356 | 356 | 356 |  | 820
| INVOICE #22 | [6 empty] | 24920 | 14952 | 24920 |  | 22960
| TRACKER #23 | [6 empty] | 414 | 414 | 414 |  | 764
| INVOICE #23 | [6 empty] | 28980 | 17388 | 28980 |  | 21392
| TRACKER #24 | [6 empty] | 300 | 300 | 300 |  | 286
| INVOICE #24 | [6 empty] | 21000 | 12600 | 21000 |  | 8008
| TRACKER #25 | [6 empty] | 61 | 61 | 61
| INVOICE #25 | [6 empty] | 4270 | 2562 | 4270
| TRACKER #26 | [10 empty] | 261
| INVOICE #26 | [10 empty] | 7308
| TRACKER #27 | [5 empty] | 1176 | 1029 | 1029 | 1029 | 0 | 1029
| INVOICE #27 | [5 empty] | 724416 | 72030 | 43218 | 72030 | 0 | 28812
| TRACKER #28 | [6 empty] | 144 | 144 | 144 | 732 | 144 | 732 | 732
| INVOICE #28 | [6 empty] | 10080 | 6048 | 10080 | 51240 | 4032 | 73785.6 | 8198.4
| TRACKER #30 | [9 empty] | 500 |  |  |  | 732
| INVOICE #30 | [9 empty] | 35000 |  |  |  | 81984
| TRACKER #31 | [5 empty] | 4 | 48 |  |  | 910 |  | 1410 | 1410 | 1410
| INVOICE #31 | [5 empty] | 2464 | 3360 |  |  | 63700 |  | 142128 | 15792 | 157920
| TRACKER #32 | [6 empty] | 108 | 156 | 156 | 1880
| INVOICE #32 | [6 empty] | 7560 | 6552 | 10920 | 131600
| TRACKER #32 | [6 empty] | 124 | 124 | 124 | 114 | 100 | 1994 | 1994
| INVOICE #32 | [6 empty] | 8680 | 5208 | 8680 | 7980 | 2800 | 200995.2 | 22332.8
| Overall Completion TRACKER | [5 empty] | 4316 | 4316 | 4316 | 4316 | 4136 | 4136 | 4136 | 4136 | 2142
| Overall Completion INVOICE | [5 empty] | 2658656 | 302120 | 181272 | 302120 | 289520 | 115808 | 416908.8 | 46323.2 | 239904
| Tot.Procument | [5 empty] | 2658656
| Tot.implementation | [5 empty] | 1190840
| Tot(T&C / Configuration+Handover) | [5 empty] | 703136
| ToT.Overall Completion INVOICE | [5 empty] | 4552632
| Overall Completion | [5 empty] | 92.47%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% |  |  |  | 65% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement |  |  |  | CONSTRUCTION | [5 empty] | T&C / Configuration |  | Handover
BQ-088 | ﻁﺭﻳﻖ ﺍﻟﺩﻭﺭﻳات الداخلية Inner Patrol Road | 4370 | 5350 | م.ط | 650 | 3477500 | Subase | Base Coarse | Asphalt 1st | Asphalt 2nd | Site prep. | Backfilling/ Levelling | Sub Base | Base Course | Asphalt Layer 1 | Asphalt Layer 2 | RFI / Config. | Acceptance
[7 empty] | 20% | 25% | 35% | 20% | 5% | 15% | 20% | 10% | 25% | 25% | 90% | 10%
| TRACKER #05 | [9 empty] | 1311
| INVOICE #05 | [9 empty] | 27694.875
| TRACKER #06 | [10 empty] | 1300
| INVOICE #06 | [10 empty] | 82387.5
| TRACKER #07 | [10 empty] | 1950 | 700
| INVOICE #07 | [10 empty] | 123581.25 | 59150
| TRACKER #08 | [9 empty] | 2650 | 700 | 2550 | 1000
| INVOICE #08 | [9 empty] | 55981.25 | 44362.5 | 215475 | 42250
| TRACKER #09 | [5 empty] | 3250 | 2650 | [5 empty] | 1650
| INVOICE #09 | [5 empty] | 63375 | 64593.75 | [5 empty] | 69712.5
| TRACKER #10 | [5 empty] | 750 | 600 |  |  |  |  | 750 | 600
| INVOICE #10 | [5 empty] | 14625 | 14625 |  |  |  |  | 63375 | 25350
| TRACKER #11 | [5 empty] | 65 | 815 |  |  | 65 | 65 | 65 | 815
| INVOICE #11 | [5 empty] | 1267.5 | 19865.625 |  |  | 1373.125 | 4119.375 | 5492.5 | 34433.75
| TRACKER #13 | [7 empty] | 3915 |  | 344 | 355 |  |  | 3915
| INVOICE #13 | [7 empty] | 133599.375 |  | 7267 | 22498.125 |  |  | 413521.875
| TRACKER #14 | [5 empty] | 305 | [5 empty] | 305
| INVOICE #14 | [5 empty] | 5947.5 | [5 empty] | 25772.5
| TRACKER #16 | [6 empty] | 305 |  | 3200 |  |  |  | 305 |  | 3200
| INVOICE #16 | [6 empty] | 7434.375 |  | 62400 |  |  |  | 12886.25 |  | 338000
| TRACKER #17 | [7 empty] | 455 | 1170 |  |  |  |  | 455 | 1170
| INVOICE #17 | [7 empty] | 15526.875 | 22815 |  |  |  |  | 48059.375 | 123581.25
| TRACKER #24 | [15 empty] | 4370 | 4370
| INVOICE #24 | [15 empty] | 255645 | 28405
| TRACKER #27 | [5 empty] | 434 | 434 | 434 | 434 | 434 | 434 | 434 | 434 | 434 | 434 | 434 | 434
| INVOICE #27 | [5 empty] | 8463 | 10578.75 | 14810.25 | 8463 | 9168.25 | 27504.75 | 36673 | 18336.5 | 45841.25 | 45841.25 | 25389 | 2821
| TRACKER #30 | [17 empty] | 4804
| INVOICE #30 | [17 empty] | 312260
| TRACKER #31 | [5 empty] | 546 | 546 | 546 | 546 | 546 | 546 | 546 | 546
| INVOICE #31 | [5 empty] | 10647 | 13308.75 | 18632.25 | 10647 | 11534.25 | 34602.75 | 46137 | 23068.5
| TRACKER #32 | [13 empty] | 546
| INVOICE #32 | [13 empty] | 57671.25
| TRACKER #33 | [14 empty] | 546 | 546 | 546
| INVOICE #33 | [14 empty] | 57671.25 | 31941 | 3549
| Overall Completion TRACKER | [5 empty] | 5350 | 5350 | 5350 | 5350 | 5350 | 5350 | 5350 | 5350 | 5350 | 5350 | 5350 | 5350 | 4804
| Overall Completion INVOICE | [5 empty] | 104325 | 130406.25 | 182568.75 | 104325 | 113018.75 | 339056.25 | 452075 | 226037.5 | 565093.75 | 565093.75 | 312975 | 34775 | 312260
| Tot.Procument | [5 empty] | 521625
| Tot.implementation | [5 empty] | 2260375
| Tot(T&C / Configuration+Handover) | [5 empty] | 660010
| ToT.Overall Completion INVOICE | [5 empty] | 3442010
| Overall Completion Percentage | [5 empty] | 98.98%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% |  |  |  | 65% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement |  |  |  | CONSTRUCTION | [5 empty] | T&C / Configuration |  | Handover
BQ-089 | ﻁﺭﻳﻖ ﺍﻟﺩﻭﺭﻳﺎﺕ الخارجية Outer Patrol Road | 3190 | 3610 | م.ط | 650 | 2346500 | Subase | Base Coarse | Asphalt 1st | Asphalt 2nd | Site prep. | Backfilling/ Levelling | Sub Base | Base Course | Asphalt Layer 1 | Asphalt Layer 2 | RFI / Config. | Acceptance
[7 empty] | 20% | 25% | 35% | 20% | 5% | 15% | 20% | 10% | 25% | 25% | 90% | 10%
| TRACKER #23 | [5 empty] | 200 |  |  |  | 200 | 200
| INVOICE #23 | [5 empty] | 3900 |  |  |  | 4225 | 12675
| TRACKER #24 | [5 empty] | 2000 | 2000 | 1300 |  | 2000 | 2000 | 2000 | 1500 | 1300
| INVOICE #24 | [5 empty] | 39000 | 48750 | 44362.5 |  | 42250 | 126750 | 169000 | 63375 | 137312.5
| TRACKER #25 | [5 empty] | 990 | 650 | 1350 |  | 990 | 990 | 650 | 1150 | 1350
| INVOICE #25 | [5 empty] | 19305 | 15843.75 | 46068.75 |  | 20913.75 | 62741.25 | 54925 | 48587.5 | 142593.75
| TRACKER #26 | [6 empty] | 540 | 540 | 3190 |  |  | 540 | 540 | 540 | 3190 | 3190 | 3190
| INVOICE #26 | [6 empty] | 13162.5 | 18427.5 | 62205 |  |  | 45630 | 22815 | 57037.5 | 336943.75 | 186615 | 20735
| TRACKER #27 | [5 empty] | 345 | 345 | 345 | 345 | 345 | 345 | 345 | 345 | 345 | 345 | 345 | 345
| INVOICE #27 | [5 empty] | 6727.5 | 8409.375 | 11773.125 | 6727.5 | 7288.125 | 21864.375 | 29152.5 | 14576.25 | 36440.625 | 36440.625 | 20182.5 | 2242.5
| TRACKER #30 | [17 empty] | 3535
| INVOICE #30 | [17 empty] | 229775
| TRACKER #32 | [5 empty] | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
| INVOICE #32 | [5 empty] | 585 | 731.25 | 1023.75 | 585 | 633.75 | 1901.25 | 2535 | 1267.5 | 3168.75
| TRACKER #33 | [5 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 75 | 75 | 75
| INVOICE #33 | [5 empty] | 877.5 | 1096.875 | 1535.625 | 877.5 | 950.625 | 2851.875 | 3802.5 | 1901.25 | 4753.125 | 7921.875 | 4387.5 | 487.5
| Overall Completion TRACKER | [5 empty] | 3610 | 3610 | 3610 | 3610 | 3610 | 3610 | 3610 | 3610 | 3610 | 3610 | 3610 | 3610 | 3535
| Overall Completion INVOICE | [5 empty] | 70395 | 87993.75 | 123191.25 | 70395 | 76261.25 | 228783.75 | 305045 | 152522.5 | 381306.25 | 381306.25 | 211185 | 23465 | 229775
| Tot.Procument | [5 empty] | 351975
| Tot.implementation | [5 empty] | 1525225
| Tot(T&C / Configuration+Handover) | [5 empty] | 464425
| ToT.Overall Completion INVOICE | [5 empty] | 2341625
| Overall Completion | [5 empty] | 99.79%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% | [6 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [6 empty] | T&C / Configuration |  | Handover
BQ-090 | ﻛﺎﻣﻳﺭﺍ ﺣﺭﺍﺭﻳﺔ ﻁﻭﻳﻠﺔ ﺍﻟﻣﺩﻯ ( LRTC ) Long Range Thermal Camera | 4 | 4 | عدد | 196800 | 787200 |  | Excavation | Precast foundt'n | Pole Installation | Backfilling & Alignment | Camera Mounting | Cabling & Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 10% | 10% | 10% | 10% | 40% | 10% | 10% | 90% | 10%
| TRACKER #16 | [5 empty] | 1
| INVOICE #16 | [5 empty] | 137760
| TRACKER #23 | [5 empty] | 3
| INVOICE #23 | [5 empty] | 413280
| TRACKER #27 | [6 empty] | 4 | 4
| INVOICE #27 | [6 empty] | 7872 | 7872
| TRACKER #30 | [8 empty] | 4 |  | 4
| INVOICE #30 | [8 empty] | 7872 |  | 31488
| TRACKER #32 | [9 empty] | 4 |  | 4
| INVOICE #32 | [9 empty] | 7872 |  | 7872
| Overall Completion TRACKER | [5 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 551040 | 7872 | 7872 | 7872 | 7872 | 31488 | 7872 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 551040
| Tot.implementation | [5 empty] | 70848
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 621888
| Overall Completion percentage | [5 empty] | 79%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 80% |  |  |  | 5% | [6 empty] | 10% |  | 5%
[7 empty] | Procurement |  |  |  | CONSTRUCTION | [6 empty] | T&C / Configuration |  | Handover
BQ-091 | الرادار Radar | 2 | 2 | عدد | 543200 | 1086400 | Foundation | Pole | Software | Radar System | Excavation | Precast foundt'n | Pole Installation | Backfilling & Alignment | Radar Mounting | Cabling & Termination | Testing | RFI / Config. | Acceptance
[7 empty] | 5% | 5% | 10% | 80% | 10% | 10% | 10% | 10% | 40% | 10% | 10% | 90% | 10%
| TRACKER #16 | [8 empty] | 2
| INVOICE #16 | [8 empty] | 695296
| TRACKER #27 | [9 empty] | 2 | 2
| INVOICE #27 | [9 empty] | 5432 | 5432
| TRACKER #30 | [11 empty] | 2 |  | 2
| INVOICE #30 | [11 empty] | 5432 |  | 21728
| TRACKER #32 | [5 empty] | 2 | 2 | 2 |  |  |  |  | 2 |  | 2
| INVOICE #32 | [5 empty] | 43456 | 43456 | 86912 |  |  |  |  | 5432 |  | 5432
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 43456 | 43456 | 86912 | 695296 | 5432 | 5432 | 5432 | 5432 | 21728 | 5432 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 869120
| Tot.implementation | [5 empty] | 48888
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 918008
| Overall Completion percentage | [5 empty] | 84.5%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-092 | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ External Fixed Camera | 138 | 170 | عدد | 3199 | 543830 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #12 | [5 empty] | 84
| INVOICE #12 | [5 empty] | 147793.8
| TRACKER #13 | [5 empty] | 54
| INVOICE #13 | [5 empty] | 95010.3
| TRACKER #27 | [5 empty] | 32 | 135 | 170 | 140 | 135
| INVOICE #27 | [5 empty] | 56302.4 | 53983.125 | 27191.5 | 11196.5 | 10796.625
| TRACKER #28 | [6 empty] | 10 |  | 30 | 10
| INVOICE #28 | [6 empty] | 3998.75 |  | 2399.25 | 799.75
| TRACKER #29 | [6 empty] | 10 |  |  | 10
| INVOICE #29 | [6 empty] | 3998.75 |  |  | 799.75
| TRACKER #32 | [6 empty] | 10 |  |  | 10 | 165
| INVOICE #32 | [6 empty] | 3998.75 |  |  | 799.75 | 13195.875
| Overall Completion TRACKER | [5 empty] | 170 | 165 | 170 | 170 | 165 | 165 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 299106.5 | 65979.375 | 27191.5 | 13595.75 | 13195.875 | 13195.875 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 299106.5
| Tot.implementation | [5 empty] | 133158.375
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 432264.875
| Overall Completion percentage | [5 empty] | 79.49%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-093 | ﻛﺎﻣﻳﺭﺍ ﻣﺗﺣﺭﻛﺔ ﺧﺎﺭﺟﻳﺔ Camera External PTZ | 24 | 24 | عدد | 8400 | 201600 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #12 | [5 empty] | 4
| INVOICE #12 | [5 empty] | 18480
| TRACKER #13 | [5 empty] | 13
| INVOICE #13 | [5 empty] | 60060
| TRACKER #27 | [5 empty] | -4 | 3 | 13 | 11 | 3
| INVOICE #27 | [5 empty] | -18480 | 3150 | 5460 | 2310 | 630
| TRACKER #28 | [6 empty] | 6 |  | 8 | 6
| INVOICE #28 | [6 empty] | 6300 |  | 1680 | 1260
| TRACKER #29 | [6 empty] | 3 |  | 3 | 3
| INVOICE #29 | [6 empty] | 3150 |  | 630 | 630
| TRACKER #32 | [5 empty] | 11 | 9 | 11 |  | 9 | 19
| INVOICE #32 | [5 empty] | 50820 | 9450 | 4620 |  | 1890 | 3990
| TRACKER #33 | [6 empty] | 2 | -1 | 1 | 2 | 4
| INVOICE #33 | [6 empty] | 2100 | -420 | 210 | 420 | 840
| Overall Completion TRACKER | [5 empty] | 24 | 23 | 23 | 23 | 23 | 23 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 110880 | 24150 | 9660 | 4830 | 4830 | 4830 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 110880
| Tot.implementation | [5 empty] | 48300
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 159180
| Overall Completion percentage | [5 empty] | 78.96%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | [5 empty] | 25% | [6 empty] | 10% |  | 10%
[7 empty] | Procurement | [5 empty] | CONSTRUCTION | [6 empty] | T&C / Configuration |  | Handover
BQ-094 | ﺍﻻﻧﺎﺭﺓ ﺍﻷﻣﻧﻳﺔ ﺍﻟﻣﺣﻳﻁﺔ Perimeter Security Lighting system (including all power cabling, lighting fixtures, distribution network, panels, accessories and all related electrical, control, civil and earth work and all necessary work to complete this item) | 443 | 528 | عدد | 8700 | 4593600 | FIXTURE | POLE | CABLE | CONTROL PANEL | FUSE AND BREAKER | FOUNDATION BASE | Excavation | Casting Foundations | Pole Installation | Lighting Fixtures | Component Installation | Cabling & Termination | BF & Compaction | RFI / Config. | Acceptance
[7 empty] | 36% | 25% | 24% | 8% | 2% | 5% | 20% | 15% | 10% | 10% | 25% | 10% | 10% | 90% | 10%
| TRACKER #09 | [5 empty] | 443
| INVOICE #09 | [5 empty] | 763111.8
| TRACKER #14 | [7 empty] | 310.1
| INVOICE #14 | [7 empty] | 356118.84
| TRACKER #17 | [10 empty] | 99
| INVOICE #17 | [10 empty] | 23685.75
| TRACKER #18 | [10 empty] | 70
| INVOICE #18 | [10 empty] | 16747.5
| TRACKER #19 | [10 empty] | 122
| INVOICE #19 | [10 empty] | 29188.5
| TRACKER #20 | [10 empty] | 93 | 259 | 236
| INVOICE #20 | [10 empty] | 22250.25 | 112665 | 76995
| TRACKER #21 | [10 empty] | 59 |  | 16
| INVOICE #21 | [10 empty] | 14115.75 |  | 5220
| TRACKER #22 | [6 empty] | 176 | 88.6
| INVOICE #22 | [6 empty] | 210540 | 101748.24
| TRACKER #23 | [6 empty] | 267
| INVOICE #23 | [6 empty] | 319398.75
| TRACKER #24 | [8 empty] | 443 |  |  | 81 | 88 | 340 | 340
| INVOICE #24 | [8 empty] | 169580.4 |  |  | 35235 | 28710 | 73950 | 73950
| TRACKER #25 | [11 empty] | 56 | 56 | 56 | 56
| INVOICE #25 | [11 empty] | 24360 | 18270 | 12180 | 12180
| TRACKER #26 | [7 empty] | 44.3 |  |  |  | 47 | 47 | 47 | 47 |  | 220 | 220
| INVOICE #26 | [7 empty] | 50874.12 |  |  |  | 20445 | 15333.75 | 10222.5 | 10222.5 |  | 47850 | 47850
| TRACKER #27 | [5 empty] | 85 | 85 | 85 | 85 | 528 | 85 | 12 | 12 | 12 | 12 | 455 | 235
| INVOICE #27 | [5 empty] | 146421 | 101681.25 | 97614 | 32538 | 50529.6 | 20336.25 | 5220 | 3915 | 2610 | 2610 | 247406.25 | 51112.5
| TRACKER #28 | [11 empty] | 27 | 69
| INVOICE #28 | [11 empty] | 11745 | 22511.25
| TRACKER #29 | [11 empty] | 13 |  | 40 | 40 | 40 | 40
| INVOICE #29 | [11 empty] | 5655 |  | 8700 | 8700 | 21750 | 8700
| TRACKER #32 | [17 empty] | 236 | 410 | 410
| INVOICE #32 | [17 empty] | 51330 | 321030 | 35670 |  | 0
| TRACKER #32 | [11 empty] | 2 |  | 2 | 2 | 2 | 2 | 41 | 87 | 87
| INVOICE #32 | [11 empty] | 870 |  | 435 | 435 | 1087.5 | 435 | 8917.5 | 68121 | 7569 |  | 870
| Overall Completion TRACKER | [5 empty] | 528 | 528 | 528 | 528 | 528 | 528 | 497 | 524 | 497 | 497 | 497 | 497 | 497 | 497 | 497 | 0
| Overall Completion INVOICE | [5 empty] | 909532.8 | 631620 | 606355.2 | 202118.4 | 50529.6 | 126324 | 216195 | 170955 | 108097.5 | 108097.5 | 270243.75 | 108097.5 | 108097.5 | 389151 | 43239 | 0
| Tot.Procument | [5 empty] | 2526480
| Tot.implementation | [5 empty] | 1089783.75
| Tot(T&C / Configuration+Handover) | [5 empty] | 432390
| ToT.Overall Completion INVOICE | [5 empty] | 4048653.75
| Overall Completion Percentage | [5 empty] | 88.14%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% |  | 25% | [6 empty] | 10% |  | 10%
[7 empty] | Procurement |  | CONSTRUCTION | [6 empty] | T&C / Configuration |  | Handover
BQ-095 | عمود كاميرا CCTV Pole | 162 | 182 | عدد | 1649 | 300118 | POLE | FOUNDATION BASE | Precasting Foundations | Excavation | Lean Conc. | Foundation Installation | Pole Installation | BF & Compaction | Pole Alignment | RFI / Config. | Acceptance
[7 empty] | 60% | 40% | 20% | 20% | 10% | 10% | 25% | 10% | 5% | 90% | 10%
| TRACKER #17 | [6 empty] | 34
| INVOICE #17 | [6 empty] | 12334.52
| TRACKER #18 | [6 empty] | 9
| INVOICE #18 | [6 empty] | 3265.02
| TRACKER #19 | [6 empty] | 32
| INVOICE #19 | [6 empty] | 11608.96
| TRACKER #20 | [6 empty] | 87 | 162 | 74 | 74 | 68
| INVOICE #20 | [6 empty] | 31561.86 | 13356.9 | 6101.3 | 3050.65 | 2803.3
| TRACKER #21 | [10 empty] | 6
| INVOICE #21 | [10 empty] | 247.35
| TRACKER #22 | [5 empty] | 48
| INVOICE #22 | [5 empty] | 26120.16
| TRACKER #23 | [5 empty] | 94 |  |  | 30 | 30
| INVOICE #23 | [5 empty] | 51151.98 |  |  | 2473.5 | 1236.75
| TRACKER #24 | [8 empty] | 26 | 26 | 26 | 100 | 100 | 100
| INVOICE #24 | [8 empty] | 2143.7 | 1071.85 | 1071.85 | 10306.25 | 4122.5 | 2061.25
| TRACKER #25 | [11 empty] | 4 | 4 | 4
| INVOICE #25 | [11 empty] | 412.25 | 164.9 | 82.45
| TRACKER #26 | [5 empty] | 9 |  |  | 32 | 32 | 62 | 47 |  | 47
| INVOICE #26 | [5 empty] | 4897.53 |  |  | 2638.4 | 1319.2 | 2555.95 | 4843.9375 |  | 968.7875
| TRACKER #27 | [5 empty] | 15 | 4 | 4 | 4 | 4 | 4
| INVOICE #27 | [5 empty] | 8162.55 | 1451.12 | 329.8 | 329.8 | 164.9 | 164.9
| TRACKER #32 | [11 empty] | 5 | 52 | 5 | 156 | 156
| INVOICE #32 | [11 empty] | 515.3125 | 2143.7 | 103.0625 | 23151.96 | 2572.44 |  | 0
| Overall Completion TRACKER | [5 empty] | 166 | 166 | 166 | 166 | 166 | 166 | 156 | 156 | 156 | 156 | 156 | 0
| Overall Completion INVOICE | [5 empty] | 90332.22 | 60221.48 | 13686.7 | 13686.7 | 6843.35 | 6843.35 | 16077.75 | 6431.1 | 3215.55 | 23151.96 | 2572.44 | 0
| Tot.Procument | [5 empty] | 150553.7
| Tot.implementation | [5 empty] | 66784.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 25724.4
| ToT.Overall Completion INVOICE | [5 empty] | 243062.6
| Overall Completion Percentage | [5 empty] | 80.99%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 60% | 20% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [5 empty] | T&C / Configuration |  | Handover
BQ-096 | الموجات الدقيقة ( المايكروويف ) Microwaves | 125 | 150 | عدد | 1479.2 | 221880 |  | Precasting Foundations | Excavation of Pits | Placing foundations | Component Installation | Cabling & Termination | Configuration | RFI / Config. | Acceptance
[8 empty] | 10% | 10% | 5% | 55% | 10% | 10% | 90% | 10%
| TRACKER #15 | [5 empty] | 125
| INVOICE #15 | [5 empty] | 110940
| TRACKER #20 | [6 empty] | 125 | 125 | 125
| INVOICE #20 | [6 empty] | 3698 | 3698 | 1849
| TRACKER #24 | [9 empty] | 100
| INVOICE #24 | [9 empty] | 16271.2
| TRACKER #25 | [9 empty] | 5
| INVOICE #25 | [9 empty] | 813.56
| TRACKER #27 | [5 empty] | 25 | 25 |  |  | 20 | 125
| INVOICE #27 | [5 empty] | 22188 | 739.6 |  |  | 3254.24 | 3698
| TRACKER #28 | [7 empty] | 6 | 6 | 6 | 6
| INVOICE #28 | [7 empty] | 177.504 | 88.752 | 976.272 | 177.504
| TRACKER #32 | [7 empty] | 14 | 14 | 14 | 14 | 145
| INVOICE #32 | [7 empty] | 414.176 | 207.088 | 2277.968 | 414.176 | 4289.68
| Overall Completion TRACKER | [5 empty] | 150 | 150 | 145 | 145 | 145 | 145 | 145 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 133128 | 4437.6 | 4289.68 | 2144.84 | 23593.24 | 4289.68 | 4289.68 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 133128
| Tot.implementation | [5 empty] | 43044.72
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 176172.72
| Overall Completion percentage | [5 empty] | 79.4%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 60% | 20% |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  | T&C / Configuration |  | Handover
BQ-097 | مستشعرات الألياف الضوئية Sensorized Fiber | 8868 | 10421 | م.ط | 360 | 3751560 |  | FOFSS mounting | Cabling | Configuration | RFI / Config. | Acceptance
[8 empty] | 65% | 10% | 25% | 90% | 10%
| TRACKER #15 | [5 empty] | 8868
| INVOICE #15 | [5 empty] | 1915488
| TRACKER #21 | [6 empty] | 3866
| INVOICE #21 | [6 empty] | 180928.8
| TRACKER #26 | [6 empty] | 3910 | 7776
| INVOICE #26 | [6 empty] | 182988 | 55987.2
| TRACKER #27 | [5 empty] | 1469 | 58 | 58
| INVOICE #27 | [5 empty] | 317304 | 2714.4 | 417.6
| TRACKER #28 | [6 empty] | 1335 | 1335
| INVOICE #28 | [6 empty] | 62478 | 9612
| TRACKER #30 | [6 empty] | 700 | 700
| INVOICE #30 | [6 empty] | 32760 | 5040
| TRACKER #31 | [6 empty] | 222 | 222
| INVOICE #31 | [6 empty] | 10389.6 | 1598.4
| TRACKER #33 | [5 empty] | 4 |  |  | 2000
| INVOICE #33 | [5 empty] | 864 |  |  | 36000
| Overall Completion TRACKER | [5 empty] | 10341 | 10091 | 10091 | 2000 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 2233656 | 472258.8 | 72655.2 | 36000 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 2233656
| Tot.implementation | [5 empty] | 580914
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 2814570
| Overall Completion percentage | [5 empty] | 75.02%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | 65% |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  | T&C / Configuration |  | Handover
CR1-001 | أعمال الحفر والتجهيز للاساسات في جميع أنواع التربة، مع توفير كافة اشتراطات السلامة، ونزح المياه، ونقل المخلفات للأماكن المخصصة، وتدعيم الحفريات، وتسوية القاعدة وفقاً للمخططات والمواصفات الفنية المعتمدة وما توافق مع موصفات من الهيئة الملكية Excavation and preparation works for foundations in all types of soil, including the provision of all necessary safety measures, water removal, disposal of waste in designated areas, shoring of excavations, and leveling the base according to approved plans and technical specifications, complying with the Royal Commission's standards . | 0 | 44 | M2 | 245.5 | 10802 |  | Site Prepration | Excavation | RFI / Config. | Acceptance
[8 empty] | 30% | 70% | 90% | 10%
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | 65% |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  | T&C / Configuration |  | Handover
CR1-002 | توريد وصب خرسانة عادية (م250 كجم/م³) مقاومة للكبريتات، بسمك 10 سم أسفل جميع الأساسات، وفقاً للمخططات التنفيذية والمواصفات الفنية للهيئة الملكية .Supply and placement of normal concrete (250 kg/m³) resistant to sulfates, with a thickness of 10 cm below all foundations, in accordance with the execution drawings and technical specifications of the Royal Commission. | 0 | 10 | M2 | 173.5 | 1735 |  | Shuttering | Lean Conc. | RFI / Config. | Acceptance
[8 empty] | 30% | 70% | 90% | 10%
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | 65% |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  | T&C / Configuration |  | Handover
CR1-003 | توريد وصب خرسانة مسلحة (م400 كجم/م³) مقاومة للكبريتات لجميع عناصر الأساسات (قواعد، شدادات، أعمدة، كمر) وفقاً للمخططات التنفيذية والمواصفات الفنية حديد التسليح المعزول، أعمال النجارة الخشبية، وجميع الأعمال الخرسانية، على ان يشتمل البند على تركيب مواسير عبور الخدمات على حسب المخططات و مواصفات الهية الملكية.Supply and placement of reinforced concrete (C40) resistant to sulfates for all foundation elements (footings, ties, columns, beams) in accordance with the construction drawings and technical specifications. The price includes: reinforced steel, formwork, all concrete works, and installation of utilites pipes (for fiber cable and lighting cable )as per drawings and Royal Commission specifications | 0 | 42 | M2 | 1689 | 70938 |  | Shuttering & Rebar | Foundation Installation | RFI / Config. | Acceptance
[8 empty] | 30% | 70% | 90% | 10%
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | 65% |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  | T&C / Configuration |  | Handover
CR1-004 | دهان طبقة عازلة من البيتومين البارد (ثلاثة أوجه) لجميع القواعد ورقاب الأعمدة الخرسانية المدفونة. يشمل العمل تنظيف الأسطح وإصلاح أي تلف ,وحسب المواصفات الفنية.application of a cold bitumen waterproofing membrane (three-sided) to all buried concrete foundations and column bases. Works include surface preparation, repair of any damages, and strict adherence to the specified technical specification | 0 | 100 | M2 | 32 | 3200 |  | Site Prepration | Isolation Insolation | RFI / Config. | Acceptance
[8 empty] | 30% | 70% | 90% | 10%
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | 65% |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  | T&C / Configuration |  | Handover
CR1-005 | توريد وتركيب شبك حديدي (فتحات 10×10 سم) أسفل الكمر حتى سطح قناة تصريف الامطار ، مُطلي بمادة مضادة للصدأ، لمنع التسلل. ينفذ العمل وفقاً للمواصفات القياسية للهيئة العليا للأمن الصناعي.Supply and installation of a welded wire mesh (10x10 cm openings) below the beam up to the level of the storm water channel, coated with an anti-rust material, to prevent infiltration. Works shall be executed in accordance with the standard specifications of the Higher Comiision for Industrial Security | 0 | 50 | عدد | 268 | 13400 |  | Site Prepration | Mesh Installation | RFI / Config. | Acceptance
[8 empty] | 30% | 70% | 90% | 10%
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [5 empty] | T&C / Configuration |  | Handover
NBQ-006 | الموجات الدقيقة ( المايكروويف ) Microwaves | 0 | 2 | عدد | 1480 | 2960 |  | Precasting Foundations | Excavation of Pits | Placing foundations | Component Installation | Cabling & Termination | Configuration | RFI / Config. | Acceptance
[8 empty] | 10% | 10% | 5% | 55% | 10% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 2
| INVOICE #27 | [5 empty] | 1628
| Overall Completion TRACKER | [5 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1628
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1628
| Overall Completion percentage | [5 empty] | 55%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 60% | 20% |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  | T&C / Configuration |  | Handover
CR1-007 | Supply,levelling and installation for jersey barrier in straight line beside outer road in overlapping area with water channel توريد وتركيب مصدات خرسانيه للمنطقة المحاذية لقناة العبور على طريق الدوريات الخارجي يشمل كامل الاعمال | 0 | 640 | ML | 400 | 256000 |  | Preparing | Jersey Barrier Installation | RFI / Config. | Acceptance
[8 empty] | 30% | 70% | 90% | 10%
| TRACKER #33 | [5 empty] | 580
| INVOICE #33 | [5 empty] | 139200
| Overall Completion TRACKER | [5 empty] | 580 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 139200 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 139200
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 139200
| Overall Completion percentage | [5 empty] | 54.37%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-098 | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ ( CEFX ) External Fixed Camera | 8 | 8 | عدد | 3200 | 25600 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 8
| INVOICE #13 | [5 empty] | 14080
| TRACKER #31 | [6 empty] | 8 | 8 | 8 | 8
| INVOICE #31 | [6 empty] | 3200 | 1280 | 640 | 640
| TRACKER #32 | [10 empty] | 8
| INVOICE #32 | [10 empty] | 640
| Overall Completion TRACKER | [5 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 14080 | 3200 | 1280 | 640 | 640 | 640 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 14080
| Tot.implementation | [5 empty] | 6400
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 20480
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% |  | 25% | [6 empty] | 10% |  | 10%
[7 empty] | Procurement |  | CONSTRUCTION | [6 empty] | T&C / Configuration |  | Handover
BQ-099 | عمود كاميرا CCTV Pole | 6 | 4 | عدد | 1650 | 6600 | POLE | FOUNDATION BASE | Precasting Foundations | Excavation | Lean Conc. | Foundation Installation | Pole Installation | BF & Compaction | Pole Alignment | RFI / Config. | Acceptance
[7 empty] | 60% | 40% | 20% | 20% | 10% | 10% | 25% | 10% | 5% | 90% | 10%
| TRACKER #17 | [6 empty] | 5
| INVOICE #17 | [6 empty] | 1815
| TRACKER #18 | [6 empty] | 1
| INVOICE #18 | [6 empty] | 363
| TRACKER #23 | [5 empty] | 6
| INVOICE #23 | [5 empty] | 3267
| TRACKER #31 | [7 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4
| INVOICE #31 | [7 empty] | 330 | 330 | 165 | 165 | 412.5 | 165 | 82.5
| TRACKER #32 | [5 empty] | -2 | -2 | [7 empty] | 4 | 4 | 4
| INVOICE #32 | [5 empty] | -1089 | -726 | [7 empty] | 594 | 66 | 660
| Overall Completion TRACKER | [5 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Overall Completion INVOICE | [5 empty] | 2178 | 1452 | 330 | 330 | 165 | 165 | 412.5 | 165 | 82.5 | 594 | 66 | 660
| Tot.Procument | [5 empty] | 3630
| Tot.implementation | [5 empty] | 1650
| Tot(T&C / Configuration+Handover) | [5 empty] | 1320
| ToT.Overall Completion INVOICE | [5 empty] | 6600
| Overall Completion Percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-100 | كاميرا متحركة خارجية ( CEPZ ) External PTZ Camera | 2 | 2 | عدد | 8400 | 16800 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 2
| INVOICE #27 | [5 empty] | 9240
| TRACKER #31 | [6 empty] | 2 | 2 | 2 | 2
| INVOICE #31 | [6 empty] | 2100 | 840 | 420 | 420
| TRACKER #32 | [10 empty] | 2
| INVOICE #32 | [10 empty] | 420
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 9240 | 2100 | 840 | 420 | 420 | 420 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 9240
| Tot.implementation | [5 empty] | 4200
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 13440
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% |  |  | 25% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement |  |  | CONSTRUCTION | [5 empty] | T&C / Configuration |  | Handover
BQ-101 | بوابة منزلقة آلية ( SGMD ) Motorized Swing Gate | 4 | 4 | عدد | 49850 | 199400 | Gate | Motor | Padlock | Excavation | Casting Foundations | Gate Installation | Backfilling | Cabling & Termination | Testing | RFI / Config. | Acceptance
[7 empty] | 70% | 20% | 10% | 25% | 15% | 20% | 20% | 10% | 10% | 90% | 10%
| TRACKER #12 | [5 empty] | 4
| INVOICE #12 | [5 empty] | 76769
| TRACKER #15 | [6 empty] | 4 | 4
| INVOICE #15 | [6 empty] | 21934 | 10967
| TRACKER #24 | [8 empty] | 2 | 2
| INVOICE #24 | [8 empty] | 6231.25 | 3738.75
| TRACKER #27 | [5 empty] | -2 | -2 | -4
| INVOICE #27 | [5 empty] | -38384.5 | -10967 | -10967
| TRACKER #31 | [8 empty] | 2 | 2 | 3 | 4
| INVOICE #31 | [8 empty] | 6231.25 | 3738.75 | 7477.5 | 9970
| TRACKER #32 | [5 empty] | 2 | 2 | 0
| INVOICE #32 | [5 empty] | 38384.5 | 10967 | 0
| Overall Completion TRACKER | [5 empty] | 4 | 4 | 0 | 4 | 4 | 3 | 4 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 76769 | 21934 | 0 | 12462.5 | 7477.5 | 7477.5 | 9970 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 98703
| Tot.implementation | [5 empty] | 37387.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 136090.5
| Overall Completion percentage | [5 empty] | 68.25%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [5 empty] | T&C / Configuration |  | Handover
BQ-102 | حاجز الذراع الكهربائي ( RAB ) Raise Arm Barrier | 4 | 4 | عدد | 9500 | 38000 |  | Excavation | Casting Foundations | Arm Barrier Installation | Backfilling | Cabling & Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 25% | 15% | 20% | 20% | 10% | 10% | 90% | 10%
| TRACKER #15 | [5 empty] | 4
| INVOICE #15 | [5 empty] | 20900
| TRACKER #27 | [5 empty] | -2
| INVOICE #27 | [5 empty] | -10450
| TRACKER #31 | [6 empty] | 4 | 4 | 2 | 4 | 2
| INVOICE #31 | [6 empty] | 2375 | 1425 | 950 | 1900 | 475
| Overall Completion TRACKER | [5 empty] | 2 | 4 | 4 | 2 | 4 | 2 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 10450 | 2375 | 1425 | 950 | 1900 | 475 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 10450
| Tot.implementation | [5 empty] | 7125
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 17575
| Overall Completion percentage | [5 empty] | 46.25%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-103 | حساس استشعار أرضي ( SLP ) Safety Loop | 12 | 12 | عدد | 1800 | 21600 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #26 | [5 empty] | 12
| INVOICE #26 | [5 empty] | 11880
| TRACKER #31 | [6 empty] | 12 | 12
| INVOICE #31 | [6 empty] | 2700 | 1080
| TRACKER #33 | [8 empty] | 12
| INVOICE #33 | [8 empty] | 1080
| Overall Completion TRACKER | [5 empty] | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 11880 | 2700 | 1080 | 1080 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 11880
| Tot.implementation | [5 empty] | 4860
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 16740
| Overall Completion percentage | [5 empty] | 77.5%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 60% | 20% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [5 empty] | T&C / Configuration |  | Handover
BQ-104 | مصدات طريق ( ROBK ) Road blocker | 4 | 4 | عدد | 172800 | 691200 |  | Excavation | Casting Foundations | Road blocker Installation | Backfilling | Cabling & Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 25% | 15% | 20% | 20% | 10% | 10% | 90% | 10%
| TRACKER #20 | [5 empty] | 1.2
| INVOICE #20 | [5 empty] | 124416
| TRACKER #25 | [5 empty] | 1.4
| INVOICE #25 | [5 empty] | 145152
| TRACKER #26 | [5 empty] | 1.4
| INVOICE #26 | [5 empty] | 145152
| TRACKER #27 | [6 empty] | 4 | 4 | 4
| INVOICE #27 | [6 empty] | 34560 | 20736 | 27648
| TRACKER #29 | [9 empty] | 4
| INVOICE #29 | [9 empty] | 27648
| TRACKER #30 | [10 empty] | 4
| INVOICE #30 | [10 empty] | 13824
| Overall Completion TRACKER | [5 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 414720 | 34560 | 20736 | 27648 | 27648 | 13824 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 414720
| Tot.implementation | [5 empty] | 124416
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 539136
| Overall Completion percentage | [5 empty] | 78%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% | [6 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [6 empty] | T&C / Configuration |  | Handover
BQ-105 | إشارات مرور Traffic Lights | 6 | 8 | عدد | 3200 | 25600 |  | Excavation | Casting Foundations | Pole Installation | Lighting Fixtures | Component Installation | Cabling & Termination | BF & Compaction | RFI / Config. | Acceptance
[8 empty] | 20% | 15% | 10% | 10% | 25% | 10% | 10% | 90% | 10%
| TRACKER #22 | [5 empty] | 4
| INVOICE #22 | [5 empty] | 7040
| TRACKER #26 | [5 empty] | 2
| INVOICE #26 | [5 empty] | 3520
| TRACKER #31 | [6 empty] | 4 | 4 |  |  |  |  | 8
| INVOICE #31 | [6 empty] | 640 | 480 |  |  |  |  | 640
| TRACKER #32 | [5 empty] | 2 | 4 | 4 | 8 | 8 | 8 | 8
| INVOICE #32 | [5 empty] | 3520 | 640 | 480 | 640 | 640 | 1600 | 640
| Overall Completion TRACKER | [5 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 14080 | 1280 | 960 | 640 | 640 | 1600 | 640 | 640 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 14080
| Tot.implementation | [5 empty] | 6400
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 20480
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  | T&C / Configuration |  | Handover
BQ-106 | مطبات التحكم في السرعة Speed Humps | 4 | 4 | عدد | 2300 | 9200 |  | Site Preparation | Anchoring on Ashphalt | Placing of Speed Humps | RFI / Config. | Acceptance
[8 empty] | 10% | 80% | 10% | 90% | 10%
| TRACKER #20 | [5 empty] | 4
| INVOICE #20 | [5 empty] | 5060
| Overall Completion TRACKER | [5 empty] | 4 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 5060 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 5060
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 5060
| Overall Completion percentage | [5 empty] | 55%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-107 | لوحة تحكم في مصدات الطريق ( RBCP ) Road Blocker Cabinet Panel | 4 | 4 | عدد | 7200 | 28800 |  | Cabinet Mounting | Component Installation | Cabling & Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 30% | 10% | 10% | 90% | 10%
| TRACKER #25 | [5 empty] | 2
| INVOICE #25 | [5 empty] | 7920
| TRACKER #26 | [5 empty] | 2
| INVOICE #26 | [5 empty] | 7920
| TRACKER #30 | [6 empty] | 4 | 4
| INVOICE #30 | [6 empty] | 3600 | 2160
| TRACKER #31 | [8 empty] | 4
| INVOICE #31 | [8 empty] | 720
| TRACKER #32 | [9 empty] | 4
| INVOICE #32 | [9 empty] | 720
| Overall Completion TRACKER | [5 empty] | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 15840 | 3600 | 2160 | 720 | 720 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 15840
| Tot.implementation | [5 empty] | 7200
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 23040
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-108 | مفتاح تحكم في مصدات الطريق ( RBCS ) Road Blocker Control Switch | 4 | 4 | عدد | 1400 | 5600 |  | Control Switch Inst'n | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #28 | [5 empty] | 4
| INVOICE #28 | [5 empty] | 3920
| TRACKER #31 | [6 empty] | 4 |  | 4
| INVOICE #31 | [6 empty] | 280 |  | 112
| TRACKER #32 | [7 empty] | 4 |  | 4
| INVOICE #32 | [7 empty] | 112 |  | 56
| Overall Completion TRACKER | [5 empty] | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 3920 | 280 | 112 | 112 | 56 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 3920
| Tot.implementation | [5 empty] | 560
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 4480
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-109 | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | 5 | 9 | عدد | 3160 | 28440 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 5
| INVOICE #13 | [5 empty] | 8690
| TRACKER #27 | [6 empty] | 1 |  | 1
| INVOICE #27 | [6 empty] | 395 | 0 | 158
| TRACKER #29 | [5 empty] | 4
| INVOICE #29 | [5 empty] | 6952
| TRACKER #31 | [6 empty] | 4 |  | 4
| INVOICE #31 | [6 empty] | 1580 |  | 632
| TRACKER #32 | [7 empty] | 5 |  | 5
| INVOICE #32 | [7 empty] | 790 |  | 395
| Overall Completion TRACKER | [5 empty] | 9 | 5 | 5 | 5 | 5 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 15642 | 1975 | 790 | 790 | 395 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 15642
| Tot.implementation | [5 empty] | 3950
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 19592
| Overall Completion percentage | [5 empty] | 68.89%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-110 | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intecom Call Panel | 1 | 1 | عدد | 4950 | 4950 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 |  | 1
| INVOICE #27 | [5 empty] | 2722.5 |  | 247.5
| TRACKER #31 | [6 empty] | 1
| INVOICE #31 | [6 empty] | 618.75
| TRACKER #32 | [8 empty] | 1 | 1
| INVOICE #32 | [8 empty] | 247.5 | 123.75
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 2722.5 | 618.75 | 247.5 | 247.5 | 123.75 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 2722.5
| Tot.implementation | [5 empty] | 1237.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 3960
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-111 | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻠﻧﻅﺎﻡ الأﻣﻧﻲ ISS ISS Work Station | 1 | 1 | عدد | 6200 | 6200 |  | Workstation Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #16 | [5 empty] | 1
| INVOICE #16 | [5 empty] | 4340
| TRACKER #31 | [6 empty] | 1 |  | 1
| INVOICE #31 | [6 empty] | 310 | 0 | 124
| TRACKER #32 | [7 empty] | 1 |  | 1
| INVOICE #32 | [7 empty] | 124 |  | 62
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 4340 | 310 | 124 | 124 | 62 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 4340
| Tot.implementation | [5 empty] | 620
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 4960
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-112 | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Workstation | 1 | 1 | عدد | 6200 | 6200 |  | Workstation Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 1
| INVOICE #13 | [5 empty] | 4340
| TRACKER #31 | [6 empty] | 1 |  | 1
| INVOICE #31 | [6 empty] | 310 |  | 124
| TRACKER #33 | [7 empty] | 1 |  | 1
| INVOICE #33 | [7 empty] | 124 |  | 62
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 4340 | 310 | 124 | 124 | 62 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 4340
| Tot.implementation | [5 empty] | 620
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 4960
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-113 | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻧﻅﺎﻡ ﻟﻔﺣﺹ ﺍﺳﻔﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ UVSS | 1 | 1 | عدد | 6200 | 6200 |  | Workstation Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 1
| INVOICE #13 | [5 empty] | 3410
| TRACKER #31 | [6 empty] | 1 |  | 1
| INVOICE #31 | [6 empty] | 775 | 0 | 310
| TRACKER #33 | [7 empty] | 1 |  | 1
| INVOICE #33 | [7 empty] | 310 |  | 155
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 3410 | 775 | 310 | 310 | 155 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 3410
| Tot.implementation | [5 empty] | 1550
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 4960
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-114 | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺭﺋﻳﺳﻳﺔ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intercom Master Unit | 1 | 1 | عدد | 5600 | 5600 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 1
| INVOICE #13 | [5 empty] | 3080
| TRACKER #27 | [7 empty] | 1
| INVOICE #27 | [7 empty] | 280
| TRACKER #31 | [6 empty] | 1
| INVOICE #31 | [6 empty] | 840
| TRACKER #33 | [8 empty] | 1
| INVOICE #33 | [8 empty] | 140
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 3080 | 840 | 280 | 140 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 3080
| Tot.implementation | [5 empty] | 1260
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 4340
| Overall Completion percentage | [5 empty] | 77.5%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-115 | ﻟﻭﺣﺔ ﻣﻔﺎﺗﻳﺢ ﺍﻟﺩﻭﺍﺋﺭ ﺍﻟﺗﻠﻔﺯﻳﻭﻧﻳﺔ ﺍﻟﻣﻐﻠﻘﺔ ( CTKB ) CCTV Keyboard | 1 | 1 | عدد | 1850 | 1850 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #26 | [5 empty] | 1
| INVOICE #26 | [5 empty] | 1017.5
| TRACKER #31 | [6 empty] | 1
| INVOICE #31 | [6 empty] | 277.5
| TRACKER #33 | [7 empty] | 1 | 1 | 1
| INVOICE #33 | [7 empty] | 92.5 | 46.25 | 46.25
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1017.5 | 277.5 | 92.5 | 46.25 | 46.25 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1017.5
| Tot.implementation | [5 empty] | 462.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1480
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-116 | ﺟﻬﺎﺯ ﺇﻧﺫﺍﺭ ﺻﻭﺗﻲ ﺿﻭﺋﻲ ( SPAS ) Flashing Sounder | 2 | 2 | عدد | 1350 | 2700 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 2
| INVOICE #14 | [5 empty] | 1485
| TRACKER #27 | [6 empty] | 2 |  | 2
| INVOICE #27 | [6 empty] | 405 |  | 67.5
| TRACKER #32 | [7 empty] | 2 |  | 2
| INVOICE #32 | [7 empty] | 135 |  | 67.5
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1485 | 405 | 135 | 67.5 | 67.5 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1485
| Tot.implementation | [5 empty] | 675
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 2160
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-117 | ﺯﺭ ﺇﻧﺫﺍﺭ ﺍﻟﻁﻭﺍﺭﺉ ( EAB ) Emergency Alarm Button | 1 | 1 | عدد | 220 | 220 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 1
| INVOICE #14 | [5 empty] | 154
| TRACKER #31 | [6 empty] | 1 |  | 1
| INVOICE #31 | [6 empty] | 13.2 | 0 | 2.2
| TRACKER #32 | [7 empty] | 1 |  | 1
| INVOICE #32 | [7 empty] | 4.4 |  | 2.2
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 154 | 13.2 | 4.4 | 2.2 | 2.2 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 154
| Tot.implementation | [5 empty] | 22
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 176
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-118 | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required work and materials to complete this item | 1 | 1 | عدد | 29700 | 29700 |  | Cabinet / Rack | UPS Installation | Batteries Installation | Cabling & Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 30% | 30% | 20% | 10% | 10% | 90% | 10%
| TRACKER #25 | [5 empty] | 1
| INVOICE #25 | [5 empty] | 20790
TRACKER #30
INVOICE #30
| TRACKER #31 | [6 empty] | 1 | 1 | 1 | 1 | 1
| INVOICE #31 | [6 empty] | 891 | 891 | 594 | 297 | 297
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 20790 | 891 | 891 | 594 | 297 | 297 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 20790
| Tot.implementation | [5 empty] | 2970
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 23760
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-119 | ﺟﻬﺎﺯ ﻛﺷﻑ ﻣﺗﻔﺟﺭﺍﺕ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ Hand-Held Explosive Detector | 1 | 1 | عدد | 132000 | 132000 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #21 | [5 empty] | 1
| INVOICE #21 | [5 empty] | 92400
| TRACKER #31 | [6 empty] | 1 |  | 1
| INVOICE #31 | [6 empty] | 7920 | 0 | 1320
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 92400 | 7920 | 0 | 1320 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 92400
| Tot.implementation | [5 empty] | 9240
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 101640
| Overall Completion percentage | [5 empty] | 77%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-120 | ﺯﺭ ﺍﻟﺿﻐﻁ ﻟﻠﺧﺭﻭﺝ ( EPB ) Exit Push Button | 1 | 1 | عدد | 160 | 160 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 1
| INVOICE #14 | [5 empty] | 88
| TRACKER #27 | [6 empty] | 1 |  | 1
| INVOICE #27 | [6 empty] | 24 |  | 4
| TRACKER #32 | [7 empty] | 1 |  | 1
| INVOICE #32 | [7 empty] | 8 |  | 4
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 88 | 24 | 8 | 4 | 4 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 88
| Tot.implementation | [5 empty] | 40
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 128
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-121 | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Electric Lock | 1 | 1 | عدد | 1200 | 1200 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 1
| INVOICE #14 | [5 empty] | 660
| TRACKER #27 | [6 empty] | 1 |  | 1
| INVOICE #27 | [6 empty] | 180 |  | 30
| TRACKER #32 | [7 empty] | 1 |  | 1
| INVOICE #32 | [7 empty] | 60 |  | 30
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 660 | 180 | 60 | 30 | 30 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 660
| Tot.implementation | [5 empty] | 300
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 960
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-122 | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) Emergency Break Glass Unit | 1 | 1 | عدد | 240 | 240 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #26 | [5 empty] | 1
| INVOICE #26 | [5 empty] | 132
| TRACKER #31 | [6 empty] | 1 |  | 1
| INVOICE #31 | [6 empty] | 36 | 0 | 6
| TRACKER #32 | [7 empty] | 1 |  | 1
| INVOICE #32 | [7 empty] | 12 |  | 6
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 132 | 36 | 12 | 6 | 6 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 132
| Tot.implementation | [5 empty] | 60
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 192
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-123 | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | 1 | 1 | عدد | 190 | 190 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 1
| INVOICE #14 | [5 empty] | 104.5
| TRACKER #27 | [6 empty] | 1 |  | 1
| INVOICE #27 | [6 empty] | 28.5 |  | 4.75
| TRACKER #32 | [7 empty] | 1 |  | 1
| INVOICE #32 | [7 empty] | 9.5 |  | 4.75
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 104.5 | 28.5 | 9.5 | 4.75 | 4.75 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 104.5
| Tot.implementation | [5 empty] | 47.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 152
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-124 | ﻫﺎﺗﻑ ( TEL ) Telephone | 2 | 2 | عدد | 2300 | 4600 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 2 |  | 2
| INVOICE #27 | [5 empty] | 3220 |  | 92
| TRACKER #31 | [6 empty] | 2
| INVOICE #31 | [6 empty] | 276
| TRACKER #32 | [8 empty] | 2 | 2
| INVOICE #32 | [8 empty] | 46 | 46
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 3220 | 276 | 92 | 46 | 46 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 3220
| Tot.implementation | [5 empty] | 460
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 3680
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-125 | ﺍﻟﺧﻁ ﺍﻟﺳﺎﺧﻥ Hot Line | 1 | 1 | عدد | 2300 | 2300 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 |  | 1
| INVOICE #27 | [5 empty] | 1610 |  | 46
| TRACKER #31 | [6 empty] | 1
| INVOICE #31 | [6 empty] | 138
| TRACKER #32 | [8 empty] | 1 | 1
| INVOICE #32 | [8 empty] | 23 | 23
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1610 | 138 | 46 | 23 | 23 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1610
| Tot.implementation | [5 empty] | 230
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1840
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-126 | ﺭﺍﺩﻳﻭ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ ( HHR ) Hand Held Radio | 1 | 1 | عدد | 3800 | 3800 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
TRACKER #00
INVOICE #00
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-127 | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺩﺍﺧﻠﻳﺔ ﻋﻠﻰ ﺷﻛﻝ ﻗﺑﺔ ( CIDX ) Internal Fixed Mini Dome Camera | 1 | 1 | عدد | 2600 | 2600 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 1
| INVOICE #13 | [5 empty] | 1430
| TRACKER #32 | [6 empty] | 1 | 1 | 1 | 1 | 1
| INVOICE #32 | [6 empty] | 325 | 130 | 65 | 65 | 65
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1430 | 325 | 130 | 65 | 65 | 65 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1430
| Tot.implementation | [5 empty] | 650
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 2080
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-128 | ﻛﺎﻣﻳﺭﺍ ﻣﻊ ﺍﻻﻧﺎﺭﺓ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Camera | 2 | 2 | عدد | 56200 | 112400 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #15 | [5 empty] | 2
| INVOICE #15 | [5 empty] | 61820
| TRACKER #27 | [5 empty] | -1
| INVOICE #27 | [5 empty] | -30910
| TRACKER #31 | [5 empty] | 1
| INVOICE #31 | [5 empty] | 30910
| TRACKER #33 | [6 empty] | 2 | 2 | 2 | 2
| INVOICE #33 | [6 empty] | 14050 | 5620 | 2810 | 2810
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 61820 | 14050 | 5620 | 2810 | 2810 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 61820
| Tot.implementation | [5 empty] | 25290
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 87110
| Overall Completion percentage | [5 empty] | 77.5%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-129 | ﺟﻬﺎﺯ ﺍﻧﺫﺍﺭ ﺿﻭﺋﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Beacon | 2 | 2 | عدد | 2100 | 4200 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #15 | [5 empty] | 2
| INVOICE #15 | [5 empty] | 2310
| Overall Completion TRACKER | [5 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 2310 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 2310
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 2310
| Overall Completion percentage | [5 empty] | 55%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-130 | ﺟﻬﺎﺯ ﺍﻧﺫﺍﺭ ﺻﻭﺗﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Sounder | 2 | 2 | عدد | 1600 | 3200 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #15 | [5 empty] | 2
| INVOICE #15 | [5 empty] | 1760
| Overall Completion TRACKER | [5 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1760 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1760
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1760
| Overall Completion percentage | [5 empty] | 55%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-131 | ﺣﺳﺎﺱ ﺍﺳﺗﺷﻌﺎﺭ ﺍﺭﺿﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR | 2 | 2 | عدد | 1800 | 3600 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #15 | [5 empty] | 2
| INVOICE #15 | [5 empty] | 1980
| Overall Completion TRACKER | [5 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1980
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1980
| Overall Completion percentage | [5 empty] | 55%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-132 | ﻛﺎﻣﻳﺭﺍ ﻟﻧﻅﺎﻡ ﻓﺣﺹ ﺍﺳﻔﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ UVSS | 2 | 2 | عدد | 58000 | 116000 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 10% | 20% | 10% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 2
| INVOICE #13 | [5 empty] | 63800
| TRACKER #33 | [6 empty] | 2 | 2 | 2 | 2
| INVOICE #33 | [6 empty] | 14500 | 2900 | 5800 | 2900
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 63800 | 14500 | 2900 | 5800 | 2900 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 63800
| Tot.implementation | [5 empty] | 26100
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 89900
| Overall Completion percentage | [5 empty] | 77.5%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-133 | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | 1 | 5 | عدد | 2900 | 14500 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 10% | 20% | 10% | 10% | 90% | 10%
| TRACKER #12 | [5 empty] | 1
| INVOICE #12 | [5 empty] | 1595
| TRACKER #27 | [5 empty] | 4 | 1 |  | 1 | 1
| INVOICE #27 | [5 empty] | 6380 | 362.5 |  | 145 | 72.5
| TRACKER #32 | [7 empty] | 1 |  |  | 1
| INVOICE #32 | [7 empty] | 72.5 |  |  | 72.5
| Overall Completion TRACKER | [5 empty] | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 7975 | 362.5 | 72.5 | 145 | 72.5 | 72.5 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 7975
| Tot.implementation | [5 empty] | 725
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 8700
| Overall Completion percentage | [5 empty] | 60%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-134 | ﻟﻭﺣﺔ ﺗﺣﻛﻡ ﻓﻲ ﺣﺎﺟﺯ ﺍﻟﺫﺭﺍﻉ ﺍﻟﻛﻬﺭﺑﺎﺋﻲ ( RAB ) Raise Arm Barrier Control Switch | 4 | 4 | عدد | 1400 | 5600 |  | Control Switch Inst'n | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #28 | [5 empty] | 4
| INVOICE #28 | [5 empty] | 3080
TRACKER #28
INVOICE #28
| TRACKER #31 | [6 empty] | 4 |  | 4
| INVOICE #31 | [6 empty] | 700 |  | 280
| TRACKER #31 | [7 empty] | 4 |  | 4
| INVOICE #31 | [7 empty] | 280 |  | 140
| Overall Completion TRACKER | [5 empty] | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 3080 | 700 | 280 | 280 | 140 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 3080
| Tot.implementation | [5 empty] | 1400
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 4480
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-135 | ﻣﻔﺗﺎﺡ ﺍﻟﺗﺣﻛﻡ ﻓﻲ ﺍﻟﺑﻭﺍﺑﺔ ﺍﻟﻣﻧﺯﻟﻘﺔ Swing Gate Control Switch | 2 | 4 | عدد | 1400 | 5600 |  | Control Switch Inst'n | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #28 | [5 empty] | 4
| INVOICE #28 | [5 empty] | 3080
| TRACKER #31 | [6 empty] | 4 |  | 4
| INVOICE #31 | [6 empty] | 700 |  | 280
| Overall Completion TRACKER | [5 empty] | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 3080 | 700 | 0 | 280 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 3080
| Tot.implementation | [5 empty] | 980
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 4060
| Overall Completion percentage | [5 empty] | 72.5%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 60% | 20% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [5 empty] | T&C / Configuration |  | Handover
BQ-136 | الموجات الدقيقة ( المايكروويف ) Microwaves | 4 | 4 | عدد | 1480 | 5920 |  | Precasting Foundations | Excavation of Pits | Placing foundations | Component Installation | Cabling & Termination | Configuration | RFI / Config. | Acceptance
[8 empty] | 10% | 10% | 5% | 55% | 10% | 10% | 90% | 10%
| TRACKER #15 | [5 empty] | 4
| INVOICE #15 | [5 empty] | 3552
| TRACKER #27 | [5 empty] | -2
| INVOICE #27 | [5 empty] | -1776
| TRACKER #31 | [6 empty] | 2 | 2 | 2 | 2
| INVOICE #31 | [6 empty] | 59.2 | 59.2 | 29.6 | 325.6
| TRACKER #32 | [5 empty] | 2 | 1 | 1 | 1 | 1 | 3
| INVOICE #32 | [5 empty] | 1776 | 29.6 | 29.6 | 14.8 | 162.8 | 88.8
| Overall Completion TRACKER | [5 empty] | 4 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 3552 | 88.8 | 88.8 | 44.4 | 488.4 | 88.8 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 3552
| Tot.implementation | [5 empty] | 799.2
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 4351.2
| Overall Completion percentage | [5 empty] | 73.5%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-137 | ﻋﻣﻭﺩ ﺛﺎﺑﺕ ﻟﻣﻧﻊ ﺩﺧﻭﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ - ﺗﺻﻧﻳﻑ - Crash Rated Static Bollard (ASTM M50-P1 Rated)ASTM M50-P1 | 88 | 82 | عدد | 5900 | 483800 |  | Excavation | Foundation Casting | Bollard Installation | Backfilling | RFI / Config. | Acceptance
[8 empty] | 20% | 10% | 60% | 10% | 90% | 10%
| TRACKER #17 | [5 empty] | 82
| INVOICE #17 | [5 empty] | 266090
| TRACKER #19 | [6 empty] | 52
| INVOICE #19 | [6 empty] | 15340
| TRACKER #20 | [6 empty] | 46 | 46 | 46
| INVOICE #20 | [6 empty] | 13570 | 6785 | 40710
| TRACKER #26 | [5 empty] | -1 | -52
| INVOICE #26 | [5 empty] | -3245 | -15340
| TRACKER #27 | [6 empty] | 13 | 5 | 5 | 51
| INVOICE #27 | [6 empty] | 3835 | 737.5 | 4425 | 7522.5
| TRACKER #28 | [6 empty] | 22 | 30 | 30 | 30 | 47 | 47
| INVOICE #28 | [6 empty] | 6490 | 4425 | 26550 | 4425 | 24957 | 2773
| TRACKER #29 | [10 empty] | 34 | 34
| INVOICE #29 | [10 empty] | 18054 | 2006
| TRACKER #30 | [12 empty] | 81
| INVOICE #30 | [12 empty] | 47790
| Overall Completion TRACKER | [5 empty] | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81
| Overall Completion INVOICE | [5 empty] | 262845 | 23895 | 11947.5 | 71685 | 11947.5 | 43011 | 4779 | 47790
| Tot.Procument | [5 empty] | 262845
| Tot.implementation | [5 empty] | 119475
| Tot(T&C / Configuration+Handover) | [5 empty] | 95580
| ToT.Overall Completion INVOICE | [5 empty] | 477900
| Overall Completion percentage | [5 empty] | 98.78%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | 65% | [13 empty] | 10% |  | 10%
[7 empty] | Procurement | 10% | 45% | [5 empty] | 30% |  |  |  | 5% | 5% | 5% | T&C / Configuration |  | Handover
BQ-138 | بناء ﻭﺗﺟﻬﻳﺯﻏﺭﻓﺔ ﺍﻟﺣﺭﺍﺳﺔ ﻣﻊ مظلة ونظام الإنارة لنقاط التفتيش Construction of Gatehouse with sunshade and checkpoint lighting system | 1 | 1 | عدد | 1760000 | 1760000 |  | Site Prep | Construction of Gate house | [5 empty] | Construction of Sunshade |  |  |  | Lighting & Grounding | Cabling & Termination | Finishing Works | RFI / Config. | Acceptance
[9 empty] | Stacking | Excavation | Substructure & Concrete | Super structure | Construction of Ballistic Wall | Finishing | Foundation Excavation | Foundation concreting works | Sunshade Erection | Installation of lighting fixtures |  |  |  | 90% | 10%
[9 empty] | 3% | 7% | 20% | 20% | 10% | 40% | 10% | 20% | 40% | 30%
| TRACKER #17 | [6 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 0.5 | 0.5
| INVOICE #17 | [6 empty] | 114400 | 15444 | 36036 | 102960 | 102960 |  |  | 5148 | 6864
| TRACKER #18 | [11 empty] | 1 | 1
| INVOICE #18 | [11 empty] | 51480 | 30888
TRACKER #19
| INVOICE #19 | [12 empty] | 74646
TRACKER #20
| INVOICE #20 | [12 empty] | 19305
| TRACKER #24 | [5 empty] | 1
| INVOICE #24 | [5 empty] | 264000 | [6 empty] | 11583
TRACKER #26
| INVOICE #26 | [12 empty] | -34749
| TRACKER #27 | [13 empty] | 0.5 | 0.5 |  |  | 0.5 | 0.5 |  | 0.5 | 0.5
| INVOICE #27 | [12 empty] | 88803 | 5148 | 6864 |  |  | 28600 | 28600 |  | 79200 | 8800
| TRACKER #28 | [15 empty] | 1
| INVOICE #28 | [15 empty] | 68640
TRACKER #31
| INVOICE #31 | [12 empty] | 15444
| TRACKER #32 | [16 empty] | 1 | 0.5 | 0.5 | 1 | 0.5 | 0.5
| INVOICE #32 | [13 empty] | 24024 | 54912 | 68640 | 102960 | 28600 | 28600 | 57200 | 79200 | 8800
| TRACKER #33 | [22 empty] | 0.5
| INVOICE #33 | [22 empty] | 88000
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
| Overall Completion INVOICE | [5 empty] | 264000 | 114400 | 15444 | 36036 | 102960 | 102960 | 51480 | 205920 | 34320 | 68640 | 137280 | 102960 | 57200 | 57200 | 57200 | 158400 | 17600 | 88000
| Tot.Procument | [5 empty] | 264000
| Tot.implementation | [5 empty] | 1144000
| Tot(T&C / Configuration+Handover) | [5 empty] | 264000
| ToT.Overall Completion INVOICE | [5 empty] | 1672000
| Overall Completion Percentage | [5 empty] | 95%
DESCRIPTION Breakdown of Procument finshing GH-1 Building
Roof insulation |  | 5% |  | 25% | 22000 | TRACKER #24 | 10% | 25% | 12870 | TRACKER #19
Electrical foundation |  |  |  | 20% | 17600 | TRACKER #24 |  | 20% | 10296 | TRACKER #18
HVAC foundation |  |  |  | 20% | 17600 | TRACKER #24 |  | 20% | 10296 | TRACKER #18
Security foundation |  |  |  | 20% | 17600 | TRACKER #24 |  | 20% | 10296 | TRACKER #18
Fire alarm foundation |  |  |  | 15% | 13200 | TRACKER #24 |  | 15% | 7722 | TRACKER #27
Interior plastering |  | 5% |  | 10% | 8800 | TRACKER #24 | 15% | 10% | 7722 | TRACKER #20
Exterior plastering |  |  |  | 10% | 8800 | TRACKER #24 |  | 10% | 7722 | TRACKER #19
False Ceiling |  |  |  | 10% | 8800 | TRACKER #24 |  | 10% | 7722 | TRACKER #27
Interior paint |  |  |  | 10% | 8800 | TRACKER #24 |  | 10% | 7722 | TRACKER #27
Exterior paint |  |  |  | 15% | 13200 | TRACKER #24 |  | 15% | 11583 | TRACKER #19
Doors and Windows |  |  |  | 15% | 13200 | TRACKER #24 |  | 15% | 11583 | TRACKER #19
Tiles |  |  |  | 15% | 13200 | TRACKER #24 |  | 15% | 11583 | TRACKER #20
Kerbstone and interlock |  |  |  | 15% | 13200 | TRACKER #24 |  | 15% | 11583 | TRACKER #24
Electrical finishing |  | 5% |  | 20% | 17600 | TRACKER #24 | 15% | 20% | 15444 | TRACKER #19
HVAC finishing |  |  |  | 20% | 17600 | TRACKER #24 |  | 20% | 15444 | TRACKER #19
Security finishing |  |  |  | 20% | 17600 | TRACKER #24 |  | 20% | 15444 | TRACKER #27
Fire alarm finishing |  |  |  | 20% | 17600 | TRACKER #24 |  | 20% | 15444 | TRACKER #27
Building furniture |  |  |  | 20% | 17600 | TRACKER #24 |  | 20% | 15444 | TRACKER #31
Total |  | 15% |  |  | 264000 |  | 40% | 205920
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-139 | ﻧﻘﻁﺔ ﺍﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﻌﺳﻛﺭﻳﺔ Over Watch | 1 | 1 | عدد | 116000 | 116000 |  | Levelling & Backfilling | Ramp Concreting | Canopy installation | Finishing works | RFI / Config. | Acceptance
[8 empty] | 20% | 45% | 30% | 5% | 90% | 10%
| TRACKER #29 | [5 empty] | 1 | 1 | 1 | 1
| INVOICE #29 | [5 empty] | 63800 | 5800 | 13050 | 8700
| TRACKER #32 | [9 empty] | 1 | 1 | 1
| INVOICE #32 | [9 empty] | 1450 | 10440 | 1160
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Overall Completion INVOICE | [5 empty] | 63800 | 5800 | 13050 | 8700 | 1450 | 10440 | 1160 | 0
| Tot.Procument | [5 empty] | 63800
| Tot.implementation | [5 empty] | 29000
| Tot(T&C / Configuration+Handover) | [5 empty] | 11600
| ToT.Overall Completion INVOICE | [5 empty] | 104400
| Overall Completion percentage | [5 empty] | 90%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-140 | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺩﺍﺧﻠﻳﺔ ﻋﻠﻰ ﺷﻛﻝ ﻗﺑﺔ ( CIDX ) Internal Fixed Mini Dome Camera | 6 | 6 | عدد | 2600 | 15600 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 6
| INVOICE #13 | [5 empty] | 8580
| TRACKER #25 | [6 empty] | 6 |  | 6
| INVOICE #25 | [6 empty] | 1950 |  | 390
| TRACKER #27 | [9 empty] | 6
| INVOICE #27 | [9 empty] | 390
| TRACKER #32 | [7 empty] | 6 |  |  | 6
| INVOICE #32 | [7 empty] | 780 |  |  | 390
| Overall Completion TRACKER | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 8580 | 1950 | 780 | 390 | 390 | 390 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 8580
| Tot.implementation | [5 empty] | 3900
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 12480
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-141 | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ ( CEFX ) External Fixed Camera | 3 | 3 | عدد | 3200 | 9600 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 3
| INVOICE #13 | [5 empty] | 5280
| TRACKER #32 | [6 empty] | 3 | 3 | 3 | 3 | 3
| INVOICE #32 | [6 empty] | 1200 | 480 | 240 | 240 | 240
| Overall Completion TRACKER | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 5280 | 1200 | 480 | 240 | 240 | 240 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 5280
| Tot.implementation | [5 empty] | 2400
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 7680
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% |  | 25% | [6 empty] | 10% |  | 10%
[7 empty] | Procurement |  | CONSTRUCTION | [6 empty] | T&C / Configuration |  | Handover
BQ-142 | عمود كاميرا CCTV Pole | 3 | 3 | عدد | 1650 | 4950 | POLE | FOUNDATION BASE | Precasting Foundations | Excavation | Lean Conc. | Foundation Installation | Pole Installation | BF & Compaction | Pole Alignment | RFI / Config. | Acceptance
[7 empty] | 60% | 40% | 20% | 20% | 10% | 10% | 25% | 10% | 5% | 90% | 10%
| TRACKER #18 | [6 empty] | 3
| INVOICE #18 | [6 empty] | 1089
| TRACKER #23 | [5 empty] | 3
| INVOICE #23 | [5 empty] | 1633.5
| TRACKER #27 | [7 empty] | 3 | 3 | 3 | 3
| INVOICE #27 | [7 empty] | 247.5 | 247.5 | 123.75 | 123.75
| TRACKER #31 | [11 empty] | 3 | 3 | 3
| INVOICE #31 | [11 empty] | 309.375 | 123.75 | 61.875
| TRACKER #32 | [14 empty] | 3 | 3 | 3
| INVOICE #32 | [14 empty] | 445.5 | 49.5 | 495
| Overall Completion TRACKER | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Overall Completion INVOICE | [5 empty] | 1633.5 | 1089 | 247.5 | 247.5 | 123.75 | 123.75 | 309.375 | 123.75 | 61.875 | 445.5 | 49.5 | 495
| Tot.Procument | [5 empty] | 2722.5
| Tot.implementation | [5 empty] | 1237.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 990
| ToT.Overall Completion INVOICE | [5 empty] | 4950
| Overall Completion Percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-143 | ﻛﺎﻣﻳﺭﺍﺕ ﺛﺎﺑﺗﺔ ﺑﺯﺍﻭﻳﺔ ﻭﺍﺳﻌﺔ Wide Angle Fixed Cameras | 9 | 5 | عدد | 2900 | 14500 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #24 | [5 empty] | 5
| INVOICE #24 | [5 empty] | 7975
| TRACKER #25 | [6 empty] | 4 |  | 4
| INVOICE #25 | [6 empty] | 1450 |  | 290
| TRACKER #27 | [9 empty] | 3
| INVOICE #27 | [9 empty] | 217.5
| TRACKER #32 | [7 empty] | 3 |  | 3 | 3
| INVOICE #32 | [7 empty] | 435 |  | 217.5 | 217.5
| TRACKER #32 | [9 empty] | -3
| INVOICE #32 | [9 empty] | -217.5
| Overall Completion TRACKER | [5 empty] | 5 | 4 | 3 | 4 | 3 | 3 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 7975 | 1450 | 435 | 290 | 217.5 | 217.5 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 7975
| Tot.implementation | [5 empty] | 2610
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 10585
| Overall Completion percentage | [5 empty] | 73%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-144 | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | 9 | 5 | عدد | 3160 | 15800 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 5
| INVOICE #13 | [5 empty] | 8690
| TRACKER #25 | [6 empty] | 3 |  | 3
| INVOICE #25 | [6 empty] | 1185 |  | 474
| TRACKER #32 | [7 empty] | 1.6666 |  | 1.6666
| INVOICE #32 | [7 empty] | 263.3228 |  | 131.6614
| TRACKER #32 | [7 empty] | 1.3334 |  | 1.3334
| INVOICE #32 | [7 empty] | 210.6772 |  | 105.3386
| Overall Completion TRACKER | [5 empty] | 5 | 3 | 3 | 3 | 3 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 8690 | 1185 | 474 | 474 | 237 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 8690
| Tot.implementation | [5 empty] | 2370
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 11060
| Overall Completion percentage | [5 empty] | 70%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-145 | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | 6 | 6 | عدد | 190 | 1140 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 6
| INVOICE #14 | [5 empty] | 627
| TRACKER #25 | [6 empty] | 6 |  | 6
| INVOICE #25 | [6 empty] | 142.5 |  | 57
| TRACKER #32 | [7 empty] | 6 |  | 6
| INVOICE #32 | [7 empty] | 57 |  | 28.5
| Overall Completion TRACKER | [5 empty] | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 627 | 142.5 | 57 | 57 | 28.5 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 627
| Tot.implementation | [5 empty] | 285
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 912
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-146 | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Electric Lock | 2 | 2 | عدد | 1200 | 2400 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 2
| INVOICE #14 | [5 empty] | 1320
| TRACKER #25 | [6 empty] | 2 |  | 2
| INVOICE #25 | [6 empty] | 300 |  | 120
| TRACKER #32 | [7 empty] | 2 |  | 2
| INVOICE #32 | [7 empty] | 120 |  | 60
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1320 | 300 | 120 | 120 | 60 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1320
| Tot.implementation | [5 empty] | 600
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1920
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-147 | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) Emergency Break Glass Unit | 2 | 2 | عدد | 240 | 480 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 2
| INVOICE #14 | [5 empty] | 264
| TRACKER #25 | [6 empty] | 2 |  | 2
| INVOICE #25 | [6 empty] | 60 |  | 24
| TRACKER #32 | [7 empty] | 2 |  | 2
| INVOICE #32 | [7 empty] | 24 |  | 12
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 264 | 60 | 24 | 24 | 12 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 264
| Tot.implementation | [5 empty] | 120
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 384
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-148 | ﺯﺭ ﺍﻟﺿﻐﻁ ﻟﻠﺧﺭﻭﺝ ( EPB ) Exit Push Button | 1 | 1 | عدد | 160 | 160 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 1
| INVOICE #14 | [5 empty] | 88
| TRACKER #25 | [6 empty] | 1 |  | 1
| INVOICE #25 | [6 empty] | 20 |  | 8
| TRACKER #32 | [7 empty] | 1 |  | 1
| INVOICE #32 | [7 empty] | 8 |  | 4
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 88 | 20 | 8 | 8 | 4 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 88
| Tot.implementation | [5 empty] | 40
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 128
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-149 | ﺟﻬﺎﺯ ﺍﻟﻛﺷﻑ ﻋﻥ ﺍﻟﻣﻌﺎﺩﻥ ﺑﺎﻟﻣﺭﻭﺭ ( WTMD ) Walk Through Metal Detector | 1 | 1 | عدد | 24000 | 24000 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #12 | [5 empty] | 1
| INVOICE #12 | [5 empty] | 16800
| Overall Completion TRACKER | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 16800 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 16800
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 16800
| Overall Completion percentage | [5 empty] | 70%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-150 | ﺑﺎﺏ ﺩﻭﺍﺭ ﻛﺎﻣﻝ ﺍﻻﺭﺗﻔﺎﻉ ( FHTS ) Full Height Turnstile | 3 | 3 | عدد | 50400 | 151200 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #24 | [5 empty] | 1
| INVOICE #24 | [5 empty] | 27720
| TRACKER #32 | [5 empty] | 2
| INVOICE #32 | [5 empty] | 55440
| Overall Completion TRACKER | [5 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 83160 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 83160
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 83160
| Overall Completion percentage | [5 empty] | 55%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-151 | ﻫﺎﺗﻑ ( TEL ) Telephone | 2 | 2 | عدد | 2300 | 4600 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 2 |  | 2
| INVOICE #27 | [5 empty] | 3220 |  | 92
| TRACKER #32 | [6 empty] | 1 |  | 1 | 1
| INVOICE #32 | [6 empty] | 138 |  | 23 | 23
| TRACKER #33 | [6 empty] | 1 |  | 1 | 1
| INVOICE #33 | [6 empty] | 138 |  | 23 | 23
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 3220 | 276 | 92 | 46 | 46 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 3220
| Tot.implementation | [5 empty] | 460
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 3680
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-152 | ﺍﻟﺧﻁ ﺍﻟﺳﺎﺧﻥ Hot Line | 1 | 1 | عدد | 2300 | 2300 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 |  | 1
| INVOICE #27 | [5 empty] | 1610 |  | 46
| TRACKER #32 | [6 empty] | 1 |  | 1 | 1
| INVOICE #32 | [6 empty] | 115 |  | 46 | 23
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1610 | 115 | 46 | 46 | 23 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1610
| Tot.implementation | [5 empty] | 230
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1840
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-153 | ﺭﺍﺩﻳﻭ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ ( HHR ) Hand Held Radio | 1 | 1 | عدد | 3800 | 3800 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-154 | ﻣﺣﻁﺔ ﻋﻣﻝ ﺑﻁﺎﻗﺔ ﺍﻟﻬﻭﻳﺔ ID Workstation | 1 | 1 | عدد | 6200 | 6200 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #26 | [5 empty] | 1
| INVOICE #26 | [5 empty] | 4340
| TRACKER #32 | [6 empty] | 1 | 1 | 1 | 1
| INVOICE #32 | [6 empty] | 310 | 124 | 124 | 62
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 4340 | 310 | 124 | 124 | 62 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 4340
| Tot.implementation | [5 empty] | 620
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 4960
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-155 | ﻛﺎﻣﻳﺭﺍ ﺭﻗﻣﻳﺔ ﻟﺑﻁﺎﻗﺔ ﺍﻟﻬﻭﻳﺔ ID Digital Camera | 1 | 1 | عدد | 1800 | 1800 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #28 | [5 empty] | 1
| INVOICE #28 | [5 empty] | 990
| Overall Completion TRACKER | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 990
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 990
| Overall Completion percentage | [5 empty] | 55%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-156 | ﻗﺎﺭﺉ ﺍﻟﺗﺳﺟﻳﻝ Enrollment Reader | 1 | 1 | عدد | 1650 | 1650 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 1
| INVOICE #14 | [5 empty] | 1155
| Overall Completion TRACKER | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1155 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1155
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1155
| Overall Completion percentage | [5 empty] | 70%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-157 | ﻁﺎﺑﻌﺔ ﺍﻟﺑﻁﺎﻗﺔ Card Printer | 1 | 1 | عدد | 19400 | 19400 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 1
| INVOICE #13 | [5 empty] | 13580
| TRACKER #32 | [6 empty] | 1 | 1 | 1 | 1
| INVOICE #32 | [6 empty] | 1164 | 388 | 194 | 194
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 13580 | 1164 | 388 | 194 | 194 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 13580
| Tot.implementation | [5 empty] | 1940
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 15520
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-158 | ﻣﺎﺳﺣﺔ ﺍﻷﻣﺗﻌﺔ ﺑﺎﻷﺷﻌﺔ ﺍﻟﺳﻳﻧﻳﺔ X-Ray Baggage Scanner | 1 | 1 | عدد | 152000 | 152000 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #10 | [5 empty] | 1
| INVOICE #10 | [5 empty] | 106400
| Overall Completion TRACKER | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 106400 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 106400
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 106400
| Overall Completion Percentage | [5 empty] | 64.4848
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-159 | ﺟﻬﺎﺯ ﻛﺷﻑ ﺍﻟﻣﻌﺎﺩﻥ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ Hand-Held Metal detector | 1 | 1 | عدد | 132000 | 132000 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #21 | [5 empty] | 1
| INVOICE #21 | [5 empty] | 92400
| TRACKER #31 | [6 empty] | 1 |  | 1
| INVOICE #31 | [6 empty] | 7920 |  | 1320
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 92400 | 7920 | 0 | 1320 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 101640
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 101640
| Overall Completion Percentage | [5 empty] | #DIV/0!
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-160 | ﺟﻬﺎﺯ ﻛﺷﻑ ﺍﻟﻣﻌﺎﺩﻥ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ Hand-Held Metal detector | 1 | 1 | عدد | 1300 | 1300 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #12 | [5 empty] | 1
| INVOICE #12 | [5 empty] | 910
| TRACKER #31 | [6 empty] | 1 |  | 1
| INVOICE #31 | [6 empty] | 78 |  | 13
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 910 | 78 | 0 | 13 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 910
| Tot.implementation | [5 empty] | 91
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1001
| Overall Completion percentage | [5 empty] | 77%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-161 | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required | 1 | 1 | عدد | 29700 | 29700 |  | Cabinet / Rack | UPS Installation | Batteries Installation | Cabling & Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 30% | 30% | 20% | 10% | 10% | 90% | 10%
| TRACKER #25 | [5 empty] | 1
| INVOICE #25 | [5 empty] | 20790
TRACKER #30
INVOICE #30
| TRACKER #31 | [6 empty] | 1 | 1 | 1 | 1 | 1
| INVOICE #31 | [6 empty] | 891 | 891 | 594 | 297 | 297
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 20790 | 891 | 891 | 594 | 297 | 297 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 20790
| Tot.implementation | [5 empty] | 2970
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 23760
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  | T&C / Configuration |  | Handover
BQ-162 | ﺑﺎﺏ ﺣﺩﻳﺩﻱ ﻣﻔﺻﻠﻲ ﺫﻭ ﺩﺭﻓﺗﻳﻥ ﻣﺗﻭﺍﻓﻖ ﻣﻊ DLSD ) SEC-09 ) Double Leaf Steel Door (Compliant with SEC-09 "Doors")8 | 2 | 2 | عدد | 11355 | 22710 |  | Door sub frames | Door & frames | RFI / Config. | Acceptance
[8 empty] | 40% | 60% | 90% | 10%
| TRACKER #17 | [5 empty] | 2
| INVOICE #17 | [5 empty] | 12490.5
| TRACKER #18 | [6 empty] | 2 | 2
| INVOICE #18 | [6 empty] | 2271 | 3406.5
| TRACKER #24 | [8 empty] | 2 | 2
| INVOICE #24 | [8 empty] | 2043.9 | 227.1
| TRACKER #30 | [10 empty] | 2
| INVOICE #30 | [10 empty] | 2271
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2
| Overall Completion INVOICE | [5 empty] | 12490.5 | 2271 | 3406.5 | 2043.9 | 227.1 | 2271
| Tot.Procument | [5 empty] | 12490.5
| Tot.implementation | [5 empty] | 5677.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 4542
| ToT.Overall Completion INVOICE | [5 empty] | 22710
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% |  |  |  | 65% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement |  |  |  | Construction of Sfc | [5 empty] | T&C / Configuration |  | Handover
BQ-163 | بناء ﻣﺑﻧﻰ ﺍﻟﺗﻔﺗﻳﺵ ﻭﻣﺭﻛﺯ ﺍﻟﺯﻭﺍﺭ Construction of Search Facility & Vistor Center | 1 | 1 | عدد | 2340000 | 2340000 | Substructure & Concrete | Super Structure | Construction of Ballistic Wall | Finishing | Stacking | Excavation | Substructure & Concrete | Super structure | Construction of Ballistic Wall | Finishng Building | RFI / Config. | Acceptance
[7 empty] | 20% | 30% | 10% | 40% | 3% | 10% | 25% | 20% | 10% | 32% | 90% | 10%
| TRACKER #08 | [9 empty] | 1 | 1
| INVOICE #08 | [9 empty] | 45630 | 152100
| TRACKER #09 | [11 empty] | 1
| INVOICE #09 | [11 empty] | 380250
| TRACKER #11 | [5 empty] | 1 | 1 | [5 empty] | 1
| INVOICE #11 | [5 empty] | 70200 | 105300 | [5 empty] | 304200
| TRACKER #13 | [7 empty] | 1 | [5 empty] | 1
| INVOICE #13 | [7 empty] | 35100 | [5 empty] | 152100
| TRACKER #14 | [8 empty] | 1 | [5 empty] | 1
| INVOICE #14 | [8 empty] | 20007 | [5 empty] | 86697
TRACKER #15
| INVOICE #15 | [8 empty] | 5265 | [5 empty] | 22815
TRACKER #17
| INVOICE #17 | [8 empty] | 8775 | [5 empty] | 22815
TRACKER #18
| INVOICE #18 | [14 empty] | 15210
TRACKER #21
| INVOICE #21 | [8 empty] | 7020 | [5 empty] | 15210
TRACKER #22
| INVOICE #22 | [8 empty] | 15795 | [5 empty] | 56277
TRACKER #23
| INVOICE #23 | [8 empty] | 14040 | [5 empty] | 42588
TRACKER #24
| INVOICE #24 | [8 empty] | 14040 | [5 empty] | 15210
TRACKER #25
| INVOICE #25 | [8 empty] | 10530 | [5 empty] | 27378
TRACKER #26
| INVOICE #26 | [8 empty] | 27378 | [5 empty] | 86814.0029
| TRACKER #27 | [15 empty] | 0.5 | 0.5
| INVOICE #27 | [8 empty] | 17550 | [5 empty] | 68328 | 105300 | 11700
| TRACKER #29 | [15 empty] | 0.25 | 0.25
| INVOICE #29 | [15 empty] | 52650 | 5850
TRACKER #30
| INVOICE #30 | [14 empty] | 27378
| TRACKER #31 | [17 empty] | 0.75
| INVOICE #31 | [17 empty] | 175500
| TRACKER #32 | [15 empty] | 0.15 | 0.15 | 0.15
| INVOICE #32 | [15 empty] | 31590 | 3510 | 35100
| TRACKER #33 | [15 empty] | 0.1 | 0.1
| INVOICE #33 | [15 empty] | 21060 | 2340
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.9
| Overall Completion INVOICE | [5 empty] | 70200 | 105300 | 35100 | 140400 | 45630 | 152100 | 380250 | 304200 | 152100 | 486720.0029 | 210600 | 23400 | 210600
| Tot.Procument | [5 empty] | 351000
| Tot.implementation | [5 empty] | 1521000.0029
| Tot(T&C / Configuration+Handover) | [5 empty] | 444600
| Overall Completion | [5 empty] | 2316600.0029
| Overall Completion Percentage | [5 empty] | 99%
| DESCRIPTION Breakdown of Procument finshing Sfc Building =40% | [7 empty] | DESCRIPTION Breakdown of Constructiom finshing Sfc Building =32%
| Roof insulation and Toilet | 10% |  | 25% | 8775 | TRACKER #14 |  |  | Roof insulation and Toilet |  |  | 10% | 25% | 38025 | TRACKER #14
| Plumbing foundation |  |  | 15% | 5265 | TRACKER #17 |  |  | Plumbing foundation |  |  |  | 15% | 22815 | TRACKER #17
| Electrical foundation |  |  | 15% | 5265 | (TRACKER #14)=40% |  |  | Electrical foundation |  |  |  | 15% | 22815 | (TRACKER #14)=40% |  | (TRACKER #26)=60%
| Hvac foundation |  |  | 15% | 5265 | (TRACKER #14)=40% |  |  | Hvac foundation |  |  |  | 15% | 22815 | (TRACKER #14)=40% |  | (TRACKER #26)=60%
| Security foundation |  |  | 15% | 5265 | TRACKER #15 |  |  | Security foundation |  |  |  | 15% | 22815 | TRACKER #15
| Fire alarm foundation |  |  | 15% | 5265 | TRACKER #22 |  |  | Fire alarm foundation |  |  |  | 15% | 22815 | TRACKER #22
| Interior plastering | 10% |  | 10% | 3510 | TRACKER #21 |  |  | Interior plastering |  |  | 10% | 10% | 15210 | TRACKER #22
| Exterior plastering |  |  | 10% | 3510 | TRACKER #14 |  |  | Exterior plastering |  |  |  | 10% | 15210 | TRACKER #14
| Ceiling |  |  | 10% | 3510 | TRACKER #23 |  |  | Ceiling |  |  |  | 10% | 15210 | TRACKER #23
| Interior paint |  |  | 10% | 3510 | TRACKER #24 |  |  | Interior paint |  |  |  | 10% | 15210 | TRACKER #14
| Exterior paint |  |  | 10% | 3510 | TRACKER #14 |  |  | Exterior paint |  |  |  | 10% | 15210 | TRACKER #18
| Doors and Windows |  |  | 10% | 3510 | TRACKER #17 |  |  | Doors and Windows |  |  |  | 10% | 15210 | TRACKER #24
| Tiles |  |  | 10% | 3510 | TRACKER #21 |  |  | Tiles |  |  |  | 10% | 15210 | TRACKER #21
| Epoxy |  |  | 10% | 3510 | TRACKER # |  |  | Epoxy |  |  |  | 10% | 15210 | (TRACKER #26)*30.76925%
| Raised floor |  |  | 10% | 3510 | TRACKER #27 |  |  | Raised floor |  |  |  | 10% | 15210 | TRACKER #27
| Kerbstone and interlock |  |  | 10% | 3510 | TRACKER #27 |  |  | Kerbstone and interlock |  |  |  | 10% | 15210 | TRACKER #27 |  | #VALUE!
| Handrail | 20% |  | 10% | 7020 | TRACKER #22 |  |  | Handrail |  |  | 12% | 10% | 18252 | TRACKER #22
| plumbing finishing |  |  | 15% | 10530 | TRACKER #23 |  |  | plumbing finishing |  |  |  | 15% | 27378 | TRACKER #23 |  | 30.77%
| Electrical finishing |  |  | 15% | 10530 | TRACKER #26 |  |  | Electrical finishing |  |  |  | 15% | 27378 | TRACKER #27
| Hvac finishing |  |  | 15% | 10530 | TRACKER #24 |  |  | Hvac finishing |  |  |  | 15% | 27378 | TRACKER #26
| Security finishing |  |  | 15% | 10530 | TRACKER #25 |  |  | Security finishing |  |  |  | 15% | 27378 | TRACKER #25
| Fire alarm finishing |  |  | 15% | 10530 | TRACKER #26 |  |  | Fire alarm finishing |  |  |  | 15% | 27378 | TRACKER #26
| Building furniture |  |  | 15% | 10530 | TRACKER #27 |  |  | Building furniture |  |  |  | 15% | 27378 | TRACKER #30
| Total | 40% |  |  | 140400 |  |  |  | Total |  |  | 32% |  | 486720
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | 65% |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  | T&C / Configuration |  | Handover
CR1-008 | تأسيس غرفة الجمارك شامل جميع اعمال الحفر و التأريض و الاحلال و الردم و الفحوصات الهندسيه المطلوبه على حسب التصاميم و مواصفات الهيئه العليا للامن الصناعي Supply and installtion of custom room including all earth work , excavation, soil replacement & backfilling work and all reuqired engineering testings as per the designs and HCIS standards | 0 | 1 | عدد | 27462 | 27462 |  | Stacking | Excavation | Backfilling | RFI / Config. | Acceptance
[8 empty] | 20% | 30% | 50% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 | 1 | 1
| INVOICE #27 | [5 empty] | 4119.3 | 3570.06 | 5355.09
| TRACKER #28 | [8 empty] | 1 | 1 | 1
| INVOICE #28 | [8 empty] | 8925.15 | 2471.58 | 274.62
| TRACKER #31 | [11 empty] | 1
| INVOICE #31 | [11 empty] | 2746.2
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 4119.3 | 3570.06 | 5355.09 | 8925.15 | 2471.58 | 274.62 | 2746.2
| Tot.Procument | [5 empty] | 4119.3
| Tot.implementation | [5 empty] | 17850.3
| Tot(T&C / Configuration+Handover) | [5 empty] | 5492.4
| ToT.Overall Completion INVOICE | [5 empty] | 27462
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | 65% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
CR1-009 | صب القواعد الارضيه شامله الاقدام و رقبة العامود و الكمره و لوح الدرج مع عمل جميع الفحوصات المطلوبه وفقا للتصاميم الهندسيه و مواصافت الهيئه العليا للامن الصناعي Substructure work including , footing , neck column, grade beam & slab on grade and all required engineering testings as per the designs and HCIS standards | 0 | 1 | عدد | 27462 | 27462 |  | Footing | Columns | Neck Columns | Beam | RFI / Config. | Acceptance
[8 empty] | 25% | 25% | 15% | 35% | 90% | 10%
| TRACKER #28 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
| INVOICE #28 | [5 empty] | 4119.3 | 4462.575 | 4462.575 | 2677.545 | 6247.605 | 2471.58 | 274.62
| TRACKER #31 | [12 empty] | 1
| INVOICE #31 | [12 empty] | 2746.2
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 4119.3 | 4462.575 | 4462.575 | 2677.545 | 6247.605 | 2471.58 | 274.62 | 2746.2
| Tot.Procument | [5 empty] | 4119.3
| Tot.implementation | [5 empty] | 17850.3
| Tot(T&C / Configuration+Handover) | [5 empty] | 5492.4
| ToT.Overall Completion INVOICE | [5 empty] | 27462
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | 65% |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  | T&C / Configuration |  | Handover
CR1-010 | بناء الهيكل الخارجي للمبنى شامل الاعمدة الخرسانيه المسلحه و كمرة السقف و لوح السقف و الدروة مع عمل جميع الفحوصات الهندسية المطلوبه على حسب التصاميم و مواصفات الهيئه العليا للامن الصناعي Superstructure work including , RC columns ,roof beams , roof slab & parapet and all required engineering testings as per the designs and HCIS standards | 0 | 1 | عدد | 41192 | 41192 |  | Super structure | Parpet | RFI / Config. | Acceptance
[8 empty] | 70% | 30% | 90% | 10%
| TRACKER #28 | [5 empty] | 1 | 0.5
| INVOICE #28 | [5 empty] | 6178.8 | 9371.18
| TRACKER #29 | [6 empty] | 0.5 | 1 | 1 | 1
| INVOICE #29 | [6 empty] | 9371.18 | 8032.44 | 3707.28 | 411.92
| TRACKER #31 | [10 empty] | 1
| INVOICE #31 | [10 empty] | 4119.2
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 6178.8 | 18742.36 | 8032.44 | 3707.28 | 411.92 | 4119.2
| Tot.Procument | [5 empty] | 6178.8
| Tot.implementation | [5 empty] | 26774.8
| Tot(T&C / Configuration+Handover) | [5 empty] | 8238.4
| ToT.Overall Completion INVOICE | [5 empty] | 41192
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | 65% |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  | T&C / Configuration |  | Handover
CR1-011 | عزل الاسطح على حسب المواصفات و المقاييس لدى الهيئه العليا للامن الصناعي Waterproofing work for roof slab as per HCIS standards | 0 | 1 | عدد | 13731 | 13731 |  | Prepration | Roof Insulation | RFI / Config. | Acceptance
[8 empty] | 20% | 80% | 90% | 10%
| TRACKER #30 | [5 empty] | 1 | 1
| INVOICE #30 | [5 empty] | 2059.65 | 1785.03
| TRACKER #33 | [7 empty] | 1 | 1 | 1 | 1
| INVOICE #33 | [7 empty] | 7140.12 | 1235.79 | 137.31 | 1373.1
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 2059.65 | 1785.03 | 7140.12 | 1235.79 | 137.31 | 1373.1
| Tot.Procument | [5 empty] | 2059.65
| Tot.implementation | [5 empty] | 8925.15
| Tot(T&C / Configuration+Handover) | [5 empty] | 2746.2
| ToT.Overall Completion INVOICE | [5 empty] | 13731
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | 65% |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  | T&C / Configuration |  | Handover
CR1-012 | جميع اعمال البناء شاملة الجدران المقاومه للرصاص مسلح بالحديد بشكل عامودي و افقي و مملوء بمادة الجراوت على حسب المخططات و مواصفات الهيئه العليا للامن الصناعي All masonary work including solid/ rigged insualted /hollow / Ballistic protected CMU with RCC lintels over openings vertical and horizantal reinforcement, fixture & filler grout as per designs and HCIS standards | 0 | 1 | عدد | 27462 | 27462 |  | Prepration | Construction of Ballistic Wall | RFI / Config. | Acceptance
[8 empty] | 20% | 80% | 90% | 10%
| TRACKER #29 | [5 empty] | 1 | 1 | 1 | 1 | 1
| INVOICE #29 | [5 empty] | 4119.3 | 3570.06 | 14280.24 | 2471.58 | 274.62
| TRACKER #31 | [10 empty] | 1
| INVOICE #31 | [10 empty] | 2746.2
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 4119.3 | 3570.06 | 14280.24 | 2471.58 | 274.62 | 2746.2
| Tot.Procument | [5 empty] | 4119.3
| Tot.implementation | [5 empty] | 17850.3
| Tot(T&C / Configuration+Handover) | [5 empty] | 5492.4
| ToT.Overall Completion INVOICE | [5 empty] | 27462
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | [6 empty] | 65% | [6 empty] | 10% |  | 10%
[7 empty] | Procurement | [6 empty] | CONSTRUCTION | [6 empty] | T&C / Configuration |  | Handover
CR1-013 | جميع اعمال التشطيبات الداخليه شامله اللياسه و البلاط والدهانات الداخليه و الخارجيه على حسب المخططات و المواصفات All finishing works including (plaster , tiles , Accoustical tiles & paint internal and external )as per designs | 0 | 1 | عدد | 54923 | 54923 | Interior plastering | Exterior plastering | Ceiling | Interior paint | Exterior paint | Tiles | Building furniture | Interior plastering | Exterior plastering | Ceiling | Interior paint | Exterior paint | Tiles | Building furniture | RFI / Config. | Acceptance
[7 empty] | 10% | 15% | 15% | 10% | 15% | 15% | 20% | 10% | 15% | 15% | 10% | 15% | 15% | 20% | 90% | 10%
| TRACKER #30 | [6 empty] | 1 |  |  | 1 |  |  |  | 1 |  |  | 1
| INVOICE #30 | [6 empty] | 1235.7675 |  |  | 1235.7675 |  |  |  | 5354.9925 |  |  | 5354.9925
| TRACKER #31 | [5 empty] | 1 |  | 1 | 1 |  | 1 | 1 | 1
| INVOICE #31 | [5 empty] | 823.845 |  | 1235.7675 | 823.845 |  | 1235.7675 | 1647.69 | 3569.995
| TRACKER #32 | [14 empty] | 1 | 1 |  | 1 | 1 | 1 | 1 | 1
| INVOICE #32 | [14 empty] | 5354.9925 | 3569.995 |  | 5354.9925 | 7139.99 | 4943.07 | 549.23 | 5492.3
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 823.845 | 1235.7675 | 1235.7675 | 823.845 | 1235.7675 | 1235.7675 | 1647.69 | 3569.995 | 5354.9925 | 5354.9925 | 3569.995 | 5354.9925 | 5354.9925 | 7139.99 | 4943.07 | 549.23 | 5492.3
| Tot.Procument | [5 empty] | 8238.45
| Tot.implementation | [5 empty] | 35699.95
| Tot(T&C / Configuration+Handover) | [5 empty] | 10984.6
| ToT.Overall Completion INVOICE | [5 empty] | 54923
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 25% |  | 55% |  | 10% |  | 10%
[7 empty] | Procurement |  | CONSTRUCTION |  | T&C / Configuration |  | Handover
CR1-014 | اعمال التشطيبات الخارجيه شاملة الممرات والمداخل ومحيط المبنى على حسب التصاميم و المواصفات Hardscape work including walkway arround the building as per designs | 0 | 1 | عدد | 32954 | 32954 | Kerbstone and marble | interlock | Kerbstone and marble | interlock | RFI / Config. | Acceptance
[7 empty] | 50% | 50% | 50% | 50% | 90% | 10%
| TRACKER #31 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1
| INVOICE #31 | [5 empty] | 4119.25 | 4119.25 | 9062.35 | 9062.35 | 2965.86 | 329.54
| TRACKER #32 | [11 empty] | 1
| INVOICE #32 | [11 empty] | 3295.4
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 4119.25 | 4119.25 | 9062.35 | 9062.35 | 2965.86 | 329.54 | 3295.4
| Tot.Procument | [5 empty] | 8238.5
| Tot.implementation | [5 empty] | 18124.7
| Tot(T&C / Configuration+Handover) | [5 empty] | 6590.8
| ToT.Overall Completion INVOICE | [5 empty] | 32954
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% |  | 25% |  | 10% |  | 10%
[7 empty] | Procurement |  | CONSTRUCTION |  | T&C / Configuration |  | Handover
CR1-015 | توريد و تركيب الابواب و الشبابيك المضادة للرصاص على حسب التصاميم و مواصفات الهيئه العليا للامن الصناعي Supply and installation of Ballistic windows and doors as per designs and HCIS standars | 0 | 1 | عدد | 30208 | 30208 | Doors | Windows | Doors | Windows | RFI / Config. | Acceptance
[7 empty] | 60% | 40% | 60% | 40% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 | 1
| INVOICE #27 | [5 empty] | 9968.64 | 6645.76
| TRACKER #30 | [7 empty] | 1 | 1 | 1 | 1
| INVOICE #30 | [7 empty] | 4531.2 | 3020.8 | 2718.72 | 302.08
| TRACKER #31 | [11 empty] | 1
| INVOICE #31 | [11 empty] | 3020.8
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 9968.64 | 6645.76 | 4531.2 | 3020.8 | 2718.72 | 302.08 | 3020.8
| Tot.Procument | [5 empty] | 16614.4
| Tot.implementation | [5 empty] | 7552
| Tot(T&C / Configuration+Handover) | [5 empty] | 6041.6
| ToT.Overall Completion INVOICE | [5 empty] | 30208
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% |  |  | 65% |  |  | 10% |  | 10%
[7 empty] | Procurement |  |  | CONSTRUCTION |  |  | T&C / Configuration |  | Handover
CR1-016 | توريد و تركيب جميع الاعمال الميكانيه شامله اعمال السباكه والتصريف و تركيب المكيفات على حسب المخططات و التصاميم All mechanical work including roof drain and installation of AC spilt unit as per drawings and designs | 0 | 1 | عدد | 10985 | 10985 | Security | Fire alarm | Hvac | Security | Fire alarm | Hvac | RFI / Config. | Acceptance
[7 empty] | 30% | 30% | 40% | 30% | 30% | 40% | 90% | 10%
| TRACKER #31 | [5 empty] | 1 | 1 | 1
| INVOICE #31 | [5 empty] | 494.325 | 494.325 | 659.1
| TRACKER #32 | [8 empty] | 1 |  | 1
| INVOICE #32 | [8 empty] | 2142.075 |  | 2856.1
| TRACKER #33 | [9 empty] | 1 |  | 1 | 1
| INVOICE #33 | [9 empty] | 2142.075 |  | 988.65 | 109.85
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Overall Completion INVOICE | [5 empty] | 494.325 | 494.325 | 659.1 | 2142.075 | 2142.075 | 2856.1 | 988.65 | 109.85 | 0
| Tot.Procument | [5 empty] | 1647.75
| Tot.implementation | [5 empty] | 7140.25
| Tot(T&C / Configuration+Handover) | [5 empty] | 1098.5
| ToT.Overall Completion INVOICE | [5 empty] | 9886.5
| Overall Completion percentage | [5 empty] | 90%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% |  | 65% |  | 10% |  | 10%
[7 empty] | Procurement |  | CONSTRUCTION |  | T&C / Configuration |  | Handover
CR1-017 | توريد وتركيب جميع اعمال الكهرباء مع الربط الى النقطة الاخيره على حسب الرسومات والتصاميم All elecrical works including ( 1st fix , 2nd fix & 3rd fix )as per drawings and designs | 0 | 1 | عدد | 8238 | 8238 | Electrical foundation | Electrical finishing | Electrical foundation | Electrical finishing | RFI / Config. | Acceptance
[7 empty] | 50% | 50% | 50% | 50% | 90% | 10%
| TRACKER #31 | [5 empty] | 1 | 1
| INVOICE #31 | [5 empty] | 617.85 | 617.85
| TRACKER #32 | [7 empty] | 1 | 1 | 1 | 1 | 1
| INVOICE #32 | [7 empty] | 2677.35 | 2677.35 | 741.42 | 82.38 | 823.8
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 617.85 | 617.85 | 2677.35 | 2677.35 | 741.42 | 82.38 | 823.8
| Tot.Procument | [5 empty] | 1235.7
| Tot.implementation | [5 empty] | 5354.7
| Tot(T&C / Configuration+Handover) | [5 empty] | 1647.6
| ToT.Overall Completion INVOICE | [5 empty] | 8238
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
NBQ-018 | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | 0 | 1 | عدد | 2900 | 2900 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 1
| INVOICE #27 | [5 empty] | 1595
| TRACKER #32 | [6 empty] | 1 | 1 | 1 | 1 | 1
| INVOICE #32 | [6 empty] | 362.5 | 145 | 72.5 | 72.5 | 72.5
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1595 | 362.5 | 145 | 72.5 | 72.5 | 72.5 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1595
| Tot.implementation | [5 empty] | 725
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 2320
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
NBQ-019 | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | 0 | 1 | عدد | 3160 | 3160 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 1
| INVOICE #27 | [5 empty] | 1738
| TRACKER #32 | [6 empty] | 1 | 1 | 1 | 1
| INVOICE #32 | [6 empty] | 395 | 158 | 158 | 79
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1738 | 395 | 158 | 158 | 79 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1738
| Tot.implementation | [5 empty] | 790
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 2528
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
NBQ-020 | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | 0 | 1 | عدد | 190 | 190 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 1
| INVOICE #27 | [5 empty] | 104.5
| TRACKER #32 | [6 empty] | 1 | 1 | 1 | 1
| INVOICE #32 | [6 empty] | 23.75 | 9.5 | 9.5 | 4.75
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 104.5 | 23.75 | 9.5 | 9.5 | 4.75 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 104.5
| Tot.implementation | [5 empty] | 47.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 152
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
NBQ-021 | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Electric Lock | 0 | 1 | عدد | 1200 | 1200 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 1
| INVOICE #27 | [5 empty] | 660
| TRACKER #32 | [6 empty] | 1 | 1 | 1 | 1
| INVOICE #32 | [6 empty] | 150 | 60 | 60 | 30
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 660 | 150 | 60 | 60 | 30 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 660
| Tot.implementation | [5 empty] | 300
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 960
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
NBQ-022 | ﺯﺭ ﺍﻟﺿﻐﻁ ﻟﻠﺧﺭﻭﺝ ( EPB ) Exit Push Button | 0 | 1 | عدد | 160 | 160 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 1
| INVOICE #27 | [5 empty] | 88
| TRACKER #32 | [6 empty] | 1 | 1 | 1 | 1
| INVOICE #32 | [6 empty] | 20 | 8 | 8 | 4
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 88 | 20 | 8 | 8 | 4 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 88
| Tot.implementation | [5 empty] | 40
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 128
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-164 | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ ( CEFX ) External Fixed Camera | 8 | 12 | عدد | 3200 | 38400 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 8
| INVOICE #13 | [5 empty] | 14080
| TRACKER #27 | [5 empty] | 4 | 3 |  | 3 | 3
| INVOICE #27 | [5 empty] | 7040 | 1200 |  | 240 | 240
| TRACKER #28 | [6 empty] | 9 | 12 | 9 | 9 | 12
| INVOICE #28 | [6 empty] | 3600 | 1920 | 720 | 720 | 960
| Overall Completion TRACKER | [5 empty] | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 21120 | 4800 | 1920 | 960 | 960 | 960 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 21120
| Tot.implementation | [5 empty] | 9600
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 30720
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% |  | 25% | [6 empty] | 10% |  | 10%
[7 empty] | Procurement |  | CONSTRUCTION | [6 empty] | T&C / Configuration |  | Handover
BQ-165 | عمود كاميرا CCTV Pole | 4 | 6 | عدد | 1650 | 9900 | POLE | FOUNDATION BASE | Precasting Foundations | Excavation | Lean Conc. | Foundation Installation | Pole Installation | BF & Compaction | Pole Alignment | RFI / Config. | Acceptance
[7 empty] | 60% | 40% | 20% | 20% | 10% | 10% | 25% | 10% | 5% | 90% | 10%
| TRACKER #18 | [5 empty] | 4 | 4
| INVOICE #18 | [5 empty] | 2179.5 | 1453.5
| TRACKER #27 | [5 empty] | 2 | 2 | 6 | 6 | 6 | 6 | 3 | 6 | 3 | 3 | 3
| INVOICE #27 | [5 empty] | 1087.5 | 724.5 | 495 | 495 | 247.5 | 247.5 | 309.375 | 247.5 | 61.875 | 445.5 | 49.5
| TRACKER #31 | [14 empty] | 6 | 6
| INVOICE #31 | [14 empty] | 891 | 99
| TRACKER #33 | [11 empty] | 3 |  | 3 | -3 | -3
| INVOICE #33 | [11 empty] | 309.375 |  | 61.875 | -445.5 | -49.5
| Overall Completion TRACKER | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
| Overall Completion INVOICE | [5 empty] | 3267 | 2178 | 495 | 495 | 247.5 | 247.5 | 618.75 | 247.5 | 123.75 | 891 | 99 | 0
| Tot.Procument | [5 empty] | 5445
| Tot.implementation | [5 empty] | 2475
| Tot(T&C / Configuration+Handover) | [5 empty] | 990
| ToT.Overall Completion INVOICE | [5 empty] | 8910
| Overall Completion percentage | [5 empty] | 90%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-166 | كاميرا متحركة خارجية ( CEPZ ) External PTZ Camera | 2 | 2 | عدد | 8400 | 16800 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 2 | 2 |  | 2 | 2
| INVOICE #27 | [5 empty] | 9240 | 2100 |  | 420 | 420
| TRACKER #28 | [7 empty] | 2 |  |  | 2
| INVOICE #28 | [7 empty] | 840 |  |  | 420
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 9240 | 2100 | 840 | 420 | 420 | 420 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 9240
| Tot.implementation | [5 empty] | 4200
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 13440
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% |  |  | 25% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement |  |  | CONSTRUCTION | [5 empty] | T&C / Configuration |  | Handover
BQ-167 | بوابة منزلقة آلية ( SGMD ) Motorized Swing Gate | 4 | 6 | عدد | 49850 | 299100 | Gate | Motor | Padlock | Excavation | Casting Foundations | Gate Installation | Backfilling | Cabling & Termination | Testing | RFI / Config. | Acceptance
[7 empty] | 70% | 20% | 10% | 25% | 15% | 20% | 20% | 10% | 10% | 90% | 10%
| TRACKER #12 | [5 empty] | 4
| INVOICE #12 | [5 empty] | 76769
| TRACKER #15 | [6 empty] | 4 | 4
| INVOICE #15 | [6 empty] | 21934 | 10967
| TRACKER #24 | [8 empty] | 4 | 4
| INVOICE #24 | [8 empty] | 12462.5 | 7477.5
| TRACKER #27 | [5 empty] | 2 | 2 | -4 | 2 | 2 | 6 | 6 | 5
| INVOICE #27 | [5 empty] | 38384.5 | 10967 | -10967 | 6231.25 | 3738.75 | 14955 | 14955 | 6231.25
| TRACKER #31 | [12 empty] | 1
| INVOICE #31 | [12 empty] | 1246.25
| Overall Completion TRACKER | [5 empty] | 6 | 6 | 0 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 115153.5 | 32901 | 0 | 18693.75 | 11216.25 | 14955 | 14955 | 7477.5 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 148054.5
| Tot.implementation | [5 empty] | 67297.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 215352
| Overall Completion percentage | [5 empty] | 72%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [5 empty] | T&C / Configuration |  | Handover
BQ-168 | حاجز الذراع الكهربائي ( RAB ) Raise Arm Barrier | 4 | 6 | عدد | 9500 | 57000 |  | Excavation | Casting Foundations | Arm Barrier Installation | Backfilling | Cabling & Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 25% | 15% | 20% | 20% | 10% | 10% | 90% | 10%
| TRACKER #15 | [5 empty] | 4
| INVOICE #15 | [5 empty] | 20900
| TRACKER #27 | [5 empty] | 2 | 6 | 6 | 6 | 6 | 6
| INVOICE #27 | [5 empty] | 10450 | 3562.5 | 2137.5 | 2850 | 2850 | 1425
| TRACKER #31 | [11 empty] | 6
| INVOICE #31 | [11 empty] | 1425
| Overall Completion TRACKER | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 31350 | 3562.5 | 2137.5 | 2850 | 2850 | 1425 | 1425 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 31350
| Tot.implementation | [5 empty] | 14250
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 45600
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-169 | حساس استشعار أرضي ( SLP ) Safety Loop | 12 | 18 | عدد | 1800 | 32400 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #26 | [5 empty] | 12
| INVOICE #26 | [5 empty] | 11880
| TRACKER #32 | [5 empty] | 6
| INVOICE #32 | [5 empty] | 5940
| TRACKER #33 | [6 empty] | 18 | 18 | 18
| INVOICE #33 | [6 empty] | 4050 | 1620 | 1620
| Overall Completion TRACKER | [5 empty] | 18 | 18 | 18 | 18 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 17820 | 4050 | 1620 | 1620 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 17820
| Tot.implementation | [5 empty] | 7290
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 25110
| Overall Completion percentage | [5 empty] | 77.5%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 60% | 20% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [5 empty] | T&C / Configuration |  | Handover
BQ-170 | مصدات طريق ( ROBK ) Road blocker | 4 | 6 | عدد | 172800 | 1036800 |  | Excavation | Casting Foundations | Road blocker Installation | Backfilling | Cabling & Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 25% | 15% | 20% | 20% | 10% | 10% | 90% | 10%
| TRACKER #20 | [5 empty] | 1.2
| INVOICE #20 | [5 empty] | 124416
| TRACKER #25 | [5 empty] | 2.8 | 4 | 4 | 4
| INVOICE #25 | [5 empty] | 290304 | 34560 | 20736 | 27648
| TRACKER #27 | [5 empty] | 2 | 2 | 2 | 2 | 6
| INVOICE #27 | [5 empty] | 207360 | 17280 | 10368 | 13824 | 41472
| TRACKER #30 | [10 empty] | 6
| INVOICE #30 | [10 empty] | 20736
| TRACKER #31 | [11 empty] | 6
| INVOICE #31 | [11 empty] | 20736
| Overall Completion TRACKER | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 622080 | 51840 | 31104 | 41472 | 41472 | 20736 | 20736 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 622080
| Tot.implementation | [5 empty] | 207360
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 829440
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% | [6 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [6 empty] | T&C / Configuration |  | Handover
BQ-171 | إشارات مرور Traffic Lights | 6 | 12 | عدد | 3200 | 38400 |  | Excavation | Casting Foundations | Pole Installation | Lighting Fixtures | Component Installation | Cabling & Termination | BF & Compaction | RFI / Config. | Acceptance
[8 empty] | 20% | 15% | 10% | 10% | 25% | 10% | 10% | 90% | 10%
| TRACKER #22 | [5 empty] | 4
| INVOICE #22 | [5 empty] | 7040
| TRACKER #26 | [5 empty] | 2
| INVOICE #26 | [5 empty] | 3520
| TRACKER #27 | [5 empty] | 6 | 12 | 12 | 12 | 12 | 12 | 12 | 12
| INVOICE #27 | [5 empty] | 10560 | 1920 | 1440 | 960 | 960 | 2400 | 960 | 960
| Overall Completion TRACKER | [5 empty] | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 21120 | 1920 | 1440 | 960 | 960 | 2400 | 960 | 960 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 21120
| Tot.implementation | [5 empty] | 9600
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 30720
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  | T&C / Configuration |  | Handover
BQ-172 | مطبات التحكم في السرعة Speed Humps | 4 | 6 | عدد | 2300 | 13800 |  | Site Preparation | Anchoring on Ashphalt | Placing of Speed Humps | RFI / Config. | Acceptance
[8 empty] | 10% | 80% | 10% | 90% | 10%
| TRACKER #20 | [5 empty] | 4
| INVOICE #20 | [5 empty] | 5060
| TRACKER #28 | [5 empty] | 2
| INVOICE #28 | [5 empty] | 2530
| Overall Completion TRACKER | [5 empty] | 6 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 7590 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 7590
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 7590
| Overall Completion percentage | [5 empty] | 55%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-173 | لوحة تحكم في مصدات الطريق ( RBCP ) Road Blocker Cabinet Panel | 4 | 6 | عدد | 7200 | 43200 |  | Cabinet Mounting | Component Installation | Cabling & Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 30% | 10% | 10% | 90% | 10%
| TRACKER #25 | [5 empty] | 4
| INVOICE #25 | [5 empty] | 15840
| TRACKER #28 | [5 empty] | 2
| INVOICE #28 | [5 empty] | 7920
| TRACKER #30 | [6 empty] | 6 | 6 | 6
| INVOICE #30 | [6 empty] | 5400 | 3240 | 1080
| TRACKER #31 | [9 empty] | 6
| INVOICE #31 | [9 empty] | 1080
| Overall Completion TRACKER | [5 empty] | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 23760 | 5400 | 3240 | 1080 | 1080 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 23760
| Tot.implementation | [5 empty] | 10800
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 34560
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-174 | مفتاح تحكم في مصدات الطريق ( RBCS ) Road Blocker Control Switch | 4 | 6 | عدد | 1400 | 8400 |  | Control Switch Inst'n | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 6 | 6 |  | 6
| INVOICE #27 | [5 empty] | 5880 | 420 |  | 168
| TRACKER #31 | [7 empty] | 6 |  | 6
| INVOICE #31 | [7 empty] | 168 |  | 84
| Overall Completion TRACKER | [5 empty] | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 5880 | 420 | 168 | 168 | 84 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 5880
| Tot.implementation | [5 empty] | 840
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 6720
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-175 | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | 5 | 11 | عدد | 3160 | 34760 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 5
| INVOICE #13 | [5 empty] | 8690
| TRACKER #27 | [5 empty] | 6 | 7 |  | 7
| INVOICE #27 | [5 empty] | 10428 | 2765 |  | 1106
| Overall Completion TRACKER | [5 empty] | 11 | 7 | 0 | 7 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 19118 | 2765 | 0 | 1106 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 19118
| Tot.implementation | [5 empty] | 3871
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 22989
| Overall Completion percentage | [5 empty] | 66.14%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-176 | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intecom Call Panel | 1 | 1 | عدد | 4950 | 4950 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 |  | 1
| INVOICE #27 | [5 empty] | 2722.5 |  | 247.5
| TRACKER #28 | [6 empty] | 1 |  | 1 | 1
| INVOICE #28 | [6 empty] | 618.75 |  | 247.5 | 123.75
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 2722.5 | 618.75 | 247.5 | 247.5 | 123.75 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 2722.5
| Tot.implementation | [5 empty] | 1237.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 3960
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-177 | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻠﻧﻅﺎﻡ الأﻣﻧﻲ ISS ISS Work Station | 1 | 1 | عدد | 6200 | 6200 |  | Workstation Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #16 | [5 empty] | 1
| INVOICE #16 | [5 empty] | 4340
| TRACKER #28 | [6 empty] | 1 | 1
| INVOICE #28 | [6 empty] | 310 | 124
| TRACKER #31 | [7 empty] | 1 |  | 1
| INVOICE #31 | [7 empty] | 124 |  | 62
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 4340 | 310 | 248 | 0 | 62 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 4340
| Tot.implementation | [5 empty] | 620
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 4960
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-178 | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Workstation | 1 | 2 | عدد | 6200 | 12400 |  | Workstation Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 1
| INVOICE #13 | [5 empty] | 4340
| TRACKER #28 | [5 empty] | 1 | 2 | 2
| INVOICE #28 | [5 empty] | 4340 | 620 | 248
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 8680 | 620 | 248 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 8680
| Tot.implementation | [5 empty] | 868
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 9548
| Overall Completion percentage | [5 empty] | 77%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-179 | 1ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺭﺋﻳﺳﻳﺔ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intercom Master Unit | 1 | 1 | عدد | 5600 | 5600 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 1
| INVOICE #13 | [5 empty] | 3080
| TRACKER #27 | [7 empty] | 1
| INVOICE #27 | [7 empty] | 280
| TRACKER #28 | [6 empty] | 1 |  | 1 | 1
| INVOICE #28 | [6 empty] | 700 |  | 280 | 140
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 3080 | 700 | 280 | 280 | 140 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 3080
| Tot.implementation | [5 empty] | 1400
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 4480
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-180 | ﻟﻭﺣﺔ ﻣﻔﺎﺗﻳﺢ ﺍﻟﺩﻭﺍﺋﺭ ﺍﻟﺗﻠﻔﺯﻳﻭﻧﻳﺔ ﺍﻟﻣﻐﻠﻘﺔ ( CTKB ) CCTV Keyboard | 1 | 1 | عدد | 1850 | 1850 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #26 | [5 empty] | 1
| INVOICE #26 | [5 empty] | 1017.5
| TRACKER #28 | [6 empty] | 1 | 1
| INVOICE #28 | [6 empty] | 231.25 | 92.5
| TRACKER #31 | [7 empty] | 1 |  | 1
| INVOICE #31 | [7 empty] | 92.5 |  | 46.25
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1017.5 | 231.25 | 185 | 0 | 46.25 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1017.5
| Tot.implementation | [5 empty] | 462.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1480
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-181 | ﺟﻬﺎﺯ ﺇﻧﺫﺍﺭ ﺻﻭﺗﻲ ﺿﻭﺋﻲ ( SPAS ) Flashing Sounder | 2 | 2 | عدد | 1350 | 2700 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 2
| INVOICE #14 | [5 empty] | 1485
| Overall Completion TRACKER | [5 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1485 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1485
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1485
| Overall Completion percentage | [5 empty] | 55%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-182 | ﺯﺭ ﺇﻧﺫﺍﺭ ﺍﻟﻁﻭﺍﺭﺉ ( EAB ) Emergency Alarm Button | 1 | 1 | عدد | 220 | 220 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 1
| INVOICE #14 | [5 empty] | 154
| TRACKER #31 | [6 empty] | 1 | 1 | 1 | 1
| INVOICE #31 | [6 empty] | 13.2 | 4.4 | 2.2 | 2.2
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 154 | 13.2 | 4.4 | 2.2 | 2.2 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 154
| Tot.implementation | [5 empty] | 22
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 176
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-183 | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required | 1 | 1 | عدد | 29700 | 29700 |  | Cabinet / Rack | UPS Installation | Batteries Installation | Cabling & Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 30% | 30% | 20% | 10% | 10% | 90% | 10%
| TRACKER #25 | [5 empty] | 1
| INVOICE #25 | [5 empty] | 20790
| TRACKER #31 | [5 empty] | -1
| INVOICE #31 | [5 empty] | -20790
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-184 | ﺟﻬﺎﺯ ﻛﺷﻑ ﻣﺗﻔﺟﺭﺍﺕ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ Hand-Held Explosive Detector | 1 | 1 | عدد | 132000 | 132000 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #21 | [5 empty] | 1
| INVOICE #21 | [5 empty] | 92400
| TRACKER #31 | [6 empty] | 1 |  | 1
| INVOICE #31 | [6 empty] | 7920 |  | 1320
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 92400 | 7920 | 0 | 1320 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 92400
| Tot.implementation | [5 empty] | 9240
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 101640
| Overall Completion percentage | [5 empty] | 77%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-185 | ﺯﺭ ﺍﻟﺿﻐﻁ ﻟﻠﺧﺭﻭﺝ ( EPB ) Exit Push Button | 1 | 1 | عدد | 160 | 160 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 1
| INVOICE #14 | [5 empty] | 88
| TRACKER #27 | [6 empty] | 1 |  | 1
| INVOICE #27 | [6 empty] | 20 |  | 8
| TRACKER #31 | [7 empty] | 1 |  | 1
| INVOICE #31 | [7 empty] | 8 |  | 4
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 88 | 20 | 8 | 8 | 4 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 88
| Tot.implementation | [5 empty] | 40
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 128
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-186 | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Electric Lock | 1 | 1 | عدد | 1200 | 1200 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 1
| INVOICE #14 | [5 empty] | 660
| TRACKER #27 | [6 empty] | 1 |  | 1
| INVOICE #27 | [6 empty] | 150 |  | 60
| TRACKER #31 | [7 empty] | 1 |  | 1
| INVOICE #31 | [7 empty] | 60 |  | 30
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 660 | 150 | 60 | 60 | 30 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 660
| Tot.implementation | [5 empty] | 300
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 960
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-187 | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) Emergency Break Glass Unit | 1 | 1 | عدد | 240 | 240 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 1
| INVOICE #14 | [5 empty] | 132
| TRACKER #31 | [6 empty] | 1 | 1 | 1 | 1
| INVOICE #31 | [6 empty] | 30 | 12 | 12 | 6
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 132 | 30 | 12 | 12 | 6 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 132
| Tot.implementation | [5 empty] | 60
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 192
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-188 | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | 1 | 1 | عدد | 190 | 190 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 1
| INVOICE #14 | [5 empty] | 104.5
| TRACKER #27 | [6 empty] | 1 |  | 1
| INVOICE #27 | [6 empty] | 23.75 |  | 9.5
| TRACKER #31 | [7 empty] | 1 |  | 1
| INVOICE #31 | [7 empty] | 9.5 |  | 4.75
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 104.5 | 23.75 | 9.5 | 9.5 | 4.75 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 104.5
| Tot.implementation | [5 empty] | 47.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 152
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-189 | ﻫﺎﺗﻑ ( TEL ) Telephone | 2 | 2 | عدد | 2300 | 4600 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 2 |  | 2
| INVOICE #27 | [5 empty] | 3220 |  | 92
| TRACKER #28 | [6 empty] | 2 |  | 2 | 2
| INVOICE #28 | [6 empty] | 276 |  | 46 | 46
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 3220 | 276 | 92 | 46 | 46 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 3220
| Tot.implementation | [5 empty] | 460
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 3680
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-190 | ﺍﻟﺧﻁ ﺍﻟﺳﺎﺧﻥ Hot Line | 1 | 1 | عدد | 2300 | 2300 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 |  | 1
| INVOICE #27 | [5 empty] | 1610 |  | 46
| TRACKER #28 | [6 empty] | 1 |  | 1 | 1
| INVOICE #28 | [6 empty] | 138 |  | 23 | 23
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1610 | 138 | 46 | 23 | 23 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1610
| Tot.implementation | [5 empty] | 230
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1840
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-191 | ﺭﺍﺩﻳﻭ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ ( HHR ) Hand Held Radio | 1 | 1 | عدد | 3800 | 3800 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-192 | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺩﺍﺧﻠﻳﺔ ﻋﻠﻰ ﺷﻛﻝ ﻗﺑﺔ ( CIDX ) Internal Fixed Mini Dome Camera | 1 | 1 | عدد | 2600 | 2600 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 1
| INVOICE #13 | [5 empty] | 1430
| TRACKER #27 | [6 empty] | 1 |  | 1 | 1
| INVOICE #27 | [6 empty] | 325 |  | 65 | 65
| TRACKER #28 | [7 empty] | 1 |  | 1 | 1
| INVOICE #28 | [7 empty] | 130 |  | 65 | 65
| TRACKER #31 | [9 empty] | -1
| INVOICE #31 | [9 empty] | -65
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1430 | 325 | 130 | 65 | 65 | 65 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1430
| Tot.implementation | [5 empty] | 650
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 2080
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-193 | ﻛﺎﻣﻳﺭﺍ ﻣﻊ ﺍﻻﻧﺎﺭﺓ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Camera | 2 | 3 | عدد | 56200 | 168600 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #15 | [5 empty] | 2
| INVOICE #15 | [5 empty] | 61820
| TRACKER #27 | [5 empty] | 1 | 3 |  | 3 | 3
| INVOICE #27 | [5 empty] | 30910 | 21075 |  | 4215 | 4215
| TRACKER #28 | [9 empty] | 3
| INVOICE #28 | [9 empty] | 4215
| TRACKER #29 | [9 empty] | -3
| INVOICE #29 | [9 empty] | -4215
| Overall Completion TRACKER | [5 empty] | 3 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 92730 | 21075 | 0 | 4215 | 4215 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 92730
| Tot.implementation | [5 empty] | 29505
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 122235
| Overall Completion percentage | [5 empty] | 72.5%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-194 | ﺟﻬﺎﺯ ﺍﻧﺫﺍﺭ ﺿﻭﺋﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Beacon | 2 | 3 | عدد | 2100 | 6300 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #26 | [5 empty] | 2
| INVOICE #26 | [5 empty] | 2310
| Overall Completion TRACKER | [5 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 2310 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 2310
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 2310
| Overall Completion percentage | [5 empty] | 36.67%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-195 | ﺟﻬﺎﺯ ﺍﻧﺫﺍﺭ ﺻﻭﺗﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Sounder | 2 | 3 | عدد | 1600 | 4800 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-196 | ﺣﺳﺎﺱ ﺍﺳﺗﺷﻌﺎﺭ ﺍﺭﺿﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Loop Sensor | 2 | 3 | عدد | 1800 | 5400 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #15 | [5 empty] | 2
| INVOICE #15 | [5 empty] | 1980
| TRACKER #28 | [5 empty] | 1
| INVOICE #28 | [5 empty] | 990
| Overall Completion TRACKER | [5 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 2970 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 2970
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 2970
| Overall Completion percentage | [5 empty] | 55%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-197 | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | 1 | 5 | عدد | 2900 | 14500 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #12 | [5 empty] | 1
| INVOICE #12 | [5 empty] | 1595
| TRACKER #27 | [5 empty] | 4 | 1 |  | 1 | 1
| INVOICE #27 | [5 empty] | 6380 | 362.5 |  | 72.5 | 72.5
| TRACKER #28 | [7 empty] | 1 |  |  | 1
| INVOICE #28 | [7 empty] | 145 |  |  | 72.5
| Overall Completion TRACKER | [5 empty] | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 7975 | 362.5 | 145 | 72.5 | 72.5 | 72.5 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 7975
| Tot.implementation | [5 empty] | 725
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 8700
| Overall Completion percentage | [5 empty] | 60%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-198 | ﻟﻭﺣﺔ ﺗﺣﻛﻡ ﻓﻲ ﺣﺎﺟﺯ ﺍﻟﺫﺭﺍﻉ ﺍﻟﻛﻬﺭﺑﺎﺋﻲ ( RAB ) Raise Arm Barrier Control Switch | 4 | 6 | عدد | 1400 | 8400 |  | Control Switch Inst'n | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 6 | 6 |  | 6
| INVOICE #27 | [5 empty] | 4620 | 1050 |  | 420
| TRACKER #31 | [7 empty] | 6 |  | 6
| INVOICE #31 | [7 empty] | 420 |  | 210
| Overall Completion TRACKER | [5 empty] | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 4620 | 1050 | 420 | 420 | 210 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 4620
| Tot.implementation | [5 empty] | 2100
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 6720
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-199 | ﻣﻔﺗﺎﺡ ﺍﻟﺗﺣﻛﻡ ﻓﻲ ﺍﻟﺑﻭﺍﺑﺔ ﺍﻟﻣﻧﺯﻟﻘﺔ Swing Gate Control Switch | 4 | 6 | عدد | 1400 | 8400 |  | Control Switch Inst'n | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 6 | 6 |  | 6
| INVOICE #27 | [5 empty] | 4620 | 1050 |  | 420
| Overall Completion TRACKER | [5 empty] | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 4620 | 1050 | 0 | 420 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 4620
| Tot.implementation | [5 empty] | 1470
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 6090
| Overall Completion percentage | [5 empty] | 72.5%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 60% | 20% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [5 empty] | T&C / Configuration |  | Handover
BQ-200 | الموجات الدقيقة ( المايكروويف ) Microwaves | 4 | 6 | عدد | 1480 | 8880 |  | Precasting Foundations | Excavation of Pits | Placing foundations | Component Installation | Cabling & Termination | Configuration | RFI / Config. | Acceptance
[8 empty] | 10% | 10% | 5% | 55% | 10% | 10% | 90% | 10%
| TRACKER #15 | [5 empty] | 4
| INVOICE #15 | [5 empty] | 3552
| TRACKER #27 | [5 empty] | -2
| INVOICE #27 | [5 empty] | -1776
| TRACKER #31 | [6 empty] | 2 | 2 | 2 | 2 | 2
| INVOICE #31 | [6 empty] | 59.2 | 59.2 | 29.6 | 325.6 | 59.2
| TRACKER #32 | [5 empty] | 1
| INVOICE #32 | [5 empty] | 888
| Overall Completion TRACKER | [5 empty] | 3 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 2664 | 59.2 | 59.2 | 29.6 | 325.6 | 59.2 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 2664
| Tot.implementation | [5 empty] | 532.8
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 3196.8
| Overall Completion percentage | [5 empty] | 36%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-201 | ﻋﻣﻭﺩ ﺛﺎﺑﺕ ﻟﻣﻧﻊ ﺩﺧﻭﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ - ﺗﺻﻧﻳﻑ -ASTM M50-P1 Crash Rated Static Bollard (ASTM M50-P1 Rated) | 82 | 85 | عدد | 5900 | 501500 |  | Excavation | Foundation Casting | Bollard Installation | Backfilling | RFI / Config. | Acceptance
[8 empty] | 20% | 10% | 60% | 10% | 90% | 10%
| TRACKER #18 | [5 empty] | 82
| INVOICE #18 | [5 empty] | 266090
| TRACKER #24 | [5 empty] | -1 | 77 | 77 | 77 |  | 77 | 77
| INVOICE #24 | [5 empty] | -3245 | 22715 | 11357.5 | 68145 |  | 40887 | 4543
| TRACKER #27 | [6 empty] | 4 | 4 | 4 | 81 | 4 | 4
| INVOICE #27 | [6 empty] | 1180 | 590 | 3540 | 11947.5 | 2124 | 236
| TRACKER #30 | [12 empty] | 81
| INVOICE #30 | [12 empty] | 47790
| Overall Completion TRACKER | [5 empty] | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81
| Overall Completion INVOICE | [5 empty] | 262845 | 23895 | 11947.5 | 71685 | 11947.5 | 43011 | 4779 | 47790
| Tot.Procument | [5 empty] | 262845
| Tot.implementation | [5 empty] | 119475
| Tot(T&C / Configuration+Handover) | [5 empty] | 95580
| ToT.Overall Completion INVOICE | [5 empty] | 477900
| Overall Completion percentage | [5 empty] | 95.29%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | 65% | [13 empty] | 10% |  | 10%
[7 empty] | Procurement | 10% | 45% | [5 empty] | 30% |  |  |  | 5% | 5% | 5% | T&C / Configuration |  | Handover
BQ-202 | بناء ﻭﺗﺟﻬﻳﺯﻏﺭﻓﺔ ﺍﻟﺣﺭﺍﺳﺔ ﻣﻊ مظلة ونظام الإنارة لنقاط التفتيش Construction of Gatehouse with sunshade and checkpoint lighting system | 1 | 1 | عدد | 1760000 | 1760000 |  | Site Prep | Construction of Gate house | [5 empty] | Construction of Sunshade |  |  |  | Lighting & Grounding | Cabling & Termination | Finishing Works | RFI / Config. | Acceptance
[9 empty] | Stacking | Excavation | Substructure & Concrete | Super structure | Construction of Ballistic Wall | Finishing | Foundation Excavation | Foundation concreting works | Sunshade Erection | Installation of lighting fixtures |  |  |  | 90% | 10%
[9 empty] | 3% | 7% | 20% | 20% | 10% | 40% | 10% | 20% | 40% | 30%
| TRACKER #21 | [6 empty] | 1 | 1 | 1 | 1 |  |  |  | 1
| INVOICE #21 | [6 empty] | 114400 | 15444 | 36036 | 102960 |  |  |  | 10296
| TRACKER #22 | [10 empty] | 1 |  |  |  | 1
| INVOICE #22 | [10 empty] | 102960 |  |  |  | 13728
| TRACKER #23 | [11 empty] | 1
| INVOICE #23 | [11 empty] | 51480
| TRACKER #24 | [12 empty] | 1
| INVOICE #24 | [12 empty] | 41184
| TRACKER #25 | [5 empty] | 1
| INVOICE #25 | [5 empty] | 264000 | [6 empty] | 43758
TRACKER #26
| INVOICE #26 | [12 empty] | 39897
| TRACKER #27 | [17 empty] | 0.5 | 0.5 |  | 0.5 | 0.5
| INVOICE #27 | [12 empty] | 65637 |  |  |  |  | 28600 | 28600 |  | 79200 | 8800
| TRACKER #28 | [15 empty] | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.4
| INVOICE #28 | [12 empty] | 15444 |  |  | 68640 | 10296 | 28600 | 28600 | 28600 | 63360
| TRACKER #29 | [19 empty] | 0.25 |  | 0.4
| INVOICE #29 | [19 empty] | 14300 |  | 7040
| TRACKER #31 | [19 empty] | 0.25 |  |  | 90%
| INVOICE #31 | [19 empty] | 14300 |  |  | 158400
TRACKER #32
| INVOICE #32 | [13 empty] | 24024 | 54912 | 68640 | 92664
| TRACKER #33 | [20 empty] | 0.1 | 0.1
| INVOICE #33 | [20 empty] | 15840 | 1760
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.9
| Overall Completion INVOICE | [5 empty] | 264000 | 114400 | 15444 | 36036 | 102960 | 102960 | 51480 | 205920 | 34320 | 68640 | 137280 | 102960 | 57200 | 57200 | 57200 | 158400 | 17600 | 158400
| Tot.Procument | [5 empty] | 264000
| Tot.implementation | [5 empty] | 1144000
| Tot(T&C / Configuration+Handover) | [5 empty] | 334400
| Overall Completion | [5 empty] | 1742400
| Overall Completion Percentage | [5 empty] | 99%
DESCRIPTION Breakdown of Procument finshing GH-1 Building
Roof insulation |  | 5% |  | 25% | 22000 | TRACKER #25 | 10% | 25% | 12870 | TRACKER #24
Electrical foundation |  |  |  | 20% | 17600 | TRACKER #25 |  | 20% | 10296 | TRACKER #25
HVAC foundation |  |  |  | 20% | 17600 | TRACKER #25 |  | 20% | 10296 | TRACKER #24
Security foundation |  |  |  | 20% | 17600 | TRACKER #25 |  | 20% | 10296 | TRACKER #24
Fire alarm foundation |  |  |  | 15% | 13200 | TRACKER #25 |  | 15% | 7722 | TRACKER #24
Interior plastering |  | 5% |  | 10% | 8800 | TRACKER #25 | 15% | 10% | 7722 | TRACKER #25
Exterior plastering |  |  |  | 10% | 8800 | TRACKER #25 |  | 10% | 7722 | (TRACKER #25)= | 0.33333 | TRACKER #26= | 0.66667
False Ceiling |  |  |  | 10% | 8800 | TRACKER #25 |  | 10% | 7722 | TRACKER #26
Interior paint |  |  |  | 10% | 8800 | TRACKER #25 |  | 10% | 7722 | TRACKER #27
Exterior paint |  |  |  | 15% | 13200 | TRACKER #25 |  | 15% | 11583 | TRACKER #25
Doors and Windows |  |  |  | 15% | 13200 | TRACKER #25 |  | 15% | 11583 | TRACKER #25
Tiles |  |  |  | 15% | 13200 | TRACKER #25 |  | 15% | 11583 | TRACKER #26
Kerbstone and interlock |  |  |  | 15% | 13200 | TRACKER #25 |  | 15% | 11583 | TRACKER #27
Electrical finishing |  | 5% |  | 20% | 17600 | TRACKER #25 | 15% | 20% | 15444 | TRACKER #26
HVAC finishing |  |  |  | 20% | 17600 | TRACKER #25 |  | 20% | 15444 | TRACKER #27
Security finishing |  |  |  | 20% | 17600 | TRACKER #25 |  | 20% | 15444 | TRACKER #27
Fire alarm finishing |  |  |  | 20% | 17600 | TRACKER #25 |  | 20% | 15444 | TRACKER #27
Building furniture |  |  |  | 20% | 17600 | TRACKER #25 |  | 20% | 15444 | TRACKER #28
Total |  | 15% |  |  | 264000 |  | 40% | 205920
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
NBQ-023 | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻧﻅﺎﻡ ﻟﻔﺣﺹ ﺍﺳﻔﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ UVSS | 0 | 1 | عدد | 6200 | 6200 |  | Workstation Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #28 | [5 empty] | 1 | 1 |  | 1
| INVOICE #28 | [5 empty] | 3410 | 775 |  | 310
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 3410 | 775 | 0 | 310 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 3410
| Tot.implementation | [5 empty] | 1085
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 4495
| Overall Completion percentage | [5 empty] | 72.5%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
NBQ-024 | ﻛﺎﻣﻳﺭﺍ ﻟﻧﻅﺎﻡ ﻓﺣﺹ ﺍﺳﻔﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ UVSS | 0 | 3 | عدد | 58000 | 174000 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
NBQ-025 | ﻧﻘﻁﺔ ﺍﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﻌﺳﻛﺭﻳﺔ Over Watch | 0 | 1 | عدد | 116000 | 116000 |  | Levelling & Backfilling | Ramp Concreting | Canopy installation | Finishing works | RFI / Config. | Acceptance
[8 empty] | 20% | 45% | 30% | 5% | 90% | 10%
| TRACKER #27 | [6 empty] | 1 | 1
| INVOICE #27 | [6 empty] | 5800 | 13050
| TRACKER #29 | [5 empty] | 1 |  |  | 1
| INVOICE #29 | [5 empty] | 63800 |  |  | 8700
| TRACKER #32 | [9 empty] | 1 | 1 | 1
| INVOICE #32 | [9 empty] | 1450 | 10440 | 1160
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Overall Completion INVOICE | [5 empty] | 63800 | 5800 | 13050 | 8700 | 1450 | 10440 | 1160 | 0
| Tot.Procument | [5 empty] | 63800
| Tot.implementation | [5 empty] | 29000
| Tot(T&C / Configuration+Handover) | [5 empty] | 11600
| ToT.Overall Completion INVOICE | [5 empty] | 104400
| Overall Completion percentage | [5 empty] | 90%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 25% | 55% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
CR1-026 | توريد وتركيب وإنشاء خزان أرضي بسعة 10 أمتار مكعبة، شاملاً جميع أعمال الحفر، والخرسانة المسلحة، والعزل المائي، وطلاء الإيبوكسي ، والتهوية، وجميع التوصيلات والملحقات اللازمة لضمان نظام متكامل وفعال. يتم تنفيذ الأعمال وفقاً للمخططات المعتمدة والمواصفات القياسية وتعليمات الاستشاري. يشمل السعر جميع المواد والعمالة والأدوات والاختبارات المطلوبة لإكمال العمل بالكامل. | 0 | 2 | عدد | 200000 | 400000 |  | Stacking | Excavation | Structure & Concrete | Finishing | RFI / Config. | Acceptance
[8 empty] | 5% | 20% | 50% | 25% | 90% | 10%
| TRACKER #27 | [5 empty] | 2 | 2 | 2 | 2 | 1
| INVOICE #27 | [5 empty] | 100000 | 11000 | 44000 | 110000 | 27500
| TRACKER #28 | [9 empty] | 1 | 1 | 1
| INVOICE #28 | [9 empty] | 27500 | 18000 | 2000
| TRACKER #29 | [9 empty] | -1 | -1 | -1
| INVOICE #29 | [9 empty] | -27500 | -18000 | -2000
TRACKER #30
INVOICE #30
| TRACKER #33 | [9 empty] | 1 | 2 | 2
| INVOICE #33 | [9 empty] | 27500 | 36000 | 4000
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Overall Completion INVOICE | [5 empty] | 100000 | 11000 | 44000 | 110000 | 55000 | 36000 | 4000 | 0
| Tot.Procument | [5 empty] | 100000
| Tot.implementation | [5 empty] | 220000
| Tot(T&C / Configuration+Handover) | [5 empty] | 40000
| ToT.Overall Completion INVOICE | [5 empty] | 360000
| Overall Completion percentage | [5 empty] | 90%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  | T&C / Configuration |  | Handover
CR1-027 | توريد وتركيب خزان مياه فوق الأرض مقاس 5000 لتر PVC | 0 | 1 | عدد | 8000 | 8000 |  | Prepating | Tank Installation | RFI / Config. | Acceptance
[8 empty] | 20% | 80% | 90% | 10%
TRACKER #30
INVOICE #30
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 25% | 55% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
CR1-028 | توريد وتركيب وردم أنبوب بقطر 500 مم لتامين عبارة تصريف الامطار في منطقة البوابة بما في ذلك إحاطته بالخرسانة وفقًا لمعايير ومتطلبات الهيئة الملكية وطبقًا للرسومات المعتمدة في منطقة البوابة. يشمل العمل الحفر، وتركيب الأنبوب بشكل صحيح، وتغليفه بالخرسانة، والدمك، وإعادة تأهيل السطح بالكامل حسب المتطلبات. يشمل السعر جميع المواد والعمالة والأدوات والاختبارات لضمان تنفيذ العمل بشكل كامل وفعال | 0 | 52 | م ط | 2850 | 148200 |  | Excavation | Pipe installation | Structure & Concrete | Backfilling | RFI / Config. | Acceptance
[8 empty] | 15% | 50% | 20% | 15% | 90% | 10%
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [5 empty] | T&C / Configuration |  | Handover
CR1-029 | توريد وتركيب واختبار وتشغيل كابل جهد متوسط 3C x 120mm² Cu/XLPE/STA/PVC بجهد 17kV، شاملاً أعمال الحفر بعمق 80 سم في التربة أو الأسفلت، ومد الكابل بشكل صحيح، ووضع شريط تحذيري وبلاط أحمر للحماية، وتركيب علامات تحديد كل 100 متر، وردم الحفر وإعادة تأهيل السطح، بالإضافة إلى تنفيذ نظام التأريض بالكامل، وإنهاء التوصيلات وجميع الملحقات اللازمة لضمان نظام آمن وكامل التشغيل، وفقاً للمواصفات والمعايير المعتمدة وتعليمات الاستشاري. يشمل السعر جميع المواد والعمالة والأدوات والاختبارات المطلوبة لإتمام العمل بالكامل. | 0 | 840 | عدد | 733 | 615720 |  | Excavation | Cable pulling | Tiles & WT | backfilling | Termination | MARKING (WARNING TAPE AND POST) | RFI / Config. | Acceptance
[8 empty] | 10% | 40% | 10% | 10% | 20% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 840 | 840 | 840 | 840 | 840 | 840 |  | 840
| INVOICE #27 | [5 empty] | 338646 | 15393 | 61572 | 15393 | 15393 | 30786 |  | 55414.8
| TRACKER #29 | [13 empty] | 840
| INVOICE #29 | [13 empty] | 6157.2
| TRACKER #30 | [14 empty] | 840
| INVOICE #30 | [14 empty] | 61572
| Overall Completion TRACKER | [5 empty] | 840 | 840 | 840 | 840 | 840 | 840 | 0 | 840 | 840 | 840
| Overall Completion INVOICE | [5 empty] | 338646 | 15393 | 61572 | 15393 | 15393 | 30786 | 0 | 55414.8 | 6157.2 | 61572
| Tot.Procument | [5 empty] | 338646
| Tot.implementation | [5 empty] | 138537
| Tot(T&C / Configuration+Handover) | [5 empty] | 123144
| ToT.Overall Completion INVOICE | [5 empty] | 600327
| Overall Completion percentage | [5 empty] | 97.5%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | 65% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
CR1-030 | توريد وتركيب غرفة تفتيش من الخرسانة مقاس 1.5*1.5*1.8 سم بغطاء زهر ثقيل لزوم الكهرباء بدون سلم وكل ما يلزم لانهاء البند حسب الشروط والمواصفات وتوجيهات جهة الاشراف . Electrical Manhole (1500L X 1500W X 1800D) | 0 | 3 | عدد | 16600 | 49800 |  | Excavation | Structure & Concrete | Finishing | Backfilling | RFI / Config. | Acceptance
[8 empty] | 15% | 50% | 20% | 15% | 90% | 10%
| TRACKER #31 | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| INVOICE #31 | [5 empty] | 7470 | 4855.5 | 16185 | 6474 | 4855.5 | 4482 | 498 | 4980
| Overall Completion TRACKER | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Overall Completion INVOICE | [5 empty] | 7470 | 4855.5 | 16185 | 6474 | 4855.5 | 4482 | 498 | 4980
| Tot.Procument | [5 empty] | 7470
| Tot.implementation | [5 empty] | 32370
| Tot(T&C / Configuration+Handover) | [5 empty] | 9960
| ToT.Overall Completion INVOICE | [5 empty] | 49800
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | 65% |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  | T&C / Configuration |  | Handover
CR1-031 | توريد وردم ودك بالمواد المعتمدة (مواد هندسية مختارة )على طبقات لا تتجاوز سماكتها 25 سم بما يشمل المواد وفرشها وتسويتها ومعالجة الرطوبة وإجراء الاختبارات الحقلية والمخبرية المطلوبة (بروكتور، اختبار الكثافة الحقلية، محتوى الرطوبة) وفقاً لمواصفات المشروع واعتماد المهندس المشروع | 0 | 8000 | عدد | 125 | 1000000 |  | Site Prepration | Backfilling | RFI / Config. | Acceptance
[8 empty] | 15% | 85% | 90% | 10%
| TRACKER #27 | [5 empty] | 6000 | 6000 | 6000 | 6000 | 6000
| INVOICE #27 | [5 empty] | 112500 | 73125 | 414375 | 67500 | 7500
| TRACKER #28 | [5 empty] | 1703.5 | 1703.5 | 1703.5 | 1703.5 | 1703.5
| INVOICE #28 | [5 empty] | 31940.625 | 20761.4062 | 117647.9688 | 19164.375 | 2129.375
| TRACKER #30 | [10 empty] | 7703.5
| INVOICE #30 | [10 empty] | 96293.75
| TRACKER #31 | [5 empty] | 242 | 242 | 242 | 242 | 242 | 242
| INVOICE #31 | [5 empty] | 4537.5 | 2949.375 | 16713.125 | 2722.5 | 302.5 | 3025
| Overall Completion TRACKER | [5 empty] | 7945.5 | 7945.5 | 7945.5 | 7945.5 | 7945.5 | 7945.5
| Overall Completion INVOICE | [5 empty] | 148978.125 | 96835.7812 | 548736.0938 | 89386.875 | 9931.875 | 99318.75
| Tot.Procument | [5 empty] | 148978.125
| Tot.implementation | [5 empty] | 645571.875
| Tot(T&C / Configuration+Handover) | [5 empty] | 198637.5
| ToT.Overall Completion INVOICE | [5 empty] | 993187.5
| Overall Completion percentage | [5 empty] | 99.32%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | 65% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
CR1-032 | توريد وتنفيذ رصف إسفلتي يتضمن طبقة أساس حجري بسمك 120مم، وطبقة رابطة بسمك 70مم، وطبقة سطحية بسمك 50مم، شاملاً تجهيز السطح، ورش Mc1وRC2، والدمك، وعلامات الطرق، بالإضافة إلى إجراء الاختبارات اللازمة مثل اختبار الكثافة، اختبار نسبة الإسفلت، واختبارات أخرى وفقاً للمواصفات وتعليمات المهندس المشرف | 0 | 1860 | عدد | 160 | 297600 |  | MC1 | 1st layer | RC2 | 2nd Layer | RFI / Config. | Acceptance
[8 empty] | 5% | 50% | 5% | 40% | 90% | 10%
| TRACKER #29 | [5 empty] | 1799 | 1799 | 1799 | 1799 | 1799 | 1799 | 1799
| INVOICE #29 | [5 empty] | 43176 | 9354.8 | 93548 | 9354.8 | 74838.4 | 25905.6 | 2878.4
| TRACKER #32 | [5 empty] | 61 | 61 | 61 | 61 | 61 | 61 | 61
| INVOICE #32 | [5 empty] | 1464 | 317.2 | 3172 | 317.2 | 2537.6 | 878.4 | 97.6
| Overall Completion TRACKER | [5 empty] | 1860 | 1860 | 1860 | 1860 | 1860 | 1860 | 1860 | 0
| Overall Completion INVOICE | [5 empty] | 44640 | 9672 | 96720 | 9672 | 77376 | 26784 | 2976 | 0
| Tot.Procument | [5 empty] | 44640
| Tot.implementation | [5 empty] | 193440
| Tot(T&C / Configuration+Handover) | [5 empty] | 29760
| ToT.Overall Completion INVOICE | [5 empty] | 267840
| Overall Completion percentage | [5 empty] | 90%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-203 | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺩﺍﺧﻠﻳﺔ ﻋﻠﻰ ﺷﻛﻝ ﻗﺑﺔ ( CIDX ) Internal Fixed Mini Dome Camera | 6 | 6 | عدد | 2600 | 15600 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 6
| INVOICE #13 | [5 empty] | 8580
| TRACKER #27 | [6 empty] | 6 |  | 6 | 6
| INVOICE #27 | [6 empty] | 1950 |  | 390 | 390
| TRACKER #28 | [7 empty] | 6 |  |  | 6
| INVOICE #28 | [7 empty] | 780 |  |  | 390
| Overall Completion TRACKER | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 8580 | 1950 | 780 | 390 | 390 | 390 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 8580
| Tot.implementation | [5 empty] | 3900
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 12480
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-204 | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ ( CEFX ) External Fixed Camera | 3 | 3 | عدد | 3200 | 9600 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 3
| INVOICE #13 | [5 empty] | 5280
| TRACKER #27 | [6 empty] | 3 |  | 3 | 3
| INVOICE #27 | [6 empty] | 1200 |  | 240 | 240
| TRACKER #28 | [7 empty] | 3 |  |  | 3
| INVOICE #28 | [7 empty] | 480 |  |  | 240
| Overall Completion TRACKER | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 5280 | 1200 | 480 | 240 | 240 | 240 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 5280
| Tot.implementation | [5 empty] | 2400
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 7680
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% | [6 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [6 empty] | T&C / Configuration |  | Handover
BQ-205 | عمود كاميرا CCTV Pole | 3 | 3 | عدد | 1650 | 4950 |  | Precasting Foundations | Excavation | Lean Conc. | Foundation Installation | Pole Installation | BF & Compaction | Pole Alignment | RFI / Config. | Acceptance
[8 empty] | 20% | 20% | 10% | 10% | 25% | 10% | 5% | 90% | 10%
| TRACKER #23 | [5 empty] | 3
| INVOICE #23 | [5 empty] | 2722.5
| TRACKER #27 | [6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3
| INVOICE #27 | [6 empty] | 247.5 | 247.5 | 123.75 | 123.75 | 309.375 | 123.75 | 61.875
| TRACKER #28 | [13 empty] | 3 | 3
| INVOICE #28 | [13 empty] | 445.5 | 49.5
| Overall Completion TRACKER | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| Overall Completion INVOICE | [5 empty] | 2722.5 | 247.5 | 247.5 | 123.75 | 123.75 | 309.375 | 123.75 | 61.875 | 445.5 | 49.5 | 0
| Tot.Procument | [5 empty] | 2722.5
| Tot.implementation | [5 empty] | 1237.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 495
| ToT.Overall Completion INVOICE | [5 empty] | 4455
| Overall Completion percentage | [5 empty] | 90%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-206 | ﻛﺎﻣﻳﺭﺍﺕ ﺛﺎﺑﺗﺔ ﺑﺯﺍﻭﻳﺔ ﻭﺍﺳﻌﺔ Wide Angle Fixed Cameras | 9 | 5 | عدد | 2900 | 14500 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #24 | [5 empty] | 5
| INVOICE #24 | [5 empty] | 7975
| TRACKER #27 | [6 empty] | 5 |  | 3 | 3
| INVOICE #27 | [6 empty] | 1812.5 |  | 217.5 | 217.5
| TRACKER #28 | [7 empty] | 3 |  |  | 3
| INVOICE #28 | [7 empty] | 435 |  |  | 217.5
| Overall Completion TRACKER | [5 empty] | 5 | 5 | 3 | 3 | 3 | 3 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 7975 | 1812.5 | 435 | 217.5 | 217.5 | 217.5 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 7975
| Tot.implementation | [5 empty] | 2900
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 10875
| Overall Completion percentage | [5 empty] | 75%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-207 | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | 9 | 5 | عدد | 3160 | 15800 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 5
| INVOICE #13 | [5 empty] | 8690
| TRACKER #27 | [6 empty] | 5 |  | 3
| INVOICE #27 | [6 empty] | 1975 |  | 474
| Overall Completion TRACKER | [5 empty] | 5 | 5 | 0 | 3 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 8690 | 1975 | 0 | 474 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 8690
| Tot.implementation | [5 empty] | 2449
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 11139
| Overall Completion percentage | [5 empty] | 70.5%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-208 | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | 6 | 4 | عدد | 190 | 760 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 6
| INVOICE #14 | [5 empty] | 627
| TRACKER #27 | [5 empty] | -2 | 4 |  | 4
| INVOICE #27 | [5 empty] | -209 | 95 |  | 38
| TRACKER #31 | [7 empty] | 4 |  | 4
| INVOICE #31 | [7 empty] | 38 |  | 19
| Overall Completion TRACKER | [5 empty] | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 418 | 95 | 38 | 38 | 19 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 418
| Tot.implementation | [5 empty] | 190
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 608
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-209 | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Electric Lock | 2 | 2 | عدد | 1200 | 2400 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 2
| INVOICE #14 | [5 empty] | 1320
| TRACKER #27 | [6 empty] | 2 |  | 2
| INVOICE #27 | [6 empty] | 300 |  | 120
| TRACKER #31 | [7 empty] | 2 |  | 2
| INVOICE #31 | [7 empty] | 120 |  | 60
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1320 | 300 | 120 | 120 | 60 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1320
| Tot.implementation | [5 empty] | 600
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1920
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-210 | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) Emergency Break Glass Unit | 2 | 2 | عدد | 240 | 480 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 2
| INVOICE #14 | [5 empty] | 264
| TRACKER #31 | [6 empty] | 2 | 2 | 2 | 2
| INVOICE #31 | [6 empty] | 60 | 24 | 24 | 12
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 264 | 60 | 24 | 24 | 12 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 264
| Tot.implementation | [5 empty] | 120
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 384
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-211 | ﺯﺭ ﺍﻟﺿﻐﻁ ﻟﻠﺧﺭﻭﺝ ( EPB ) Exit Push Button | 1 | 2 | عدد | 160 | 320 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 1
| INVOICE #14 | [5 empty] | 88
| TRACKER #27 | [6 empty] | 1 |  | 1
| INVOICE #27 | [6 empty] | 20 |  | 8
| TRACKER #28 | [5 empty] | 1
| INVOICE #28 | [5 empty] | 88
| TRACKER #31 | [6 empty] | 1 | 2 | 1 | 2
| INVOICE #31 | [6 empty] | 20 | 16 | 8 | 8
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 176 | 40 | 16 | 16 | 8 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 176
| Tot.implementation | [5 empty] | 80
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 256
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-212 | ﺟﻬﺎﺯ ﺍﻟﻛﺷﻑ ﻋﻥ ﺍﻟﻣﻌﺎﺩﻥ ﺑﺎﻟﻣﺭﻭﺭ ( WTMD ) Walk Through Metal Detector | 1 | 1 | عدد | 24000 | 24000 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #12 | [5 empty] | 1
| INVOICE #12 | [5 empty] | 16800
| Overall Completion TRACKER | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 16800 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 16800
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 16800
| Overall Completion percentage | [5 empty] | 70%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-213 | ﺑﺎﺏ ﺩﻭﺍﺭ ﻛﺎﻣﻝ ﺍﻻﺭﺗﻔﺎﻉ ( FHTS ) Full Height Turnstile | 3 | 3 | عدد | 50400 | 151200 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #24 | [5 empty] | 1
| INVOICE #24 | [5 empty] | 27720
| TRACKER #32 | [5 empty] | 2
| INVOICE #32 | [5 empty] | 55440
| Overall Completion TRACKER | [5 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 83160 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 83160
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 83160
| Overall Completion percentage | [5 empty] | 55%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-214 | ﻫﺎﺗﻑ ( TEL ) Telephone | 2 | 2 | عدد | 2300 | 4600 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 2 |  | 2
| INVOICE #27 | [5 empty] | 3220 |  | 92
| TRACKER #28 | [6 empty] | 1 |  | 1 | 1
| INVOICE #28 | [6 empty] | 115 |  | 46 | 23
| Overall Completion TRACKER | [5 empty] | 2 | 1 | 2 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 3220 | 115 | 92 | 46 | 23 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 3220
| Tot.implementation | [5 empty] | 276
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 3496
| Overall Completion percentage | [5 empty] | 76%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-215 | ﺍﻟﺧﻁ ﺍﻟﺳﺎﺧﻥ Hot Line | 1 | 1 | عدد | 2300 | 2300 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 |  | 1
| INVOICE #27 | [5 empty] | 1610 |  | 46
| TRACKER #28 | [6 empty] | 1 |  | 1 | 1
| INVOICE #28 | [6 empty] | 138 |  | 23 | 23
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1610 | 138 | 46 | 23 | 23 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1610
| Tot.implementation | [5 empty] | 230
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1840
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-216 | ﺭﺍﺩﻳﻭ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ ( HHR ) | 1 | 1 | عدد | 3800 | 3800 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-217 | ﻣﺣﻁﺔ ﻋﻣﻝ ﺑﻁﺎﻗﺔ ﺍﻟﻬﻭﻳﺔ ID Workstation | 1 | 1 | عدد | 6200 | 6200 |  | Workstation Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #16 | [5 empty] | 1
| INVOICE #16 | [5 empty] | 4340
| TRACKER #28 | [6 empty] | 1 |  | 1
| INVOICE #28 | [6 empty] | 310 |  | 124
| TRACKER #32 | [7 empty] | 1 |  | 1
| INVOICE #32 | [7 empty] | 124 |  | 62
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 4340 | 310 | 124 | 124 | 62 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 4340
| Tot.implementation | [5 empty] | 620
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 4960
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-218 | ﻛﺎﻣﻳﺭﺍ ﺭﻗﻣﻳﺔ ﻟﺑﻁﺎﻗﺔ ﺍﻟﻬﻭﻳﺔ ID Digital Camera | 1 | 1 | عدد | 1800 | 1800 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #28 | [5 empty] | 1
| INVOICE #28 | [5 empty] | 990
| Overall Completion TRACKER | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 990
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 990
| Overall Completion percentage | [5 empty] | 55%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-219 | ﻗﺎﺭﺉ ﺍﻟﺗﺳﺟﻳﻝ Enrollment Reader | 1 | 1 | عدد | 1650 | 1650 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 1
| INVOICE #14 | [5 empty] | 1155
| Overall Completion TRACKER | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1155 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1155
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1155
| Overall Completion percentage | [5 empty] | 70%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-220 | ﻁﺎﺑﻌﺔ ﺍﻟﺑﻁﺎﻗﺔ Card Printer | 1 | 1 | عدد | 19400 | 19400 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 1
| INVOICE #13 | [5 empty] | 13580
| TRACKER #28 | [6 empty] | 1 |  | 1
| INVOICE #28 | [6 empty] | 1164 |  | 194
| TRACKER #32 | [7 empty] | 1 |  | 1
| INVOICE #32 | [7 empty] | 388 |  | 194
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 13580 | 1164 | 388 | 194 | 194 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 13580
| Tot.implementation | [5 empty] | 1940
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 15520
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-221 | ﻣﺎﺳﺣﺔ ﺍﻷﻣﺗﻌﺔ ﺑﺎﻷﺷﻌﺔ ﺍﻟﺳﻳﻧﻳﺔ X-Ray Baggage Scanner | 1 | 1 | عدد | 152000 | 152000 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #10 | [5 empty] | 1
| INVOICE #10 | [5 empty] | 106400
| Overall Completion TRACKER | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 106400 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 106400
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 106400
| Overall Completion Percentage | [5 empty] | 64.4848
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-222 | ﺟﻬﺎﺯ ﻛﺷﻑ ﻣﺗﻔﺟﺭﺍﺕ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ Hand-Held Explosive Detector | 1 | 1 | عدد | 132000 | 132000 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #21 | [5 empty] | 1
| INVOICE #21 | [5 empty] | 92400
| TRACKER #31 | [6 empty] | 1 |  | 1
| INVOICE #31 | [6 empty] | 7920 |  | 1320
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 92400 | 7920 | 0 | 1320 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 92400
| Tot.implementation | [5 empty] | 9240
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 101640
| Overall Completion percentage | [5 empty] | 77%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-223 | ﺟﻬﺎﺯ ﻛﺷﻑ ﺍﻟﻣﻌﺎﺩﻥ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ Hand-Held Metal detector | 1 | 1 | عدد | 1300 | 1300 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #12 | [5 empty] | 1
| INVOICE #12 | [5 empty] | 910
| TRACKER #31 | [6 empty] | 1 |  | 1
| INVOICE #31 | [6 empty] | 78 |  | 13
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 910 | 78 | 0 | 13 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 910
| Tot.implementation | [5 empty] | 91
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1001
| Overall Completion percentage | [5 empty] | 77%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-224 | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required | 1 | 1 | عدد | 29700 | 29700 |  | Cabinet / Rack | UPS Installation | Batteries Installation | Cabling & Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 30% | 30% | 20% | 10% | 10% | 90% | 10%
| TRACKER #25 | [5 empty] | 1
| INVOICE #25 | [5 empty] | 20790
| TRACKER #30 | [6 empty] | 1 | 1 | 1 | 1 | 1
| INVOICE #30 | [6 empty] | 891 | 891 | 594 | 297 | 297
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 20790 | 891 | 891 | 594 | 297 | 297 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 20790
| Tot.implementation | [5 empty] | 2970
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 23760
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  | T&C / Configuration |  | Handover
BQ-225 | ﺑﺎﺏ ﺣﺩﻳﺩﻱ ﻣﻔﺻﻠﻲ ﺫﻭ ﺩﺭﻓﺗﻳﻥ ﻣﺗﻭﺍﻓﻖ ﻣﻊDouble Leaf Steel Door (Compliant with SEC-09 "Doors") DLSD ) SEC-09 ) | 2 | 2 | عدد | 11355 | 22710 |  | Door sub frames | Door & frames | RFI / Config. | Acceptance
[8 empty] | 40% | 60% | 90% | 10%
| TRACKER #17 | [5 empty] | 2
| INVOICE #17 | [5 empty] | 12490.5
| TRACKER #24 | [8 empty] | 2 | 2
| INVOICE #24 | [8 empty] | 2043.9 | 227.1
| TRACKER #25 | [6 empty] | 2 | 2
| INVOICE #25 | [6 empty] | 2271 | 3406.5
| TRACKER #30 | [10 empty] | 2
| INVOICE #30 | [10 empty] | 2271
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2
| Overall Completion INVOICE | [5 empty] | 12490.5 | 2271 | 3406.5 | 2043.9 | 227.1 | 2271
| Tot.Procument | [5 empty] | 12490.5
| Tot.implementation | [5 empty] | 5677.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 4542
| ToT.Overall Completion INVOICE | [5 empty] | 22710
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% |  |  |  | 65% | [9 empty] | 10% |  | 10%
[7 empty] | Procurement |  |  |  | 5% | 75% | [5 empty] | 10% | 5% | 5% | T&C / Configuration |  | Handover
BQ-226 | بناء ﻣﺑﻧﻰ ﺍﻟﺗﻔﺗﻳﺵ ﻭﻣﺭﻛﺯ ﺍﻟﺯﻭﺍﺭ Construction of Search Facility & Vistor Center | 1 | 1 | عدد | 2340000 | 2340000 | Substructure & Concrete | Super Structure | Construction of Ballistic Wall | Finishing | Site Prep | Construction of SFVC Bldg. | [5 empty] | MEP Works | Cabling & Termination | Finishing | RFI / Config. | Acceptance
[7 empty] | 20% | 30% | 10% | 40% |  | Stacking | Excavation | Substructure & Concrete | Super structure | Construction of Ballistic Wall | Finishng Building |  |  |  | 90% | 10%
[12 empty] | 3% | 10% | 25% | 20% | 10% | 32%
| TRACKER #21 | [9 empty] | 1 | 1 | 1 | 1
| INVOICE #21 | [9 empty] | 76050 | 34222.5 | 114075 | 285187.5
| TRACKER #22 | [5 empty] | 1 | 1 | [6 empty] | 1
| INVOICE #22 | [5 empty] | 70200 | 105300 | [6 empty] | 228150
| TRACKER #23 | [14 empty] | 1
| INVOICE #23 | [14 empty] | 114075
| TRACKER #24 | [7 empty] | 1 | 1 | [6 empty] | 1
| INVOICE #24 | [7 empty] | 35100 | 33345 | [6 empty] | 108371.25
TRACKER #25
| INVOICE #25 | [8 empty] | 19305 | [6 empty] | 74148.75
| TRACKER #26 | [16 empty] | 1
| INVOICE #26 | [8 empty] | 59670 | [6 empty] | 114075 | 152100
| TRACKER #27 | [17 empty] | 1 | 1 | 0.5 | 0.5
| INVOICE #27 | [8 empty] | 28080 | [6 empty] | 47911.5 |  | 76050 | 76050 | 105300 | 11700
| TRACKER #28 | [19 empty] | 0.25 | 0.25
| INVOICE #28 | [19 empty] | 52650 | 5850
| TRACKER #29 | [19 empty] | 0.15 | 0.15
| INVOICE #29 | [15 empty] | 20533.5 |  |  |  | 31590 | 3510
| TRACKER #31 | [21 empty] | 0.9
| INVOICE #31 | [21 empty] | 210600
| TRACKER #33 | [19 empty] | 0.1 | 0.1
| INVOICE #33 | [19 empty] | 21060 | 2340
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.9
| Overall Completion INVOICE | [5 empty] | 70200 | 105300 | 35100 | 140400 | 76050 | 34222.5 | 114075 | 285187.5 | 228150 | 114075 | 365040 | 152100 | 76050 | 76050 | 210600 | 23400 | 210600
| Tot.Procument | [5 empty] | 351000
| Tot.implementation | [5 empty] | 1521000
| Tot(T&C / Configuration+Handover) | [5 empty] | 444600
| Overall Completion | [5 empty] | 2316600
| Overall Completion Percentage | [5 empty] | 0.99
| DESCRIPTION Breakdown of Procument finshing Sfc Building =40% | [7 empty] | DESCRIPTION Breakdown of Constructiom finshing Sfc Building =32%
| Roof insulation and Toilet | 10% |  | 25% | 8775 | TRACKER #25 |  |  | Roof insulation and Toilet |  |  | 10% | 25% | 28518.75 | TRACKER #25
| Plumbing foundation |  |  | 15% | 5265 | TRACKER #24 |  |  | Plumbing foundation |  |  |  | 15% | 17111.25 | TRACKER #24
| Electrical foundation |  |  | 15% | 5265 | TRACKER #24 |  |  | Electrical foundation |  |  |  | 15% | 17111.25 | TRACKER #24
| HVAC foundation |  |  | 15% | 5265 | TRACKER #24 |  |  | HVAC foundation |  |  |  | 15% | 17111.25 | TRACKER #24
| Security foundation |  |  | 15% | 5265 | TRACKER #24 |  |  | Security foundation |  |  |  | 15% | 17111.25 | TRACKER #24
| Fire foundation |  |  | 15% | 5265 | TRACKER #24 |  |  | Fire foundation |  |  |  | 15% | 17111.25 | TRACKER #24
| Interior plastering | 10% |  | 10% | 3510 | TRACKER #25 |  |  | Interior plastering |  |  | 10% | 10% | 11407.5 | TRACKER #25
| Exterior plastering |  |  | 10% | 3510 | TRACKER #24 |  |  | Exterior plastering |  |  |  | 10% | 11407.5 | TRACKER #24
| Ceiling |  |  | 20% | 7020 | TRACKER #26 |  |  | Ceiling |  |  |  | 10% | 11407.5 | TRACKER #26
| Interior paint |  |  | 10% | 3510 | TRACKER #27 |  |  | Interior paint |  |  |  | 10% | 11407.5 | TRACKER #27
| Exterior paint |  |  | 10% | 3510 | TRACKER #24 |  |  | Exterior paint |  |  |  | 10% | 11407.5 | TRACKER #24
| Doors and Windows |  |  | 10% | 3510 | TRACKER #25 |  |  | Doors and Windows |  |  |  | 15% | 17111.25 | TRACKER #25
| Tiles |  |  | 10% | 3510 | TRACKER #25 |  |  | Tiles |  |  |  | 15% | 17111.25 | TRACKER #25
| Epoxy |  |  | 10% | 3510 | TRACKER #27 |  |  | Epoxy |  |  |  | 10% | 11407.5 | TRACKER #27
| Kerbstone and interlock | 20% |  | 10% | 3510 | TRACKER #27 |  |  | Kerbstone and interlock |  |  | 12% | 10% | 11407.5 | TRACKER #27
| Handrail |  |  | 10% | 7020 | TRACKER #27 |  |  | Handrail |  |  |  | 10% | 13689 | TRACKER #27
| plumbing finishing |  |  | 15% | 10530 | TRACKER #26 |  |  | plumbing finishing |  |  |  | 15% | 20533.5 | TRACKER #26
| Electrical finishing |  |  | 20% | 14040 | TRACKER #26 |  |  | Electrical finishing |  |  |  | 15% | 20533.5 | TRACKER #26
| Hvac finishing |  |  | 20% | 14040 | TRACKER #26 |  |  | Hvac finishing |  |  |  | 15% | 20533.5 | TRACKER #26
| Fire finishing |  |  | 20% | 14040 | TRACKER #26 |  |  | Fire finishing |  |  |  | 30% | 41067 | TRACKER #26
| Building furniture |  |  | 15% | 10530 | TRACKER #27 |  |  | Building furniture |  |  |  | 15% | 20533.5 | TRACKER #29
| Total | 40% |  |  | 140400 |  |  |  | Total |  |  | 32% |  | 365040
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | 65% |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  | T&C / Configuration |  | Handover
CR1-033 | تأسيس غرفة الجمارك شامل جميع اعمال الحفر و التأريض و الاحلال و الردم و الفحوصات الهندسيه المطلوبه على حسب التصاميم و مواصفات الهيئه العليا للامن الصناعي Supply and installtion of custom room including all earth work , excavation, soil replacement & backfilling work and all reuqired engineering testings as per the designs and HCIS standards | 0 | 1 | عدد | 27462 | 27462 |  | Stacking | Excavation | Backfilling | RFI / Config. | Acceptance
[8 empty] | 20% | 30% | 50% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1
| INVOICE #27 | [5 empty] | 4119.3 | 3570.06 | 5355.09 | 8925.15 | 2471.58 | 274.62
| TRACKER #31 | [11 empty] | 1
| INVOICE #31 | [11 empty] | 2746.2
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 4119.3 | 3570.06 | 5355.09 | 8925.15 | 2471.58 | 274.62 | 2746.2
| Tot.Procument | [5 empty] | 4119.3
| Tot.implementation | [5 empty] | 17850.3
| Tot(T&C / Configuration+Handover) | [5 empty] | 5492.4
| ToT.Overall Completion INVOICE | [5 empty] | 27462
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | 65% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
CR1-034 | صب القواعد الارضيه شامله الاقدام و رقبة العامود و الكمره و لوح الدرج مع عمل جميع الفحوصات المطلوبه وفقا للتصاميم الهندسيه و مواصافت الهيئه العليا للامن الصناعي Substructure work including , footing , neck column, grade beam & slab on grade and all required engineering testings as per the designs and HCIS standards | 0 | 1 | عدد | 27462 | 27462 |  | Footing | Columns | Neck Columns | Beam | RFI / Config. | Acceptance
[8 empty] | 25% | 25% | 15% | 35% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
| INVOICE #27 | [5 empty] | 4119.3 | 4462.575 | 4462.575 | 2677.545 | 6247.605 | 2471.58 | 274.62
| TRACKER #31 | [12 empty] | 1
| INVOICE #31 | [12 empty] | 2746.2
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 4119.3 | 4462.575 | 4462.575 | 2677.545 | 6247.605 | 2471.58 | 274.62 | 2746.2
| Tot.Procument | [5 empty] | 4119.3
| Tot.implementation | [5 empty] | 17850.3
| Tot(T&C / Configuration+Handover) | [5 empty] | 5492.4
| ToT.Overall Completion INVOICE | [5 empty] | 27462
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | 65% |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  | T&C / Configuration |  | Handover
CR1-035 | بناء الهيكل الخارجي للمبنى شامل الاعمدة الخرسانيه المسلحه و كمرة السقف و لوح السقف و الدروة مع عمل جميع الفحوصات الهندسية المطلوبه على حسب التصاميم و مواصفات الهيئه العليا للامن الصناعي Superstructure work including , RC columns ,roof beams , roof slab & parapet and all required engineering testings as per the designs and HCIS standards | 0 | 1 | عدد | 41192 | 41192 |  | Super structure | Parpet | RFI / Config. | Acceptance
[8 empty] | 70% | 30% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 | 1 | 1 | 1 | 1
| INVOICE #27 | [5 empty] | 6178.8 | 18742.36 | 8032.44 | 3707.28 | 411.92
| TRACKER #31 | [10 empty] | 1
| INVOICE #31 | [10 empty] | 4119.2
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 6178.8 | 18742.36 | 8032.44 | 3707.28 | 411.92 | 4119.2
| Tot.Procument | [5 empty] | 6178.8
| Tot.implementation | [5 empty] | 26774.8
| Tot(T&C / Configuration+Handover) | [5 empty] | 8238.4
| ToT.Overall Completion INVOICE | [5 empty] | 41192
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | 65% |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  | T&C / Configuration |  | Handover
CR1-036 | عزل الاسطح على حسب المواصفات و المقاييس لدى الهيئه العليا للامن الصناعي Waterproofing work for roof slab as per HCIS standards | 0 | 1 | عدد | 13731 | 13731 |  | Prepration | Roof Insulation | RFI / Config. | Acceptance
[8 empty] | 20% | 80% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 | 1 | 1 | 1 | 1
| INVOICE #27 | [5 empty] | 2059.65 | 1785.03 | 7140.12 | 1235.79 | 137.31
| TRACKER #31 | [10 empty] | 1
| INVOICE #31 | [10 empty] | 1373.1
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 2059.65 | 1785.03 | 7140.12 | 1235.79 | 137.31 | 1373.1
| Tot.Procument | [5 empty] | 2059.65
| Tot.implementation | [5 empty] | 8925.15
| Tot(T&C / Configuration+Handover) | [5 empty] | 2746.2
| ToT.Overall Completion INVOICE | [5 empty] | 13731
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | 65% |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  | T&C / Configuration |  | Handover
CR1-037 | جميع اعمال البناء شاملة الجدران المقاومه للرصاص مسلح بالحديد بشكل عامودي و افقي و مملوء بمادة الجراوت على حسب المخططات و مواصفات الهيئه العليا للامن الصناعي All masonary work including solid/ rigged insualted /hollow / Ballistic protected CMU with RCC lintels over openings vertical and horizantal reinforcement, fixture & filler grout as per designs and HCIS standards | 0 | 1 | عدد | 27462 | 27462 |  | Prepration | Construction of Ballistic Wall | RFI / Config. | Acceptance
[8 empty] | 20% | 80% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 | 1 | 1 | 1 | 1
| INVOICE #27 | [5 empty] | 4119.3 | 3570.06 | 14280.24 | 2471.58 | 274.62
| TRACKER #31 | [10 empty] | 1
| INVOICE #31 | [10 empty] | 2746.2
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 4119.3 | 3570.06 | 14280.24 | 2471.58 | 274.62 | 2746.2
| Tot.Procument | [5 empty] | 4119.3
| Tot.implementation | [5 empty] | 17850.3
| Tot(T&C / Configuration+Handover) | [5 empty] | 5492.4
| ToT.Overall Completion INVOICE | [5 empty] | 27462
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% | [6 empty] | 65% | [6 empty] | 10% |  | 10%
[7 empty] | Procurement | [6 empty] | CONSTRUCTION | [6 empty] | T&C / Configuration |  | Handover
CR1-038 | جميع اعمال التشطيبات الداخليه شامله اللياسه و البلاط والدهانات الداخليه و الخارجيه على حسب المخططات و المواصفات All finishing works including (plaster , tiles , Accoustical tiles & paint internal and external )as per designs | 0 | 1 | عدد | 54923 | 54923 | Interior plastering | Exterior plastering | Ceiling | Interior paint | Exterior paint | Tiles | Building furniture | Interior plastering | Exterior plastering | Ceiling | Interior paint | Exterior paint | Tiles | Building furniture | RFI / Config. | Acceptance
[7 empty] | 10% | 15% | 15% | 10% | 15% | 15% | 20% | 10% | 15% | 15% | 10% | 15% | 15% | 20% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| INVOICE #27 | [5 empty] | 823.845 | 1235.7675 | 1235.7675 | 823.845 | 1235.7675 | 1235.7675 | 1647.69 | 3569.995 | 5354.9925 | 5354.9925 | 3569.995 | 5354.9925 | 5354.9925 | 7139.99 | 4943.07 | 549.23
| TRACKER #31 | [21 empty] | 1
| INVOICE #31 | [21 empty] | 5492.3
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 823.845 | 1235.7675 | 1235.7675 | 823.845 | 1235.7675 | 1235.7675 | 1647.69 | 3569.995 | 5354.9925 | 5354.9925 | 3569.995 | 5354.9925 | 5354.9925 | 7139.99 | 4943.07 | 549.23 | 5492.3
| Tot.Procument | [5 empty] | 8238.45
| Tot.implementation | [5 empty] | 35699.95
| Tot(T&C / Configuration+Handover) | [5 empty] | 10984.6
| ToT.Overall Completion INVOICE | [5 empty] | 54923
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 25% |  | 55% |  | 10% |  | 10%
[7 empty] | Procurement |  | CONSTRUCTION |  | T&C / Configuration |  | Handover
CR1-039 | اعمال التشطيبات الخارجيه شاملة الممرات والمداخل ومحيط المبنى على حسب التصاميم و المواصفات Hardscape work including walkway arround the building as per designs | 0 | 1 | عدد | 32954 | 32954 | Kerbstone and interlock | Handrail | Kerbstone and interlock | Handrail | RFI / Config. | Acceptance
[7 empty] | 70% | 30% | 50% | 50% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1
| INVOICE #27 | [5 empty] | 5766.95 | 2471.55 | 9062.35 | 9062.35 | 2965.86 | 329.54
| TRACKER #31 | [11 empty] | 1
| INVOICE #31 | [11 empty] | 3295.4
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 5766.95 | 2471.55 | 9062.35 | 9062.35 | 2965.86 | 329.54 | 3295.4
| Tot.Procument | [5 empty] | 8238.5
| Tot.implementation | [5 empty] | 18124.7
| Tot(T&C / Configuration+Handover) | [5 empty] | 6590.8
| ToT.Overall Completion INVOICE | [5 empty] | 32954
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% |  | 25% |  | 10% |  | 10%
[7 empty] | Procurement |  | CONSTRUCTION |  | T&C / Configuration |  | Handover
CR1-040 | توريد و تركيب الابواب و الشبابيك المضادة للرصاص على حسب التصاميم و مواصفات الهيئه العليا للامن الصناعي Supply and installation of Ballistic windows and doors as per designs and HCIS standars | 0 | 1 | عدد | 30208 | 30208 | Doors | Windows | Doors | Windows | RFI / Config. | Acceptance
[7 empty] | 60% | 40% | 60% | 40% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 | 1 | 1 | 1
| INVOICE #27 | [5 empty] | 9968.64 | 6645.76 | 4531.2 | 3020.8
| TRACKER #28 | [9 empty] | 1 | 1
| INVOICE #28 | [9 empty] | 2718.72 | 302.08
| TRACKER #31 | [11 empty] | 1
| INVOICE #31 | [11 empty] | 3020.8
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 9968.64 | 6645.76 | 4531.2 | 3020.8 | 2718.72 | 302.08 | 3020.8
| Tot.Procument | [5 empty] | 16614.4
| Tot.implementation | [5 empty] | 7552
| Tot(T&C / Configuration+Handover) | [5 empty] | 6041.6
| ToT.Overall Completion INVOICE | [5 empty] | 30208
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% |  |  | 65% |  |  | 10% |  | 10%
[7 empty] | Procurement |  |  | CONSTRUCTION |  |  | T&C / Configuration |  | Handover
CR1-041 | توريد و تركيب جميع الاعمال الميكانيه شامله اعمال السباكه والتصريف و تركيب المكيفات على حسب المخططات و التصاميم All mechanical work including roof drain and installation of AC spilt unit as per drawings and designs | 0 | 1 | عدد | 10985 | 10985 | Security | Fire alarm | Hvac | Security | Fire alarm | Hvac | RFI / Config. | Acceptance
[7 empty] | 30% | 30% | 40% | 30% | 30% | 40% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1
| INVOICE #27 | [5 empty] | 494.325 | 494.325 | 659.1 | 2142.075 | 2142.075 | 2856.1
| TRACKER #28 | [11 empty] | 1 | 1
| INVOICE #28 | [11 empty] | 988.65 | 109.85
| TRACKER #31 | [13 empty] | 1
| INVOICE #31 | [13 empty] | 1098.5
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 494.325 | 494.325 | 659.1 | 2142.075 | 2142.075 | 2856.1 | 988.65 | 109.85 | 1098.5
| Tot.Procument | [5 empty] | 1647.75
| Tot.implementation | [5 empty] | 7140.25
| Tot(T&C / Configuration+Handover) | [5 empty] | 2197
| ToT.Overall Completion INVOICE | [5 empty] | 10985
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 15% |  | 65% |  | 10% |  | 10%
[7 empty] | Procurement |  | CONSTRUCTION |  | T&C / Configuration |  | Handover
CR1-042 | توريد وتركيب جميع اعمال الكهرباء مع الربط الى النقطة الاخيره على حسب الرسومات والتصاميم All elecrical works including ( 1st fix , 2nd fix & 3rd fix )as per drawings and designs | 0 | 1 | عدد | 8238 | 8238 | Electrical foundation | Electrical finishing | Electrical foundation | Electrical finishing | RFI / Config. | Acceptance
[7 empty] | 50% | 50% | 50% | 50% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 | 1 | 1 | 1
| INVOICE #27 | [5 empty] | 617.85 | 617.85 | 2677.35 | 2677.35
| TRACKER #30 | [9 empty] | 1 | 1
| INVOICE #30 | [9 empty] | 741.42 | 82.38
| TRACKER #31 | [11 empty] | 1
| INVOICE #31 | [11 empty] | 823.8
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 617.85 | 617.85 | 2677.35 | 2677.35 | 741.42 | 82.38 | 823.8
| Tot.Procument | [5 empty] | 1235.7
| Tot.implementation | [5 empty] | 5354.7
| Tot(T&C / Configuration+Handover) | [5 empty] | 1647.6
| ToT.Overall Completion INVOICE | [5 empty] | 8238
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
NBQ-043 | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | 0 | 1 | عدد | 2900 | 2900 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 | 1 |  | 1 | 1
| INVOICE #27 | [5 empty] | 1595 | 362.5 |  | 72.5 | 72.5
| TRACKER #28 | [7 empty] | 1 |  |  | 1
| INVOICE #28 | [7 empty] | 145 |  |  | 72.5
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1595 | 362.5 | 145 | 72.5 | 72.5 | 72.5 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1595
| Tot.implementation | [5 empty] | 725
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 2320
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
NBQ-044 | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | 0 | 1 | عدد | 3160 | 3160 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 | 1 |  | 1
| INVOICE #27 | [5 empty] | 1738 | 395 |  | 158
| TRACKER #31 | [7 empty] | 1
| INVOICE #31 | [7 empty] | 158
| TRACKER #32 | [9 empty] | 1
| INVOICE #32 | [9 empty] | 79
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1738 | 395 | 158 | 158 | 79 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1738
| Tot.implementation | [5 empty] | 790
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 2528
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
NBQ-045 | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | 0 | 1 | عدد | 190 | 190 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 | 1 |  | 1
| INVOICE #27 | [5 empty] | 104.5 | 23.75 |  | 9.5
| TRACKER #31 | [7 empty] | 1
| INVOICE #31 | [7 empty] | 9.5
| TRACKER #32 | [9 empty] | 1
| INVOICE #32 | [9 empty] | 4.75
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 104.5 | 23.75 | 9.5 | 9.5 | 4.75 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 104.5
| Tot.implementation | [5 empty] | 47.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 152
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
NBQ-046 | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Electric Lock | 5 | 1 | عدد | 1200 | 1200 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 1 | 1 |  | 1
| INVOICE #27 | [5 empty] | 660 | 150 |  | 60
| TRACKER #31 | [7 empty] | 1
| INVOICE #31 | [7 empty] | 60
| TRACKER #32 | [9 empty] | 1
| INVOICE #32 | [9 empty] | 30
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 660 | 150 | 60 | 60 | 30 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 660
| Tot.implementation | [5 empty] | 300
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 960
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
NBQ-047 | ﺯﺭ ﺍﻟﺿﻐﻁ ﻟﻠﺧﺭﻭﺝ ( EPB ) Exit Push Button | 0 | 1 | عدد | 160 | 160 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #28 | [5 empty] | 1
| INVOICE #28 | [5 empty] | 88
| TRACKER #31 | [6 empty] | 1 | 1 | 1 | 1
| INVOICE #31 | [6 empty] | 20 | 8 | 8 | 4
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 88 | 20 | 8 | 8 | 4 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 88
| Tot.implementation | [5 empty] | 40
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 128
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
NBQ-048 | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ ( CEFX ) External Fixed Camera | 0 | 1 | عدد | 3200 | 3200 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #28 | [5 empty] | 1
| INVOICE #28 | [5 empty] | 1760
| TRACKER #31 | [6 empty] | 1 | 1 | 1 | 1 | 1
| INVOICE #31 | [6 empty] | 400 | 160 | 80 | 80 | 80
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1760 | 400 | 160 | 80 | 80 | 80 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1760
| Tot.implementation | [5 empty] | 800
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 2560
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% | [6 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [6 empty] | T&C / Configuration |  | Handover
NBQ-049 | عمود كاميرا CCTV Pole | 0 | 1 | عدد | 1650 | 1650 |  | Precasting Foundations | Excavation | Lean Conc. | Foundation Installation | Pole Installation | BF & Compaction | Pole Alignment | RFI / Config. | Acceptance
[8 empty] | 20% | 20% | 10% | 10% | 25% | 10% | 5% | 90% | 10%
| TRACKER #27 | [5 empty] | 1
| INVOICE #27 | [5 empty] | 907.5
| TRACKER #31 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| INVOICE #31 | [6 empty] | 82.5 | 82.5 | 41.25 | 41.25 | 103.125 | 41.25 | 20.625 | 148.5 | 16.5
| TRACKER #32 | [15 empty] | 1
| INVOICE #32 | [15 empty] | 165
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Overall Completion INVOICE | [5 empty] | 907.5 | 82.5 | 82.5 | 41.25 | 41.25 | 103.125 | 41.25 | 20.625 | 148.5 | 16.5 | 165
| Tot.Procument | [5 empty] | 907.5
| Tot.implementation | [5 empty] | 412.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 330
| ToT.Overall Completion INVOICE | [5 empty] | 1650
| Overall Completion percentage | [5 empty] | 100%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-227 | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ ﻣﻊ ﺗﺣﻠﻳﻼﺕ ﺍﻟﻔﻳﺩﻳﻭ (CEFXVA) External Fixed Camera with Video Analytics | 1 | 2 | عدد | 3500 | 7000 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 2
| INVOICE #27 | [5 empty] | 3850
| Overall Completion TRACKER | [5 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 3850
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 3850
| Overall Completion percentage | [5 empty] | 55%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% | [6 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [6 empty] | T&C / Configuration |  | Handover
BQ-228 | عمود كاميرا CCTV Pole | 1 | 2 | عدد | 1650 | 3300 |  | Precasting Foundations | Excavation | Lean Conc. | Foundation Installation | Pole Installation | BF & Compaction | Pole Alignment | RFI / Config. | Acceptance
[8 empty] | 20% | 20% | 10% | 10% | 25% | 10% | 5% | 90% | 10%
| TRACKER #23 | [5 empty] | 1
| INVOICE #23 | [5 empty] | 907.5
| TRACKER #27 | [5 empty] | 1
| INVOICE #27 | [5 empty] | 907.5
| Overall Completion TRACKER | [5 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 1815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 1815
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1815
| Overall Completion percentage | [5 empty] | 55%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [5 empty] | T&C / Configuration |  | Handover
BQ-229 | ﺑﻭﺍﺑﺔ ﻣﻔﺻﻠﻳﺔ ﻳﺩﻭﻳﺔManually Operated Swing Gate | 1 | 1 | عدد | 49850 | 49850 |  | Excavation | Casting Foundations | Gate Installation | Backfilling | Cabling & Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 25% | 15% | 20% | 20% | 10% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 1
| INVOICE #27 | [5 empty] | 27417.5
| TRACKER #32 | [6 empty] | 1 | 1 |  | 1
| INVOICE #32 | [6 empty] | 3115.625 | 1869.375 |  | 2492.5
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 27417.5 | 3115.625 | 1869.375 | 0 | 2492.5 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 27417.5
| Tot.implementation | [5 empty] | 7477.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 34895
| Overall Completion percentage | [5 empty] | 70%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  | T&C / Configuration |  | Handover
BQ-230 | ﻣﻁﺑﺎﺕ ﺍﻟﺗﺣﻛﻡ ﻓﻲ ﺍﻟﺳﺭﻋﺔ Speed Humps | 2 | 2 | عدد | 2300 | 4600 |  | Site Preparation | Anchoring on Ashphalt | Placing of Speed Humps | RFI / Config. | Acceptance
[8 empty] | 10% | 80% | 10% | 90% | 10%
| TRACKER #22 | [5 empty] | 2
| INVOICE #22 | [5 empty] | 2530
| Overall Completion TRACKER | [5 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 2530 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 2530
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 2530
| Overall Completion percentage | [5 empty] | 55%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [5 empty] | T&C / Configuration |  | Handover
BQ-231 | ﺫﺭﺍﻉ ﻫﻳﺩﺭﻭﻟﻳﻛﻲ ﻣﺿﺎﺽ ﻟﻠﻣﺭﻛﺑﺎﺕ (ﺗﺻﻧﻳﻑ ASTM M50-P1) Crash Rated Arm Barrier (ASTM M50-P1 Rated) | 1 | 1 | عدد | 207915 | 207915 |  | Excavation | Casting Foundations | Arm Barrier Installation | Backfilling | Cabling & Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 25% | 15% | 20% | 20% | 10% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 1
| INVOICE #27 | [5 empty] | 114353.25
| TRACKER #32 | [6 empty] | 1 | 1 |  | 1
| INVOICE #32 | [6 empty] | 12994.6875 | 7796.8125 |  | 10395.75
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 114353.25 | 12994.6875 | 7796.8125 | 0 | 10395.75 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 114353.25
| Tot.implementation | [5 empty] | 31187.25
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 145540.5
| Overall Completion percentage | [5 empty] | 70%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [5 empty] | T&C / Configuration |  | Handover
CR1-050 | Supply & Install a Thermal Camera توريد وتركيب كاميرا حرارية | 0 | 1 | عدد | 39500 | 39500 |  | Excavation | Precast foundt'n & Pole Installation | Backfilling & Alignment | Camera Mounting | Cabling & Termination | Config | RFI / Config. | Acceptance
[8 empty] | 10% | 20% | 10% | 40% | 10% | 10% | 90% | 10%
| TRACKER #027 | [5 empty] | 1
| INVOICE #027 | [5 empty] | 21725
| Overall Completion TRACKER | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 21725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 21725
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 21725
| Overall Completion percentage | [5 empty] | 55%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-232 | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺩﺍﺧﻠﻳﺔ ﻋﻠﻰ ﺷﻛﻝ ﻗﺑﺔ ( CIDX ) Camera Internal Fixed Dome | 1 | 4 | عدد | 2600 | 10400 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 1
| INVOICE #13 | [5 empty] | 1430
| TRACKER #25 | [6 empty] | 1 |  | 1
| INVOICE #25 | [6 empty] | 325 |  | 65
| TRACKER #027 | [5 empty] | 3 | 3 |  | 3 | 4
| INVOICE #027 | [5 empty] | 4290 | 975 |  | 195 | 260
| TRACKER #028 | [7 empty] | 4 |  |  | 4
| INVOICE #028 | [7 empty] | 520 |  |  | 260
| Overall Completion TRACKER | [5 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 5720 | 1300 | 520 | 260 | 260 | 260 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 5720
| Tot.implementation | [5 empty] | 2600
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 8320
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-233 | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | 9 | 9 | عدد | 2900 | 26100 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
| TRACKER #12 | [5 empty] | 9
| INVOICE #12 | [5 empty] | 14355
| TRACKER #25 | [6 empty] | 9 |  | 9
| INVOICE #25 | [6 empty] | 3262.5 |  | 652.5
| TRACKER #028 | [7 empty] | 9 |  | 9 | 9
| INVOICE #028 | [7 empty] | 1305 |  | 652.5 | 652.5
| Overall Completion TRACKER | [5 empty] | 9 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 14355 | 3262.5 | 1305 | 652.5 | 652.5 | 652.5 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 14355
| Tot.implementation | [5 empty] | 6525
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 20880
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-234 | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | 10 | 6 | عدد | 3160 | 18960 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #13 | [5 empty] | 10
| INVOICE #13 | [5 empty] | 17380
| TRACKER #25 | [6 empty] | 10 |  | 10
| INVOICE #25 | [6 empty] | 3950 |  | 1580
| TRACKER #028 | [5 empty] | -4 | -4 |  | -4
| INVOICE #028 | [5 empty] | -6952 | -1580 |  | -632
| TRACKER #033 | [7 empty] | 6 |  | 6
| INVOICE #033 | [7 empty] | 948 |  | 474
| Overall Completion TRACKER | [5 empty] | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 10428 | 2370 | 948 | 948 | 474 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 10428
| Tot.implementation | [5 empty] | 4740
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 15168
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-235 | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Electric Lock | 5 | 4 | عدد | 1200 | 4800 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 5
| INVOICE #14 | [5 empty] | 3300
| TRACKER #25 | [6 empty] | 5 |  | 5
| INVOICE #25 | [6 empty] | 750 |  | 300
| TRACKER #028 | [5 empty] | -1 | -1 |  | -1
| INVOICE #028 | [5 empty] | -660 | -150 |  | -60
| TRACKER #033 | [7 empty] | 4 |  | 4
| INVOICE #033 | [7 empty] | 240 |  | 120
| Overall Completion TRACKER | [5 empty] | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 2640 | 600 | 240 | 240 | 120 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 2640
| Tot.implementation | [5 empty] | 1200
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 3840
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-236 | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) Emergency Break Glass Unit | 5 | 4 | عدد | 240 | 960 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 5
| INVOICE #14 | [5 empty] | 660
| TRACKER #25 | [6 empty] | 4 |  | 4
| INVOICE #25 | [6 empty] | 120 |  | 48
| TRACKER #028 | [5 empty] | -1
| INVOICE #028 | [5 empty] | -132
| TRACKER #033 | [7 empty] | 4 |  | 4
| INVOICE #033 | [7 empty] | 48 |  | 24
| Overall Completion TRACKER | [5 empty] | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 528 | 120 | 48 | 48 | 24 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 528
| Tot.implementation | [5 empty] | 240
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 768
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-237 | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | 12 | 7 | عدد | 190 | 1330 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 12
| INVOICE #14 | [5 empty] | 1254
| TRACKER #25 | [6 empty] | 11 |  | 11
| INVOICE #25 | [6 empty] | 261.25 |  | 104.5
| TRACKER #028 | [5 empty] | -5 | -5 |  | -5
| INVOICE #028 | [5 empty] | -522.5 | -69.27 |  | -27.71
TRACKER #029
| INVOICE #029 | [6 empty] | -69.27
| TRACKER #033 | [6 empty] | 1 | 7 | 1 | 7
| INVOICE #033 | [6 empty] | 23.75 | 66.5 | 9.5 | 33.25
| Overall Completion TRACKER | [5 empty] | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 731.5 | 146.46 | 66.5 | 86.29 | 33.25 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 731.5
| Tot.implementation | [5 empty] | 332.5
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 1064
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-238 | ﺯﺭ ﺍﻟﺿﻐﻁ ﻟﻠﺧﺭﻭﺝ ( EPB ) Exit Push Button | 1 | 2 | عدد | 160 | 320 |  | Component Installation | Configuration of System | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 20% | 10% | 90% | 10%
| TRACKER #14 | [5 empty] | 1
| INVOICE #14 | [5 empty] | 88
| TRACKER #25 | [6 empty] | 1 |  | 1
| INVOICE #25 | [6 empty] | 20 |  | 8
| TRACKER #27 | [5 empty] | 1 | 1 |  | 1
| INVOICE #27 | [5 empty] | 88 | 20 |  | 8
| TRACKER #033 | [7 empty] | 2 |  | 2
| INVOICE #033 | [7 empty] | 16 |  | 8
| Overall Completion TRACKER | [5 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 176 | 40 | 16 | 16 | 8 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 176
| Tot.implementation | [5 empty] | 80
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 256
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
BQ-239 | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required | 1 | 1 | عدد | 29700 | 29700 |  | Cabinet / Rack | UPS Installation | Batteries Installation | Cabling & Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 30% | 30% | 20% | 10% | 10% | 90% | 10%
| TRACKER #27 | [5 empty] | 1
| INVOICE #27 | [5 empty] | 20790
| TRACKER #31 | [6 empty] | 1 | 1 | 1 | 1 | 1
| INVOICE #31 | [6 empty] | 891 | 891 | 594 | 297 | 297
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 20790 | 891 | 891 | 594 | 297 | 297 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 20790
| Tot.implementation | [5 empty] | 2970
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 23760
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
BQ-240 | ﺯﺭ ﺇﻧﺫﺍﺭ ﺍﻟﻁﻭﺍﺭﺉ ( EAB ) Emergency Alarm Button | 1 | 1 | عدد | 220 | 220 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| TRACKER #25 | [6 empty] | 1 |  | 1
| INVOICE #25 | [6 empty] | 13.2 |  | 2.2
| TRACKER #26 | [5 empty] | 1
| INVOICE #26 | [5 empty] | 154
| TRACKER #033 | [7 empty] | 1 |  | 1
| INVOICE #033 | [7 empty] | 4.4 |  | 2.2
| Overall Completion TRACKER | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 154 | 13.2 | 4.4 | 2.2 | 2.2 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 154
| Tot.implementation | [5 empty] | 22
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 176
| Overall Completion percentage | [5 empty] | 80%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 70% | 10% |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  | T&C / Configuration |  | Handover
BQ-242 | ﺑﺎﺏ ﺣﺩﻳﺩﻱ ﻣﻔﺻﻠﻲ ﺫﻭ ﺩﺭﻓﺗﻳﻥ ﻣﺗﻭﺍﻓﻖ ﻣﻊ DLSD ) SEC-09 ) | 2 | 2 | عدد | 11355 | 22710 |  | Door sub frames | Door & frames | RFI / Config. | Acceptance
[8 empty] | 40% | 60% | 90% | 10%
TRACKER #00
INVOICE #00
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
NBQ-051 | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | 0 | 2 | عدد | 2900 | 5800 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
TRACKER #12
INVOICE #12
TRACKER #25
INVOICE #25
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [5 empty] | T&C / Configuration |  | Handover
NBQ-052 | Supply & Install a Thermal Camera توريد وتركيب كاميرا حرارية | 0 | 1 | عدد | 39500 | 39500 |  | Excavation | Precast foundt'n & Pole Installation | Backfilling & Alignment | Camera Mounting | Cabling & Termination | Config | RFI / Config. | Acceptance
[8 empty] | 10% | 20% | 10% | 40% | 10% | 10% | 90% | 10%
TRACKER #00
INVOICE #00
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  |  | T&C / Configuration |  | Handover
NBQ-053 | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ ﻣﻊ ﺗﺣﻠﻳﻼﺕ ﺍﻟﻔﻳﺩﻳﻭ (CEFXVA) External Fixed Camera with Video Analytics | 0 | 1 | عدد | 3500 | 3500 |  | Camera Mounting | Configuration | Cabling | Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 50% | 20% | 10% | 10% | 10% | 90% | 10%
TRACKER #00
INVOICE #00
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% | [6 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [6 empty] | T&C / Configuration |  | Handover
NBQ-054 | عمود كاميرا CCTV Pole | 0 | 4 | عدد | 1650 | 6600 |  | Precasting Foundations | Excavation | Lean Conc. | Foundation Installation | Pole Installation | BF & Compaction | Pole Alignment | RFI / Config. | Acceptance
[8 empty] | 20% | 20% | 10% | 10% | 25% | 10% | 5% | 90% | 10%
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
NBQ-055 | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | 0 | 2 | عدد | 3160 | 6320 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
NBQ-056 | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | 0 | 1 | عدد | 190 | 190 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% |  |  |  | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION |  |  |  | T&C / Configuration |  | Handover
NBQ-057 | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Electric Lock | 0 | 1 | عدد | 1200 | 1200 |  | Component Installation | Configuration | Patching & Cabling | Testing | RFI / Config. | Acceptance
[8 empty] | 60% | 20% | 10% | 10% | 90% | 10%
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%
ITEM | Description | OLD QUANTITY | C.R QUANTITY | UNITE | PRICE | TOTAL | 55% | 25% | [5 empty] | 10% |  | 10%
[7 empty] | Procurement | CONSTRUCTION | [5 empty] | T&C / Configuration |  | Handover
NBQ-058 | (single leaf) ﺑﻭﺍﺑﺔ ﻣﻔﺻﻠﻳﺔ ﻳﺩﻭﻳﺔManually Operated Swing Gate | 0 | 1 | عدد | 19850 | 19850 |  | Excavation | Casting Foundations | Gate Installation | Backfilling | Cabling & Termination | Testing | RFI / Config. | Acceptance
[8 empty] | 25% | 15% | 20% | 20% | 10% | 10% | 90% | 10%
| Overall Completion TRACKER | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overall Completion INVOICE | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tot.Procument | [5 empty] | 0
| Tot.implementation | [5 empty] | 0
| Tot(T&C / Configuration+Handover) | [5 empty] | 0
| ToT.Overall Completion INVOICE | [5 empty] | 0
| Overall Completion percentage | [5 empty] | 0%

## Summry Invoices
رقم المستخلص | الفترة |  | السنة | قيمة الأعمال المنجزة | نسبة المستخلص من العقد | النسبة التراكمية | الأعمال التراكمية | استقطاع الدفعة المقدمة | احتجاز الختامي | صافي المستخلص بعد الاستقطاعات | حسومات أخرى | بيان الحسومات | غرامات التأخير | غرامات الإشراف | إجمالي الحسومات والغرامات | صافي المستحق | المنصرف التراكمي
Tot' | From | To |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 210000 |  | #VALUE! | 698425.3333 | #REF! | #REF! | #REF!
1 | 2023-04-09 | 2023-08-31 | 2023 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 119000 | (عدم تواجد مدير المشروع 119 يوم عمل) | 0 | 0 | #REF! | #REF! | #REF!
2 | 2023-09-01 | 2023-10-10 | 2023 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
3 | 2023-10-11 | 2023-10-29 | 2023 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
4 | 2026-10-29 | 2023-11-08 | 2023 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
5 | 2023-11-09 | 2024-01-28 | 2024 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 27000 | (عدم تواجد المهندس المدني 45 يوم ) | 0 | 0 | #REF! | #REF! | #REF!
6 | 2024-01-28 | 2024-02-25 | 2024 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
7 | 2024-04-29 | 2024-03-28 | 2024 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
8 | 2024-03-08 | 2024-04-29 | 2024 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
9 | April 30, 2024 | May 22, 2024 | 2024 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
10 | June 11, 2024 | July 29, 2024 | 2024 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
11 | May 23, 2024 | June 10, 2024 | 2024 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
12 | July 30, 2024 | August 28, 2024 | 2024 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
13 | August 29, 2024 | September 29, 2024 | 2024 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
14 | September 30, 2024 | October 28, 2024 | 2024 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
15 | October 29, 2024 | November 19, 2024 | 2024 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
16 | November 20, 2024 | December 31, 2024 | 2024 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
17 | January 1, 2025 | February 25, 2025 | 2025 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
18 | February 26, 2025 | March 23, 2025 | 2025 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
19 | March 24, 2025 | April 28, 2025 | 2025 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
20 | April 29, 2025 | May 25, 2025 | 2025 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
21 | May 26, 2025 | June 26, 2025 | 2025 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
22 | June 27, 2025 | July 30, 2025 | 2025 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
23 | July 31, 2025 | August 28, 2025 | 2025 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
24 | August 29, 2025 | September 29, 2025 | 2025 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 11000 | (عدم تواجد مدير المشروع 11 يوم عمل) | 0 | 0 | #REF! | #REF! | #REF!
25 | September 30, 2025 | October 28, 2025 | 2025 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF! | #REF! | #REF!
26 | October 29, 2025 | November 26, 2025 | 2025 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4000 | (عدم تواجد فني أنظمة وتركيبات 10 يوم عمل) | 0 | 0 | #REF! | #REF! | #REF!
27 | November 27, 2025 | April 20, 2026 | 2026 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 22000 | (عدم تواجد فني أنظمة وتركيبات 35 يوم عمل+عدم تواجد مدير المشروع 8 يوم عمل) | 0 | 0 | #REF! | #REF! | #REF!
28 | April 21, 2026 | May 19, 2026 | 2026 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #VALUE! | 131299.7849 | #REF! | #REF! | #REF!
29 | May 20, 2026 | June 30, 2026 | 2026 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #VALUE! | 192473.5484 | #REF! | #REF! | #REF!
30 | July 1, 2026 | July 27, 2026 | 2026 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2000 | (عدم تواجد مدير المشروع 2 يوم عمل) | #VALUE! | 120855.4839 | #REF! | #REF! | #REF!
31 | July 28, 2026 | August 26, 2026 | 2026 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 25000 | (عدم تواجد مدير المشروع 25 يوم عمل) | #VALUE! | 134283.871 | #REF! | #REF! | #REF!
32 | 2026-08-27 | September 21, 2026 | 2026 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #VALUE! | 119512.6452 | #REF! | #REF! | #REF!
33 | 2026-09-22 | 2026-10-25 | 2026
34 |  |  | 2026
35
36
قيمة العقد المعتمدة | #VALUE! |  | البند |  | القيمة (ريال) | % من العقد |  |  | السنة | عدد المستخلصات | قيمة الأعمال | % من العقد
مدة المشروع (يوم عمل) | 839 |  | إجمالي الأعمال المنجزة (المفوتر) |  | #REF! | #REF! |  |  | 2023 | 4 | #REF! | #REF!
الدفعة المقدمة المنصرفة | 6860536 |  | استقطاع الدفعة المقدمة المتراكم |  | #REF! | #REF! |  |  | 2024 | 12 | #REF! | #REF!
نسبة استقطاع الدفعة المقدمة | 10% |  | رصيد الدفعة المقدمة المتبقي للاستقطاع |  | #REF! | #REF! |  |  | 2025 | 10 | #REF! | #REF!
نسبة احتجاز المستخلص الختامي | 10% |  | المحتجز للمستخلص الختامي |  | #REF! | #REF! |  |  | 2026 | 8 | #REF! | #REF!
التكلفة الشهرية لطاقم الإشراف | 138760 |  | حسومات أخرى (عدم تواجد فريق العمل) |  | 210000 | #VALUE! |  |  | 2027 | 0 | 0 | 0%
التكلفة اليومية للمشروع | #VALUE! |  | غرامات التأخير |  | #VALUE! | #VALUE! |  |  | 2028 | 0 | 0 | 0%
|  |  | غرامات الإشراف |  | 698425.3333 | #VALUE! |  |  | الإجمالي | 34 | #REF! | #REF!
|  |  | إجمالي الحسومات والغرامات |  | #REF! | #REF!
|  |  | صافي المستحق عن المستخلصات |  | #REF! | #REF!
|  |  | إجمالي المنصرف الفعلي (شامل الدفعة المقدمة) |  | #REF! | #REF!
|  |  | الصافي + الاستقطاعات + المحتجز + الحسومات والغرامات |  | #REF!
[13 empty] | 4/30/2024 | 5/22/2024
[13 empty] | 6/11/2024 | 7/29/2024
[14 empty] | 5/23/2024 | 6/10/2024
[13 empty] | 7/30/2024 | 8/28/2024
[13 empty] | 8/29/2024 | 9/29/2024
[13 empty] | 9/30/2024 | 10/28/2024
[13 empty] | 10/29/2024 | 11/19/2024
[13 empty] | 11/20/2024 | 12/31/2024
[13 empty] | 1/1/2025 | 2/25/2025
[13 empty] | 2/26/2025 | 3/23/2025
[13 empty] | 3/24/2025 | 4/28/2025
[14 empty] | 4/29/2025 | 5/25/2025
[14 empty] | 5/26/2025 | 6/26/2025
[14 empty] | 7/30/2025 | 6/27/2025
[14 empty] | 8/28/2025 | 7/31/2025
[14 empty] | 9/29/2025 | 8/29/2025
[14 empty] | 10/28/2025 | 9/30/2025
[14 empty] | 11/26/2025 | 10/29/2025
[14 empty] | 11/27/2025 | 4/20/2026
[14 empty] | 5/19/2026 | 4/21/2026
[14 empty] | 6/30/2026 | 5/20/2026
[14 empty] | 7/27/2026 | 7/1/2026
[14 empty] | 7/28/2026 | 8/26/2026
[14 empty] | 8/28/2026 | 9/21/2026

## Progress Report
29 | الإجمالي | [6 empty] | #VALUE! | #VALUE! | #VALUE! | 6052369.9904 | #VALUE! |  |  | #VALUE! | #VALUE!
م | رقم البند | وصف البند | الوحدة | سعر الوحدة (SAR) | الكمية الأصلية (B.Q) | الكمية المعتمدة (C.R) | فرق الكمية | القيمة الأصلية (SAR) | القيمة المعتمدة (SAR) | فرق القيمة (أمر التغيير) | إجمالي المفوتر (SAR) | نسبة الإنجاز الفعلية % | الكمية المنجزة | الكمية المتبقية | القيمة المتبقية (SAR) | نسبة المتبقي % | المتبقي | الحالة | حالة أمر التغيير | المجموعة | مفتاح ترتيب المتبقي | مفتاح ترتيب الفرق | صف البند في SUMMARY | فرق عن TOTAL
1 | D-001 | التصاميم التفصيلية وتصاميم المرحلة الثالثة Stage 3 Design Package | عدد | 2840000 | 1 | 1 | 0 | 2840000 | 2840000 | 0 | 2840000 | 100% | 1 | 0 | 0 | 0% | 0 عدد ¦ 0 ريال ¦ 0.0% | مكتمل | بدون تغيير | D | 5e-06 | 5e-06 | 4 | 0
2 | D-002 | الهندسة والتصميم IFC, Shop drawings and Stage 4 drawings | عدد | 2630000 | 1 | 1 | 0 | 2630000 | 2630000 | 0 | 1577999.9904 | 60% | 0.6 | 0.4 | 1052000.0096 | 40% | 0.40 عدد ¦ 1,052,000 ريال ¦ 40.0% | جاري | بدون تغيير | D | 1052000.0096 | 6e-06 | 17 | 0
3 | D-003 | تدريب المشغلين وموظفي الصيانة Training of Operators and Maintenance Personnel | عدد | 110000 | 1 | 1 | 0 | 110000 | 110000 | 0 | 0 | 0% | 0 | 1 | 110000 | 100% | 1 عدد ¦ 110,000 ريال ¦ 100.0% | لم يبدأ | بدون تغيير | D | 110000 | 7e-06 | 48 | 0
4 | BQ-001 | محمول شبكة مركزي مع جميع الكابلات ذات الصلة والملحقات والأجهزة التمهيدية وأجهزة الشبكة Central Redundant Network Core Switch with all related cabling, accessories, prepherals and network devices | عدد | 130000 | 4 | 4 | 0 | 520000 | 520000 | 0 | 416000 | 80% | 3.2 | 0.8 | 104000 | 20% | 0.80 عدد ¦ 104,000 ريال ¦ 20.0% | جاري | بدون تغيير | BQ | 104000 | 8e-06 | 59 | 0
5 | BQ-002 | محول شبكة جيجابايت مع جميع الكابلات ذات الصلة والملحقات والأجهزة التمهيدية وأجهزة الشبكة Gigabit Network Switch with all related cabling, accessories, prepherals and network devices | عدد | 19600 | 10 | 10 | 0 | 196000 | 196000 | 0 | 78400 | 40% | 4 | 6 | 117600 | 60% | 6 عدد ¦ 117,600 ريال ¦ 60.0% | جاري | بدون تغيير | BQ | 117600 | 9e-06 | 79 | 0
6 | BQ-003 | كابينة المعدات الميدانية بما في ذلك جميع إمدادات الطاقة وكابلات الطاقة والبيانات إلى FEC وجميع المعدات الأمنية والمفاتيح الصناعية ولوحات التصحيح و CBs و TB وجميع الملحقات الكهربائية والاتصالات ذات الصلة وجميع الأعمال اللازمة لإكمال البند. Field Equipment cabinets including all power supplies, power and data cabling to the FEC and all security equipment, Industrial switches, patch panels, CBs, TBs, and all related electrical and communications accessories and all necessary work to complete the item. | عدد | 23700 | 66 | 61 | -5 | 1564200 | 1445700 | -118500 | 1139970 | 78.85% | 48.1 | 12.9 | 305730 | 21.15% | 12.90 عدد ¦ 305,730 ريال ¦ 21.1% | جاري | نقص | BQ | 305730 | -118500 | 103 | 0
7 | ITEM | Description | UNITE | #VALUE! | OLD QUANTITY | C.R QUANTITY | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | لم يبدأ | نقص | ITEM | #VALUE! | #VALUE! | 137 | #VALUE!
8 | 0 | Overall Completion percentage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 1.2e-05 | 1.2e-05 | 173 | 0
9 | 0 | INVOICE #13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 1.3e-05 | 1.3e-05 | 195 | 0
10 | 0 | INVOICE #13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 1.4e-05 | 1.4e-05 | 217 | 0
11 | 0 | INVOICE #12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 1.5e-05 | 1.5e-05 | 239 | 0
12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 1.6e-05 | 1.6e-05 | 257 | 0
13 | 0 | INVOICE #13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 1.7e-05 | 1.7e-05 | 279 | 0
14 | 0 | INVOICE #14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 1.8e-05 | 1.8e-05 | 301 | 0
15 | 0 | INVOICE #14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 1.9e-05 | 1.9e-05 | 323 | 0
16 | 0 | INVOICE #14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 2e-05 | 2e-05 | 345 | 0
17 | 0 | INVOICE #26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 2.1e-05 | 2.1e-05 | 367 | 0
18 | 0 | INVOICE #16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 2.2e-05 | 2.2e-05 | 389 | 0
19 | 0 | INVOICE #13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 2.3e-05 | 2.3e-05 | 411 | 0
20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 2.4e-05 | 2.4e-05 | 429 | 0
21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 2.5e-05 | 2.5e-05 | 445 | 0
22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 2.6e-05 | 2.6e-05 | 461 | 0
23 | 0 | ToT.Overall Completion INVOICE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 2.7e-05 | 2.7e-05 | 475 | 0
24 | 0 | TRACKER #19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 2.8e-05 | 2.8e-05 | 498 | 0
25 | 0 | INVOICE #18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 2.9e-05 | 2.9e-05 | 522 | 0
26 | 0 | INVOICE #18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 3e-05 | 3e-05 | 546 | 0
27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 3.1e-05 | 3.1e-05 | 562 | 0
28 | 0 | Ceiling | 0.1 | 4335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0.1 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 3.2e-05 | 3.2e-05 | 638 | #VALUE!
29 | 0 | INVOICE #25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 0 ¦ 0 ريال ¦ 0.0% | لم يبدأ | بدون تغيير | 0 | 3.3e-05 | 3.3e-05 | 660 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Late&Supervision payment fee
مراحل غرامة التأخير (حسب العقد)
المرحلة | نسبة الغرامة من التكلفة اليومية | الحد الأدنى (يوم) | % من مدة المشروع | الحد التراكمي (يوم)
المرحلة الأولى | 25% | 15 | 10% | 84
المرحلة الثانية | 50% | 30 | 15% | 126 |  | 2026-10-25 | 11:58
المرحلة الثالثة | 100% | — | — | ما بعد المرحلة الثانية
حساب غرامة التأخير
رقم المستخلص | الفترة |  | أيام التأخير في الفترة | التأخير التراكمي قبله | أيام بغرامة 25% | أيام بغرامة 50% | أيام بغرامة 100% | غرامة 25% | غرامة 50% | غرامة 100% | إجمالي غرامة التأخير
الإجمالي |  |  | 132 |  | 84 | 42 | 6 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
28 | April 21, 2026 | May 19, 2026 | 25 | 0 | 25 | 0 | 0 | #VALUE! | 0 | 0 | #VALUE!
29 | May 20, 2026 | June 30, 2026 | 36 | 25 | 36 | 0 | 0 | #VALUE! | 0 | 0 | #VALUE!
30 | July 1, 2026 | July 27, 2026 | 23 | 61 | 23 | 0 | 0 | #VALUE! | 0 | 0 | #VALUE!
31 | July 28, 2026 | August 26, 2026 | 26 | 84 | 0 | 26 | 0 | 0 | #VALUE! | 0 | #VALUE!
32 | 2026-08-27 | September 21, 2026 | 22 | 110 | 0 | 16 | 6 | 0 | #VALUE! | #VALUE! | #VALUE!
33 | 46287 | 46320
34 | 0 | 0
35 | 0 | 0
36 | 0 | 0
حساب غرامة الأشراف
رقم المستخلص | الفترة |  | أيام الشهر الأول | عدد أيام الشهر الأول | أيام الشهر الثاني | عدد أيام الشهر الثاني | تكلفة الأيام الأولى | تكلفة الأيام الثانية | إجمالي غرامة الإشراف
الإجمالي |  |  | 58 |  | 96 |  | 261107.5269 | 437317.8065 | 698425.3333 | 2026-04-30 | 2026-05-01
28 | April 21, 2026 | May 19, 2026 | 10 | 30 | 19 | 31 | 46253.3333 | 85046.4516 | 131299.7849 | 2026-05-31 | 2026-06-01
29 | May 20, 2026 | June 30, 2026 | 12 | 31 | 30 | 30 | 53713.5484 | 138760 | 192473.5484 | 2026-06-30 | 2026-07-01
30 | July 1, 2026 | July 27, 2026 | 27 | 31 |  |  | 120855.4839 |  | 120855.4839 | 2026-07-31 | 2026-08-01
31 | July 28, 2026 | August 26, 2026 | 4 | 31 | 26 | 31 | 17904.5161 | 116379.3548 | 134283.871 | 2026-08-31 | 2026-09-01
32 | 2026-08-27 | September 21, 2026 | 5 | 31 | 21 | 30 | 22380.6452 | 97132 | 119512.6452 | 2026-09-30 | 2026-10-01
33 | 46287 | 46320 | [7 empty] | 2026-10-31 | 2026-11-01
34 | 0 | 0 | [7 empty] | 2026-11-30 | 2026-12-01
35 | 0 | 0 | [7 empty] | 2026-12-31 | 2027-01-01
36 | 0 | 0 | [7 empty] | 2027-01-01 | 2027-02-01
Formulas:
أيام التأخير في الفترة = NETWORKDAYS.INTL([نسبة الغرامة من التكلفة اليومية],[الحد الأدنى (يوم)],16)
أيام التأخير في الفترة = DAYS(C30,[إجمالي غرامة التأخير, row above])+1
أيام بغرامة 25% = DAYS([الحد الأدنى (يوم)],[إجمالي غرامة التأخير, row above])+1

## Dashboard
القيمة الأصلية للحصر (قبل أمر التغيير) |  |  | القيمة المعتمدة (بعد أمر التغيير) | إجمالي المفوتر (SAR) |  | المتبقي (SAR) |  | نسبة الإنجاز الفعلية
#VALUE! |  |  | #VALUE! | 6052369.9904 |  | #VALUE! |  | #VALUE!
عدد البنود: 29 |  |  | #VALUE! | #VALUE! |  | #VALUE! |  | #REF!
بنود مكتملة |  |  | بنود جارية | بنود لم تبدأ |  | متجاوزة 100% |  | بنود عدّلها أمر التغيير
1 |  |  | 4 | 24 |  | 0 |  | 2
أعلى 10 بنود من حيث القيمة المتبقية
# | رقم البند | وصف البند |  |  | القيمة المتبقية (SAR) | القيمة المعتمدة (SAR) | نسبة الإنجاز % |  | الحالة
1 | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
2 | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
3 | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
4 | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
5 | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
6 | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
7 | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
8 | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
9 | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
10 | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
أكبر 10 زيادات في القيمة بسبب أمر التغيير
# | رقم البند | وصف البند |  |  | زيادة القيمة (SAR) | القيمة المعتمدة (SAR) | نسبة الإنجاز % |  | الحالة
1 | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
2 | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
3 | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
4 | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
5 | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
6 | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
7 | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
8 | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
9 | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
10 | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!

## Data Board
البيان | القيمة (SAR)
مفوتر | 6052369.9904
متبقي | #VALUE!
الحالة | عدد البنود | القيمة المعتمدة (SAR) | مفوتر (SAR) | متبقي (SAR)
مكتمل | 1 | 2840000 | 2840000 | 0 |  | 71718664
جاري | 4 | 4791700 | 3212369.9904 | 1579330.0096
لم يبدأ | 24 | #VALUE! | 0 | #VALUE!
إلغاء | 0 | 0 | 0 | 0
تجاوز 100% - راجع | 0 | 0 | 0 | 0
الإجمالي | 29 | #VALUE! | 6052369.9904 | #VALUE!
المجموعة (عدّل القائمة) | القيمة الأصلية (SAR) | القيمة المعتمدة (SAR) | فرق أمر التغيير (SAR) | مفوتر (SAR) | نسبة الإنجاز % | متبقي (SAR) | عدد البنود
D | 5580000 | 5580000 | 0 | 4417999.9904 | 79.18% | 1162000.0096 | 3
BQ | 2280200 | 2161700 | -118500 | 1634370 | 75.61% | 527330 | 3
NBQ | 0 | 0 | 0 | 0 | 0% | 0 | 0
CR1 | 0 | 0 | 0 | 0 | 0% | 0 | 0
الإجمالي | 7860200 | 7741700 | -118500 | 6052369.9904 | 78.18% | 1689330.0096 | 6
حالة أمر التغيير | عدد البنود | القيمة الأصلية (SAR) | القيمة المعتمدة (SAR) | الفرق (SAR)
جديد بأمر التغيير | 0 | 0 | 0 | 0
زيادة | 0 | 0 | 0 | 0
نقص | 2 | #VALUE! | #VALUE! | #VALUE!
بدون تغيير | 27 | 6296000 | 6296000 | 0
إلغاء | 0 | 0 | 0 | 0
الإجمالي | 29 | #VALUE! | #VALUE! | #VALUE!
رقم المستخلص | قيمة المستخلص (SAR) | تراكمي (SAR) | تراكمي % من المعتمد |  | آخر مستخلص | #REF!
1 | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF!
20 | #REF! | #REF! | #REF!
21 | #REF! | #REF! | #REF!
22 | #REF! | #REF! | #REF!
23 | #REF! | #REF! | #REF!
24 | #REF! | #REF! | #REF!
25 | #REF! | #REF! | #REF!
26 | #REF! | #REF! | #REF!
27 | #REF! | #REF! | #REF!
28 | #REF! | #REF! | #REF!
29 | #REF! | #REF! | #REF!
30 | #REF! | #REF! | #REF!
31 | #REF! | #REF! | #REF!
32 | #REF! | #REF! | #REF!
33 | #REF! | #REF! | #REF!
34 | #REF! | #REF! | #REF!
35 | #REF! | #REF! | #REF!
36 | #REF! | #REF! | #REF!
مراجعة المطابقة | الفرق (يجب = 0)
القيمة المعتمدة في التقرير مقابل TOTAL في SUMMARY (مجموع الفروق) | #VALUE!
المفوتر في التقرير مقابل مجموع صفوف INVOICE | #REF!
المفوتر مقابل مجموع صفوف Overall Completion INVOICE (إجماليات البنود) | #REF!
مجموع المجموعات مقابل إجمالي التقرير (لو ظهرت مجموعة جديدة أضفها للقائمة) | #VALUE!
عدد بنود SUMMARY مقابل عدد صفوف التقرير (سعة التقرير 350) | #REF!

## Details Data Board
عداد البنود | صف بند؟ | كود البند | نوع الصف | رقم المستخلص | آخر عمود (صف البند) | آخر عمود (صف الإجمالي) | حد أعمدة المراحل | قيمة صف المستخلص | إجمالي صف Overall
0 | 0 |  |  |  | 8 | 8 | 8 | 0 | 0
0 | 0 |  |  |  | 8 | 8 | 8 | 0 | 0
1 | 1 | D-001 |  |  | 10 | 8 | 10 | 0 | 0
1 | 0 | D-001 |  |  | 10 | 8 | 10 | 0 | 0
1 | 0 | D-001 |  |  | 10 | 8 | 10 | 0 | 0
1 | 0 | D-001 | INVOICE | 1 | 10 | 8 | 10 | 1704000 | 0
1 | 0 | D-001 |  |  | 10 | 8 | 10 | 0 | 0
1 | 0 | D-001 | INVOICE | 3 | 10 | 8 | 10 | 852000 | 0
1 | 0 | D-001 |  |  | 10 | 8 | 10 | 0 | 0
1 | 0 | D-001 | INVOICE | 5 | 10 | 8 | 10 | 284000 | 0
1 | 0 | D-001 | OVERALL |  | 10 | 8 | 10 | 0 | 2840000
1 | 0 | D-001 |  |  | 10 | 9 | 10 | 0 | 0
1 | 0 | D-001 |  |  | 10 | 9 | 10 | 0 | 0
1 | 0 | D-001 |  |  | 10 | 9 | 10 | 0 | 0
1 | 0 | D-001 |  |  | 10 | 9 | 10 | 0 | 0
2 | 1 | D-002 |  |  | 10 | 9 | 10 | 0 | 0
2 | 0 | D-002 |  |  | 10 | 9 | 10 | 0 | 0
2 | 0 | D-002 |  |  | 10 | 9 | 10 | 0 | 0
2 | 0 | D-002 | INVOICE | 5 | 10 | 9 | 10 | 126240 | 0
2 | 0 | D-002 |  |  | 10 | 9 | 10 | 0 | 0
2 | 0 | D-002 | INVOICE | 6 | 10 | 9 | 10 | 325163.6364 | 0
2 | 0 | D-002 |  |  | 10 | 9 | 10 | 0 | 0
2 | 0 | D-002 | INVOICE | 7 | 10 | 9 | 10 | 478181.8182 | 0
2 | 0 | D-002 |  |  | 10 | 9 | 10 | 0 | 0
2 | 0 | D-002 | INVOICE | 8 | 10 | 9 | 10 | 47818.1818 | 0
2 | 0 | D-002 |  |  | 10 | 9 | 10 | 0 | 0
2 | 0 | D-002 | INVOICE | 10 | 10 | 9 | 10 | 76509.0909 | 0
2 | 0 | D-002 |  |  | 10 | 9 | 10 | 0 | 0
2 | 0 | D-002 | INVOICE | 11 | 10 | 9 | 10 | 33472.7273 | 0
2 | 0 | D-002 |  |  | 10 | 9 | 10 | 0 | 0
2 | 0 | D-002 | INVOICE | 12 | 10 | 9 | 10 | 38254.5455 | 0
2 | 0 | D-002 |  |  | 10 | 9 | 10 | 0 | 0
2 | 0 | D-002 | INVOICE | 14 | 10 | 9 | 10 | 26778.1723 | 0
2 | 0 | D-002 |  |  | 10 | 9 | 10 | 0 | 0
2 | 0 | D-002 | INVOICE | 15 | 10 | 9 | 10 | 86072.7273 | 0
2 | 0 | D-002 |  |  | 10 | 9 | 10 | 0 | 0
2 | 0 | D-002 | INVOICE | 20 | 10 | 9 | 10 | 23909.0909 | 0
2 | 0 | D-002 |  |  | 10 | 9 | 10 | 0 | 0
2 | 0 | D-002 | INVOICE | 26 | 10 | 9 | 10 | 315600 | 0
2 | 0 | D-002 |  |  | 10 | 9 | 10 | 0 | 0
2 | 0 | D-002 | OVERALL |  | 10 | 9 | 10 | 0 | 1578000.0004
2 | 0 | D-002 |  |  | 10 | 9 | 10 | 0 | 0
2 | 0 | D-002 |  |  | 10 | 9 | 10 | 0 | 0
2 | 0 | D-002 |  |  | 10 | 9 | 10 | 0 | 0
2 | 0 | D-002 |  |  | 10 | 9 | 10 | 0 | 0
2 | 0 | D-002 |  |  | 10 | 9 | 10 | 0 | 0
3 | 1 | D-003 |  |  | 9 | 9 | 9 | 0 | 0
3 | 0 | D-003 |  |  | 9 | 9 | 9 | 0 | 0
3 | 0 | D-003 |  |  | 9 | 9 | 9 | 0 | 0
3 | 0 | D-003 | INVOICE | 0 | 9 | 9 | 9 | 0 | 0
3 | 0 | D-003 |  |  | 9 | 9 | 9 | 0 | 0
3 | 0 | D-003 | OVERALL |  | 9 | 9 | 9 | 0 | 0
3 | 0 | D-003 |  |  | 9 | 15 | 15 | 0 | 0
3 | 0 | D-003 |  |  | 9 | 15 | 15 | 0 | 0
3 | 0 | D-003 |  |  | 9 | 15 | 15 | 0 | 0
3 | 0 | D-003 |  |  | 9 | 15 | 15 | 0 | 0
3 | 0 | D-003 |  |  | 9 | 15 | 15 | 0 | 0
4 | 1 | BQ-001 |  |  | 14 | 15 | 15 | 0 | 0
4 | 0 | BQ-001 |  |  | 14 | 15 | 15 | 0 | 0
4 | 0 | BQ-001 |  |  | 14 | 15 | 15 | 0 | 0
4 | 0 | BQ-001 | INVOICE | 13 | 14 | 15 | 15 | 364000 | 0
4 | 0 | BQ-001 |  |  | 14 | 15 | 15 | 0 | 0
4 | 0 | BQ-001 | INVOICE | 25 | 14 | 15 | 15 | 31200 | 0
4 | 0 | BQ-001 |  |  | 14 | 15 | 15 | 0 | 0
4 | 0 | BQ-001 | INVOICE | 28 | 14 | 15 | 15 | 18200 | 0
4 | 0 | BQ-001 |  |  | 14 | 15 | 15 | 0 | 0
4 | 0 | BQ-001 | INVOICE | 32 | 14 | 15 | 15 | 2600 | 0
4 | 0 | BQ-001 |  |  | 14 | 15 | 15 | 0 | 0
4 | 0 | BQ-001 | OVERALL |  | 14 | 15 | 15 | 0 | 416000
4 | 0 | BQ-001 |  |  | 14 | 15 | 15 | 0 | 0
4 | 0 | BQ-001 |  |  | 14 | 15 | 15 | 0 | 0
4 | 0 | BQ-001 |  |  | 14 | 15 | 15 | 0 | 0
4 | 0 | BQ-001 |  |  | 14 | 15 | 15 | 0 | 0
4 | 0 | BQ-001 |  |  | 14 | 15 | 15 | 0 | 0
4 | 0 | BQ-001 |  |  | 14 | 15 | 15 | 0 | 0
4 | 0 | BQ-001 |  |  | 14 | 15 | 15 | 0 | 0
4 | 0 | BQ-001 |  |  | 14 | 15 | 15 | 0 | 0
5 | 1 | BQ-002 |  |  | 14 | 15 | 15 | 0 | 0
5 | 0 | BQ-002 |  |  | 14 | 15 | 15 | 0 | 0
5 | 0 | BQ-002 |  |  | 14 | 15 | 15 | 0 | 0
5 | 0 | BQ-002 | INVOICE | 13 | 14 | 15 | 15 | 41160 | 0
5 | 0 | BQ-002 |  |  | 14 | 15 | 15 | 0 | 0
5 | 0 | BQ-002 | INVOICE | 15 | 14 | 15 | 15 | 96040 | 0
5 | 0 | BQ-002 |  |  | 14 | 15 | 15 | 0 | 0
5 | 0 | BQ-002 | INVOICE | 25 | 14 | 15 | 15 | 11760 | 0
5 | 0 | BQ-002 |  |  | 14 | 15 | 15 | 0 | 0
5 | 0 | BQ-002 | INVOICE | 28 | 14 | 15 | 15 | -67816 | 0
5 | 0 | BQ-002 |  |  | 14 | 15 | 15 | 0 | 0
5 | 0 | BQ-002 | INVOICE | 29 | 14 | 15 | 15 | -5880 | 0
5 | 0 | BQ-002 |  |  | 14 | 15 | 15 | 0 | 0
5 | 0 | BQ-002 | INVOICE | 32 | 14 | 15 | 15 | 3136 | 0
5 | 0 | BQ-002 |  |  | 14 | 15 | 15 | 0 | 0
5 | 0 | BQ-002 | OVERALL |  | 14 | 15 | 15 | 0 | 78400
5 | 0 | BQ-002 |  |  | 14 | 17 | 17 | 0 | 0
5 | 0 | BQ-002 |  |  | 14 | 17 | 17 | 0 | 0
5 | 0 | BQ-002 |  |  | 14 | 17 | 17 | 0 | 0
5 | 0 | BQ-002 |  |  | 14 | 17 | 17 | 0 | 0
5 | 0 | BQ-002 |  |  | 14 | 17 | 17 | 0 | 0
5 | 0 | BQ-002 |  |  | 14 | 17 | 17 | 0 | 0
5 | 0 | BQ-002 |  |  | 14 | 17 | 17 | 0 | 0
5 | 0 | BQ-002 |  |  | 14 | 17 | 17 | 0 | 0
6 | 1 | BQ-003 |  |  | 16 | 17 | 17 | 0 | 0
6 | 0 | BQ-003 |  |  | 16 | 17 | 17 | 0 | 0
6 | 0 | BQ-003 |  |  | 16 | 17 | 17 | 0 | 0
6 | 0 | BQ-003 | INVOICE | 20 | 16 | 17 | 17 | 54510 | 0
6 | 0 | BQ-003 |  |  | 16 | 17 | 17 | 0 | 0
6 | 0 | BQ-003 | INVOICE | 21 | 16 | 17 | 17 | 4740 | 0
6 | 0 | BQ-003 |  |  | 16 | 17 | 17 | 0 | 0
6 | 0 | BQ-003 | INVOICE | 24 | 16 | 17 | 17 | 796320 | 0
6 | 0 | BQ-003 |  |  | 16 | 17 | 17 | 0 | 0
6 | 0 | BQ-003 | INVOICE | 25 | 16 | 17 | 17 | 57472.5 | 0
6 | 0 | BQ-003 |  |  | 16 | 17 | 17 | 0 | 0
6 | 0 | BQ-003 | INVOICE | 26 | 16 | 17 | 17 | 117315 | 0
6 | 0 | BQ-003 |  |  | 16 | 17 | 17 | 0 | 0
6 | 0 | BQ-003 | INVOICE | 27 | 16 | 17 | 17 | 9480 | 0
6 | 0 | BQ-003 |  |  | 16 | 17 | 17 | 0 | 0
6 | 0 | BQ-003 | INVOICE | 28 | 16 | 17 | 17 | 28440 | 0
6 | 0 | BQ-003 |  |  | 16 | 17 | 17 | 0 | 0
6 | 0 | BQ-003 | INVOICE | 29 | 16 | 17 | 17 | 45326.25 | 0
6 | 0 | BQ-003 |  |  | 16 | 17 | 17 | 0 | 0
6 | 0 | BQ-003 | INVOICE | 30 | 16 | 17 | 17 | 5628.75 | 0
6 | 0 | BQ-003 |  |  | 16 | 17 | 17 | 0 | 0
6 | 0 | BQ-003 | INVOICE | 31 | 16 | 17 | 17 | 11257.5 | 0
6 | 0 | BQ-003 |  |  | 16 | 17 | 17 | 0 | 0
6 | 0 | BQ-003 | INVOICE | 32 | 16 | 17 | 17 | 9480 | 0
6 | 0 | BQ-003 |  |  | 16 | 17 | 17 | 0 | 0
6 | 0 | BQ-003 | OVERALL |  | 16 | 17 | 17 | 0 | 1146487.5
6 | 0 | BQ-003 |  |  | 16 | 22 | 22 | 0 | 0
6 | 0 | BQ-003 |  |  | 16 | 22 | 22 | 0 | 0
6 | 0 | BQ-003 |  |  | 16 | 22 | 22 | 0 | 0
6 | 0 | BQ-003 |  |  | 16 | 22 | 22 | 0 | 0
6 | 0 | BQ-003 |  |  | 16 | 22 | 22 | 0 | 0
6 | 0 | BQ-003 |  |  | 16 | 22 | 22 | 0 | 0
6 | 0 | BQ-003 |  |  | 16 | 22 | 22 | 0 | 0
6 | 0 | BQ-003 |  |  | 16 | 22 | 22 | 0 | 0
7 | 1 | BQ-004 |  |  | 21 | 22 | 22 | 0 | 0
7 | 0 | BQ-004 |  |  | 21 | 22 | 22 | 0 | 0
7 | 0 | BQ-004 |  |  | 21 | 22 | 22 | 0 | 0
7 | 0 | BQ-004 | INVOICE | 13 | 21 | 22 | 22 | 454041.6 | 0
7 | 0 | BQ-004 |  |  | 21 | 22 | 22 | 0 | 0
7 | 0 | BQ-004 | INVOICE | 19 | 21 | 22 | 22 | 153600 | 0
7 | 0 | BQ-004 |  |  | 21 | 22 | 22 | 0 | 0
7 | 0 | BQ-004 | INVOICE | 20 | 21 | 22 | 22 | 38400 | 0
7 | 0 | BQ-004 |  |  | 21 | 22 | 22 | 0 | 0
7 | 0 | BQ-004 | INVOICE | 23 | 21 | 22 | 22 | 33792 | 0
7 | 0 | BQ-004 |  |  | 21 | 22 | 22 | 0 | 0
7 | 0 | BQ-004 | INVOICE | 24 | 21 | 22 | 22 | 412800 | 0
7 | 0 | BQ-004 |  |  | 21 | 22 | 22 | 0 | 0
7 | 0 | BQ-004 | INVOICE | 25 | 21 | 22 | 22 | 422899.2 | 0
7 | 0 | BQ-004 |  |  | 21 | 22 | 22 | 0 | 0
7 | 0 | BQ-004 | INVOICE | 26 | 21 | 22 | 22 | 412721.6 | 0
7 | 0 | BQ-004 |  |  | 21 | 22 | 22 | 0 | 0
7 | 0 | BQ-004 | INVOICE | 27 | 21 | 22 | 22 | 734252.8 | 0
7 | 0 | BQ-004 |  |  | 21 | 22 | 22 | 0 | 0
7 | 0 | BQ-004 | INVOICE | 28 | 21 | 22 | 22 | 342326.4 | 0
7 | 0 | BQ-004 |  |  | 21 | 22 | 22 | 0 | 0
7 | 0 | BQ-004 | INVOICE | 29 | 21 | 22 | 22 | 413308.8 | 0
7 | 0 | BQ-004 |  |  | 21 | 22 | 22 | 0 | 0
7 | 0 | BQ-004 | INVOICE | 30 | 21 | 22 | 22 | 145728 | 0
7 | 0 | BQ-004 |  |  | 21 | 22 | 22 | 0 | 0
7 | 0 | BQ-004 | INVOICE | 32 | 21 | 22 | 22 | 53145.6 | 0
7 | 0 | BQ-004 |  |  | 21 | 22 | 22 | 0 | 0
7 | 0 | BQ-004 | OVERALL |  | 21 | 22 | 22 | 0 | 4120612.8
7 | 0 | BQ-004 |  |  | 21 | 16 | 21 | 0 | 0
7 | 0 | BQ-004 |  |  | 21 | 16 | 21 | 0 | 0
7 | 0 | BQ-004 |  |  | 21 | 16 | 21 | 0 | 0
7 | 0 | BQ-004 |  |  | 21 | 16 | 21 | 0 | 0
7 | 0 | BQ-004 |  |  | 21 | 16 | 21 | 0 | 0
7 | 0 | BQ-004 |  |  | 21 | 16 | 21 | 0 | 0
7 | 0 | BQ-004 |  |  | 21 | 16 | 21 | 0 | 0
7 | 0 | BQ-004 |  |  | 21 | 16 | 21 | 0 | 0
8 | 1 | BQ-059 |  |  | 15 | 16 | 16 | 0 | 0
8 | 0 | BQ-059 |  |  | 15 | 16 | 16 | 0 | 0
8 | 0 | BQ-059 |  |  | 15 | 16 | 16 | 0 | 0
8 | 0 | BQ-059 | INVOICE | 13 | 15 | 16 | 16 | 1430 | 0
8 | 0 | BQ-059 |  |  | 15 | 16 | 16 | 0 | 0
8 | 0 | BQ-059 | INVOICE | 25 | 15 | 16 | 16 | 390 | 0
8 | 0 | BQ-059 |  |  | 15 | 16 | 16 | 0 | 0
8 | 0 | BQ-059 | INVOICE | 27 | 15 | 16 | 16 | 65 | 0
8 | 0 | BQ-059 |  |  | 15 | 16 | 16 | 0 | 0
8 | 0 | BQ-059 | INVOICE | 28 | 15 | 16 | 16 | 195 | 0
8 | 0 | BQ-059 |  |  | 15 | 16 | 16 | 0 | 0
8 | 0 | BQ-059 |  |  | 15 | 16 | 16 | 0 | 0
8 | 0 | BQ-059 |  |  | 15 | 16 | 16 | 0 | 0
8 | 0 | BQ-059 | OVERALL |  | 15 | 16 | 16 | 0 | 2080
8 | 0 | BQ-059 |  |  | 15 | 16 | 16 | 0 | 0
8 | 0 | BQ-059 |  |  | 15 | 16 | 16 | 0 | 0
8 | 0 | BQ-059 |  |  | 15 | 16 | 16 | 0 | 0
8 | 0 | BQ-059 |  |  | 15 | 16 | 16 | 0 | 0
8 | 0 | BQ-059 |  |  | 15 | 16 | 16 | 0 | 0
8 | 0 | BQ-059 |  |  | 15 | 16 | 16 | 0 | 0
8 | 0 | BQ-059 |  |  | 15 | 16 | 16 | 0 | 0
8 | 0 | BQ-059 |  |  | 15 | 16 | 16 | 0 | 0
9 | 1 | BQ-060 |  |  | 15 | 16 | 16 | 0 | 0
9 | 0 | BQ-060 |  |  | 15 | 16 | 16 | 0 | 0
9 | 0 | BQ-060 |  |  | 15 | 16 | 16 | 0 | 0
9 | 0 | BQ-060 | INVOICE | 13 | 15 | 16 | 16 | 3520 | 0
9 | 0 | BQ-060 |  |  | 15 | 16 | 16 | 0 | 0
9 | 0 | BQ-060 | INVOICE | 25 | 15 | 16 | 16 | 480 | 0
9 | 0 | BQ-060 |  |  | 15 | 16 | 16 | 0 | 0
9 | 0 | BQ-060 | INVOICE | 27 | 15 | 16 | 16 | 80 | 0
9 | 0 | BQ-060 |  |  | 15 | 16 | 16 | 0 | 0
9 | 0 | BQ-060 | INVOICE | 28 | 15 | 16 | 16 | 1040 | 0
9 | 0 | BQ-060 |  |  | 15 | 16 | 16 | 0 | 0
9 | 0 | BQ-060 |  |  | 15 | 16 | 16 | 0 | 0
9 | 0 | BQ-060 |  |  | 15 | 16 | 16 | 0 | 0
9 | 0 | BQ-060 | OVERALL |  | 15 | 16 | 16 | 0 | 5120
9 | 0 | BQ-060 |  |  | 15 | 16 | 16 | 0 | 0
9 | 0 | BQ-060 |  |  | 15 | 16 | 16 | 0 | 0
9 | 0 | BQ-060 |  |  | 15 | 16 | 16 | 0 | 0
9 | 0 | BQ-060 |  |  | 15 | 16 | 16 | 0 | 0
9 | 0 | BQ-060 |  |  | 15 | 16 | 16 | 0 | 0
9 | 0 | BQ-060 |  |  | 15 | 16 | 16 | 0 | 0
9 | 0 | BQ-060 |  |  | 15 | 16 | 16 | 0 | 0
9 | 0 | BQ-060 |  |  | 15 | 16 | 16 | 0 | 0
10 | 1 | BQ-061 |  |  | 15 | 16 | 16 | 0 | 0
10 | 0 | BQ-061 |  |  | 15 | 16 | 16 | 0 | 0
10 | 0 | BQ-061 |  |  | 15 | 16 | 16 | 0 | 0
10 | 0 | BQ-061 | INVOICE | 12 | 15 | 16 | 16 | 22330 | 0
10 | 0 | BQ-061 |  |  | 15 | 16 | 16 | 0 | 0
10 | 0 | BQ-061 | INVOICE | 25 | 15 | 16 | 16 | 6090 | 0
10 | 0 | BQ-061 |  |  | 15 | 16 | 16 | 0 | 0
10 | 0 | BQ-061 | INVOICE | 27 | 15 | 16 | 16 | 1015 | 0
10 | 0 | BQ-061 |  |  | 15 | 16 | 16 | 0 | 0
10 | 0 | BQ-061 | INVOICE | 28 | 15 | 16 | 16 | 3045 | 0
10 | 0 | BQ-061 |  |  | 15 | 16 | 16 | 0 | 0
10 | 0 | BQ-061 |  |  | 15 | 16 | 16 | 0 | 0
10 | 0 | BQ-061 |  |  | 15 | 16 | 16 | 0 | 0
10 | 0 | BQ-061 | OVERALL |  | 15 | 16 | 16 | 0 | 32480
10 | 0 | BQ-061 |  |  | 15 | 15 | 15 | 0 | 0
10 | 0 | BQ-061 |  |  | 15 | 15 | 15 | 0 | 0
10 | 0 | BQ-061 |  |  | 15 | 15 | 15 | 0 | 0
10 | 0 | BQ-061 |  |  | 15 | 15 | 15 | 0 | 0
10 | 0 | BQ-061 |  |  | 15 | 15 | 15 | 0 | 0
10 | 0 | BQ-061 |  |  | 15 | 15 | 15 | 0 | 0
10 | 0 | BQ-061 |  |  | 15 | 15 | 15 | 0 | 0
10 | 0 | BQ-061 |  |  | 15 | 15 | 15 | 0 | 0
11 | 1 | BQ-062 |  |  | 14 | 15 | 15 | 0 | 0
11 | 0 | BQ-062 |  |  | 14 | 15 | 15 | 0 | 0
11 | 0 | BQ-062 |  |  | 14 | 15 | 15 | 0 | 0
11 | 0 | BQ-062 | INVOICE | 27 | 14 | 15 | 15 | 2970 | 0
11 | 0 | BQ-062 |  |  | 14 | 15 | 15 | 0 | 0
11 | 0 | BQ-062 | INVOICE | 28 | 14 | 15 | 15 | 990 | 0
11 | 0 | BQ-062 |  |  | 14 | 15 | 15 | 0 | 0
11 | 0 | BQ-062 |  |  | 14 | 15 | 15 | 0 | 0
11 | 0 | BQ-062 |  |  | 14 | 15 | 15 | 0 | 0
11 | 0 | BQ-062 | OVERALL |  | 14 | 15 | 15 | 0 | 3960
11 | 0 | BQ-062 |  |  | 14 | 15 | 15 | 0 | 0
11 | 0 | BQ-062 |  |  | 14 | 15 | 15 | 0 | 0
11 | 0 | BQ-062 |  |  | 14 | 15 | 15 | 0 | 0
11 | 0 | BQ-062 |  |  | 14 | 15 | 15 | 0 | 0
11 | 0 | BQ-062 |  |  | 14 | 15 | 15 | 0 | 0
11 | 0 | BQ-062 |  |  | 14 | 15 | 15 | 0 | 0
11 | 0 | BQ-062 |  |  | 14 | 15 | 15 | 0 | 0
11 | 0 | BQ-062 |  |  | 14 | 15 | 15 | 0 | 0
12 | 1 | BQ-063 |  |  | 14 | 15 | 15 | 0 | 0
12 | 0 | BQ-063 |  |  | 14 | 15 | 15 | 0 | 0
12 | 0 | BQ-063 |  |  | 14 | 15 | 15 | 0 | 0
12 | 0 | BQ-063 | INVOICE | 13 | 14 | 15 | 15 | 24332 | 0
12 | 0 | BQ-063 |  |  | 14 | 15 | 15 | 0 | 0
12 | 0 | BQ-063 | INVOICE | 25 | 14 | 15 | 15 | 7742 | 0
12 | 0 | BQ-063 |  |  | 14 | 15 | 15 | 0 | 0
12 | 0 | BQ-063 | INVOICE | 30 | 14 | 15 | 15 | 3318 | 0
12 | 0 | BQ-063 |  |  | 14 | 15 | 15 | 0 | 0
12 | 0 | BQ-063 |  |  | 14 | 15 | 15 | 0 | 0
12 | 0 | BQ-063 |  |  | 14 | 15 | 15 | 0 | 0
12 | 0 | BQ-063 |  |  | 14 | 15 | 15 | 0 | 0
12 | 0 | BQ-063 |  |  | 14 | 15 | 15 | 0 | 0
12 | 0 | BQ-063 | OVERALL |  | 14 | 15 | 15 | 0 | 35392
12 | 0 | BQ-063 |  |  | 14 | 15 | 15 | 0 | 0
12 | 0 | BQ-063 |  |  | 14 | 15 | 15 | 0 | 0
12 | 0 | BQ-063 |  |  | 14 | 15 | 15 | 0 | 0
12 | 0 | BQ-063 |  |  | 14 | 15 | 15 | 0 | 0
12 | 0 | BQ-063 |  |  | 14 | 15 | 15 | 0 | 0
12 | 0 | BQ-063 |  |  | 14 | 15 | 15 | 0 | 0
12 | 0 | BQ-063 |  |  | 14 | 15 | 15 | 0 | 0
12 | 0 | BQ-063 |  |  | 14 | 15 | 15 | 0 | 0
13 | 1 | BQ-064 |  |  | 14 | 15 | 15 | 0 | 0
13 | 0 | BQ-064 |  |  | 14 | 15 | 15 | 0 | 0
13 | 0 | BQ-064 |  |  | 14 | 15 | 15 | 0 | 0
13 | 0 | BQ-064 | INVOICE | 14 | 14 | 15 | 15 | 4620 | 0
13 | 0 | BQ-064 |  |  | 14 | 15 | 15 | 0 | 0
13 | 0 | BQ-064 | INVOICE | 25 | 14 | 15 | 15 | 1470 | 0
13 | 0 | BQ-064 |  |  | 14 | 15 | 15 | 0 | 0
13 | 0 | BQ-064 | INVOICE | 30 | 14 | 15 | 15 | 630 | 0
13 | 0 | BQ-064 |  |  | 14 | 15 | 15 | 0 | 0
13 | 0 | BQ-064 |  |  | 14 | 15 | 15 | 0 | 0
13 | 0 | BQ-064 |  |  | 14 | 15 | 15 | 0 | 0
13 | 0 | BQ-064 |  |  | 14 | 15 | 15 | 0 | 0
13 | 0 | BQ-064 |  |  | 14 | 15 | 15 | 0 | 0
13 | 0 | BQ-064 | OVERALL |  | 14 | 15 | 15 | 0 | 6720
13 | 0 | BQ-064 |  |  | 14 | 15 | 15 | 0 | 0
13 | 0 | BQ-064 |  |  | 14 | 15 | 15 | 0 | 0
13 | 0 | BQ-064 |  |  | 14 | 15 | 15 | 0 | 0
13 | 0 | BQ-064 |  |  | 14 | 15 | 15 | 0 | 0
13 | 0 | BQ-064 |  |  | 14 | 15 | 15 | 0 | 0
13 | 0 | BQ-064 |  |  | 14 | 15 | 15 | 0 | 0
13 | 0 | BQ-064 |  |  | 14 | 15 | 15 | 0 | 0
13 | 0 | BQ-064 |  |  | 14 | 15 | 15 | 0 | 0
14 | 1 | BQ-065 |  |  | 14 | 15 | 15 | 0 | 0
14 | 0 | BQ-065 |  |  | 14 | 15 | 15 | 0 | 0
14 | 0 | BQ-065 |  |  | 14 | 15 | 15 | 0 | 0
14 | 0 | BQ-065 | INVOICE | 14 | 14 | 15 | 15 | 924 | 0
14 | 0 | BQ-065 |  |  | 14 | 15 | 15 | 0 | 0
14 | 0 | BQ-065 | INVOICE | 25 | 14 | 15 | 15 | 294 | 0
14 | 0 | BQ-065 |  |  | 14 | 15 | 15 | 0 | 0
14 | 0 | BQ-065 | INVOICE | 30 | 14 | 15 | 15 | 126 | 0
14 | 0 | BQ-065 |  |  | 14 | 15 | 15 | 0 | 0
14 | 0 | BQ-065 |  |  | 14 | 15 | 15 | 0 | 0
14 | 0 | BQ-065 |  |  | 14 | 15 | 15 | 0 | 0
14 | 0 | BQ-065 |  |  | 14 | 15 | 15 | 0 | 0
14 | 0 | BQ-065 |  |  | 14 | 15 | 15 | 0 | 0
14 | 0 | BQ-065 | OVERALL |  | 14 | 15 | 15 | 0 | 1344
14 | 0 | BQ-065 |  |  | 14 | 15 | 15 | 0 | 0
14 | 0 | BQ-065 |  |  | 14 | 15 | 15 | 0 | 0
14 | 0 | BQ-065 |  |  | 14 | 15 | 15 | 0 | 0
14 | 0 | BQ-065 |  |  | 14 | 15 | 15 | 0 | 0
14 | 0 | BQ-065 |  |  | 14 | 15 | 15 | 0 | 0
14 | 0 | BQ-065 |  |  | 14 | 15 | 15 | 0 | 0
14 | 0 | BQ-065 |  |  | 14 | 15 | 15 | 0 | 0
14 | 0 | BQ-065 |  |  | 14 | 15 | 15 | 0 | 0
15 | 1 | BQ-066 |  |  | 14 | 15 | 15 | 0 | 0
15 | 0 | BQ-066 |  |  | 14 | 15 | 15 | 0 | 0
15 | 0 | BQ-066 |  |  | 14 | 15 | 15 | 0 | 0
15 | 0 | BQ-066 | INVOICE | 14 | 14 | 15 | 15 | 940.5 | 0
15 | 0 | BQ-066 |  |  | 14 | 15 | 15 | 0 | 0
15 | 0 | BQ-066 | INVOICE | 25 | 14 | 15 | 15 | 233.415 | 0
15 | 0 | BQ-066 |  |  | 14 | 15 | 15 | 0 | 0
15 | 0 | BQ-066 | INVOICE | 27 | 14 | 15 | 15 | 65.835 | 0
15 | 0 | BQ-066 |  |  | 14 | 15 | 15 | 0 | 0
15 | 0 | BQ-066 | INVOICE | 30 | 14 | 15 | 15 | 128.25 | 0
15 | 0 | BQ-066 |  |  | 14 | 15 | 15 | 0 | 0
15 | 0 | BQ-066 |  |  | 14 | 15 | 15 | 0 | 0
15 | 0 | BQ-066 |  |  | 14 | 15 | 15 | 0 | 0
15 | 0 | BQ-066 | OVERALL |  | 14 | 15 | 15 | 0 | 1368
15 | 0 | BQ-066 |  |  | 14 | 16 | 16 | 0 | 0
15 | 0 | BQ-066 |  |  | 14 | 16 | 16 | 0 | 0
15 | 0 | BQ-066 |  |  | 14 | 16 | 16 | 0 | 0
15 | 0 | BQ-066 |  |  | 14 | 16 | 16 | 0 | 0
15 | 0 | BQ-066 |  |  | 14 | 16 | 16 | 0 | 0
15 | 0 | BQ-066 |  |  | 14 | 16 | 16 | 0 | 0
15 | 0 | BQ-066 |  |  | 14 | 16 | 16 | 0 | 0
15 | 0 | BQ-066 |  |  | 14 | 16 | 16 | 0 | 0
16 | 1 | BQ-067 |  |  | 15 | 16 | 16 | 0 | 0
16 | 0 | BQ-067 |  |  | 15 | 16 | 16 | 0 | 0
16 | 0 | BQ-067 |  |  | 15 | 16 | 16 | 0 | 0
16 | 0 | BQ-067 | INVOICE | 26 | 15 | 16 | 16 | 68320 | 0
16 | 0 | BQ-067 |  |  | 15 | 16 | 16 | 0 | 0
16 | 0 | BQ-067 | INVOICE | 29 | 15 | 16 | 16 | 8784 | 0
16 | 0 | BQ-067 |  |  | 15 | 16 | 16 | 0 | 0
16 | 0 | BQ-067 | INVOICE | 31 | 15 | 16 | 16 | 976 | 0
16 | 0 | BQ-067 |  |  | 15 | 16 | 16 | 0 | 0
16 | 0 | BQ-067 |  |  | 15 | 16 | 16 | 0 | 0
16 | 0 | BQ-067 |  |  | 15 | 16 | 16 | 0 | 0
16 | 0 | BQ-067 |  |  | 15 | 16 | 16 | 0 | 0
16 | 0 | BQ-067 |  |  | 15 | 16 | 16 | 0 | 0
16 | 0 | BQ-067 | OVERALL |  | 15 | 16 | 16 | 0 | 78080
16 | 0 | BQ-067 |  |  | 15 | 15 | 15 | 0 | 0
16 | 0 | BQ-067 |  |  | 15 | 15 | 15 | 0 | 0
16 | 0 | BQ-067 |  |  | 15 | 15 | 15 | 0 | 0
16 | 0 | BQ-067 |  |  | 15 | 15 | 15 | 0 | 0
16 | 0 | BQ-067 |  |  | 15 | 15 | 15 | 0 | 0
16 | 0 | BQ-067 |  |  | 15 | 15 | 15 | 0 | 0
16 | 0 | BQ-067 |  |  | 15 | 15 | 15 | 0 | 0
16 | 0 | BQ-067 |  |  | 15 | 15 | 15 | 0 | 0
17 | 1 | BQ-068 |  |  | 14 | 15 | 15 | 0 | 0
17 | 0 | BQ-068 |  |  | 14 | 15 | 15 | 0 | 0
17 | 0 | BQ-068 |  |  | 14 | 15 | 15 | 0 | 0
17 | 0 | BQ-068 | INVOICE | 16 | 14 | 15 | 15 | 13020 | 0
17 | 0 | BQ-068 |  |  | 14 | 15 | 15 | 0 | 0
17 | 0 | BQ-068 | INVOICE | 28 | 14 | 15 | 15 | 1302 | 0
17 | 0 | BQ-068 |  |  | 14 | 15 | 15 | 0 | 0
17 | 0 | BQ-068 | INVOICE | 30 | 14 | 15 | 15 | 558 | 0
17 | 0 | BQ-068 |  |  | 14 | 15 | 15 | 0 | 0
17 | 0 | BQ-068 |  |  | 14 | 15 | 15 | 0 | 0
17 | 0 | BQ-068 |  |  | 14 | 15 | 15 | 0 | 0
17 | 0 | BQ-068 |  |  | 14 | 15 | 15 | 0 | 0
17 | 0 | BQ-068 |  |  | 14 | 15 | 15 | 0 | 0
17 | 0 | BQ-068 | OVERALL |  | 14 | 15 | 15 | 0 | 14880
17 | 0 | BQ-068 |  |  | 14 | 15 | 15 | 0 | 0
17 | 0 | BQ-068 |  |  | 14 | 15 | 15 | 0 | 0
17 | 0 | BQ-068 |  |  | 14 | 15 | 15 | 0 | 0
17 | 0 | BQ-068 |  |  | 14 | 15 | 15 | 0 | 0
17 | 0 | BQ-068 |  |  | 14 | 15 | 15 | 0 | 0
17 | 0 | BQ-068 |  |  | 14 | 15 | 15 | 0 | 0
17 | 0 | BQ-068 |  |  | 14 | 15 | 15 | 0 | 0
17 | 0 | BQ-068 |  |  | 14 | 15 | 15 | 0 | 0
18 | 1 | BQ-069 |  |  | 14 | 15 | 15 | 0 | 0
18 | 0 | BQ-069 |  |  | 14 | 15 | 15 | 0 | 0
18 | 0 | BQ-069 |  |  | 14 | 15 | 15 | 0 | 0
18 | 0 | BQ-069 | INVOICE | 13 | 14 | 15 | 15 | 9240 | 0
18 | 0 | BQ-069 |  |  | 14 | 15 | 15 | 0 | 0
18 | 0 | BQ-069 | INVOICE | 27 | 14 | 15 | 15 | 840 | 0
18 | 0 | BQ-069 |  |  | 14 | 15 | 15 | 0 | 0
18 | 0 | BQ-069 | INVOICE | 28 | 14 | 15 | 15 | 3360 | 0
18 | 0 | BQ-069 |  |  | 14 | 15 | 15 | 0 | 0
18 | 0 | BQ-069 |  |  | 14 | 15 | 15 | 0 | 0
18 | 0 | BQ-069 |  |  | 14 | 15 | 15 | 0 | 0
18 | 0 | BQ-069 |  |  | 14 | 15 | 15 | 0 | 0
18 | 0 | BQ-069 |  |  | 14 | 15 | 15 | 0 | 0
18 | 0 | BQ-069 | OVERALL |  | 14 | 15 | 15 | 0 | 13440
18 | 0 | BQ-069 |  |  | 14 | 15 | 15 | 0 | 0
18 | 0 | BQ-069 |  |  | 14 | 15 | 15 | 0 | 0
18 | 0 | BQ-069 |  |  | 14 | 15 | 15 | 0 | 0
18 | 0 | BQ-069 |  |  | 14 | 15 | 15 | 0 | 0
18 | 0 | BQ-069 |  |  | 14 | 15 | 15 | 0 | 0
18 | 0 | BQ-069 |  |  | 14 | 15 | 15 | 0 | 0
18 | 0 | BQ-069 |  |  | 14 | 15 | 15 | 0 | 0
18 | 0 | BQ-069 |  |  | 14 | 15 | 15 | 0 | 0
19 | 1 | BQ-070 |  |  | 14 | 15 | 15 | 0 | 0
19 | 0 | BQ-070 |  |  | 14 | 15 | 15 | 0 | 0
19 | 0 | BQ-070 |  |  | 14 | 15 | 15 | 0 | 0
19 | 0 | BQ-070 | INVOICE | 26 | 14 | 15 | 15 | 3885 | 0
19 | 0 | BQ-070 |  |  | 14 | 15 | 15 | 0 | 0
19 | 0 | BQ-070 | INVOICE | 28 | 14 | 15 | 15 | 388.5 | 0
19 | 0 | BQ-070 |  |  | 14 | 15 | 15 | 0 | 0
19 | 0 | BQ-070 | INVOICE | 32 | 14 | 15 | 15 | 166.5 | 0
19 | 0 | BQ-070 |  |  | 14 | 15 | 15 | 0 | 0
19 | 0 | BQ-070 | OVERALL |  | 14 | 15 | 15 | 0 | 4440
19 | 0 | BQ-070 |  |  | 14 | 15 | 15 | 0 | 0
19 | 0 | BQ-070 |  |  | 14 | 15 | 15 | 0 | 0
19 | 0 | BQ-070 |  |  | 14 | 15 | 15 | 0 | 0
19 | 0 | BQ-070 |  |  | 14 | 15 | 15 | 0 | 0
19 | 0 | BQ-070 |  |  | 14 | 15 | 15 | 0 | 0
19 | 0 | BQ-070 |  |  | 14 | 15 | 15 | 0 | 0
19 | 0 | BQ-070 |  |  | 14 | 15 | 15 | 0 | 0
19 | 0 | BQ-070 |  |  | 14 | 15 | 15 | 0 | 0
20 | 1 | BQ-071 |  |  | 14 | 15 | 15 | 0 | 0
20 | 0 | BQ-071 |  |  | 14 | 15 | 15 | 0 | 0
20 | 0 | BQ-071 |  |  | 14 | 15 | 15 | 0 | 0
20 | 0 | BQ-071 | INVOICE | 27 | 14 | 15 | 15 | 3312 | 0
20 | 0 | BQ-071 |  |  | 14 | 15 | 15 | 0 | 0
20 | 0 | BQ-071 | INVOICE | 28 | 14 | 15 | 15 | 368 | 0
20 | 0 | BQ-071 |  |  | 14 | 15 | 15 | 0 | 0
20 | 0 | BQ-071 | OVERALL |  | 14 | 15 | 15 | 0 | 3680
20 | 0 | BQ-071 |  |  | 14 | 15 | 15 | 0 | 0
20 | 0 | BQ-071 |  |  | 14 | 15 | 15 | 0 | 0
20 | 0 | BQ-071 |  |  | 14 | 15 | 15 | 0 | 0
20 | 0 | BQ-071 |  |  | 14 | 15 | 15 | 0 | 0
20 | 0 | BQ-071 |  |  | 14 | 15 | 15 | 0 | 0
20 | 0 | BQ-071 |  |  | 14 | 15 | 15 | 0 | 0
20 | 0 | BQ-071 |  |  | 14 | 15 | 15 | 0 | 0
20 | 0 | BQ-071 |  |  | 14 | 15 | 15 | 0 | 0
21 | 1 | BQ-072 |  |  | 14 | 15 | 15 | 0 | 0
21 | 0 | BQ-072 |  |  | 14 | 15 | 15 | 0 | 0
21 | 0 | BQ-072 |  |  | 14 | 15 | 15 | 0 | 0
21 | 0 | BQ-072 | INVOICE | 27 | 14 | 15 | 15 | 3312 | 0
21 | 0 | BQ-072 |  |  | 14 | 15 | 15 | 0 | 0
21 | 0 | BQ-072 | INVOICE | 28 | 14 | 15 | 15 | 368 | 0
21 | 0 | BQ-072 |  |  | 14 | 15 | 15 | 0 | 0
21 | 0 | BQ-072 | OVERALL |  | 14 | 15 | 15 | 0 | 3680
21 | 0 | BQ-072 |  |  | 14 | 15 | 15 | 0 | 0
21 | 0 | BQ-072 |  |  | 14 | 15 | 15 | 0 | 0
21 | 0 | BQ-072 |  |  | 14 | 15 | 15 | 0 | 0
21 | 0 | BQ-072 |  |  | 14 | 15 | 15 | 0 | 0
21 | 0 | BQ-072 |  |  | 14 | 15 | 15 | 0 | 0
21 | 0 | BQ-072 |  |  | 14 | 15 | 15 | 0 | 0
21 | 0 | BQ-072 |  |  | 14 | 15 | 15 | 0 | 0
21 | 0 | BQ-072 |  |  | 14 | 15 | 15 | 0 | 0
22 | 1 | BQ-073 |  |  | 14 | 15 | 15 | 0 | 0
22 | 0 | BQ-073 |  |  | 14 | 15 | 15 | 0 | 0
22 | 0 | BQ-073 |  |  | 14 | 15 | 15 | 0 | 0
22 | 0 | BQ-073 | INVOICE | 0 | 14 | 15 | 15 | 0 | 0
22 | 0 | BQ-073 |  |  | 14 | 15 | 15 | 0 | 0
22 | 0 | BQ-073 | OVERALL |  | 14 | 15 | 15 | 0 | 0
22 | 0 | BQ-073 |  |  | 14 | 15 | 15 | 0 | 0
22 | 0 | BQ-073 |  |  | 14 | 15 | 15 | 0 | 0
22 | 0 | BQ-073 |  |  | 14 | 15 | 15 | 0 | 0
22 | 0 | BQ-073 |  |  | 14 | 15 | 15 | 0 | 0
22 | 0 | BQ-073 |  |  | 14 | 15 | 15 | 0 | 0
22 | 0 | BQ-073 |  |  | 14 | 15 | 15 | 0 | 0
22 | 0 | BQ-073 |  |  | 14 | 15 | 15 | 0 | 0
22 | 0 | BQ-073 |  |  | 14 | 15 | 15 | 0 | 0
23 | 1 | BQ-074 |  |  | 14 | 15 | 15 | 0 | 0
23 | 0 | BQ-074 |  |  | 14 | 15 | 15 | 0 | 0
23 | 0 | BQ-074 |  |  | 14 | 15 | 15 | 0 | 0
23 | 0 | BQ-074 | INVOICE | 17 | 14 | 15 | 15 | 45430 | 0
23 | 0 | BQ-074 |  |  | 14 | 15 | 15 | 0 | 0
23 | 0 | BQ-074 | INVOICE | 19 | 14 | 15 | 15 | 20650 | 0
23 | 0 | BQ-074 |  |  | 14 | 15 | 15 | 0 | 0
23 | 0 | BQ-074 | INVOICE | 29 | 14 | 15 | 15 | 8260 | 0
23 | 0 | BQ-074 |  |  | 14 | 15 | 15 | 0 | 0
23 | 0 | BQ-074 | INVOICE | 30 | 14 | 15 | 15 | 8260 | 0
23 | 0 | BQ-074 |  |  | 14 | 15 | 15 | 0 | 0
23 | 0 | BQ-074 |  |  | 14 | 15 | 15 | 0 | 0
23 | 0 | BQ-074 |  |  | 14 | 15 | 15 | 0 | 0
23 | 0 | BQ-074 | OVERALL |  | 14 | 15 | 15 | 0 | 82600
23 | 0 | BQ-074 |  |  | 14 | 13 | 14 | 0 | 0
23 | 0 | BQ-074 |  |  | 14 | 13 | 14 | 0 | 0
23 | 0 | BQ-074 |  |  | 14 | 13 | 14 | 0 | 0
23 | 0 | BQ-074 |  |  | 14 | 13 | 14 | 0 | 0
23 | 0 | BQ-074 |  |  | 14 | 13 | 14 | 0 | 0
23 | 0 | BQ-074 |  |  | 14 | 13 | 14 | 0 | 0
23 | 0 | BQ-074 |  |  | 14 | 13 | 14 | 0 | 0
23 | 0 | BQ-074 |  |  | 14 | 13 | 14 | 0 | 0
23 | 0 | BQ-074 |  |  | 14 | 13 | 14 | 0 | 0
24 | 1 | BQ-075 |  |  | 12 | 13 | 13 | 0 | 0
24 | 0 | BQ-075 |  |  | 12 | 13 | 13 | 0 | 0
24 | 0 | BQ-075 |  |  | 12 | 13 | 13 | 0 | 0
24 | 0 | BQ-075 | INVOICE | 17 | 12 | 13 | 13 | 15675 | 0
24 | 0 | BQ-075 |  |  | 12 | 13 | 13 | 0 | 0
24 | 0 | BQ-075 | INVOICE | 18 | 12 | 13 | 13 | 7125 | 0
24 | 0 | BQ-075 |  |  | 12 | 13 | 13 | 0 | 0
24 | 0 | BQ-075 | INVOICE | 27 | 12 | 13 | 13 | 2850 | 0
24 | 0 | BQ-075 |  |  | 12 | 13 | 13 | 0 | 0
24 | 0 | BQ-075 | INVOICE | 28 | 12 | 13 | 13 | 2850 | 0
24 | 0 | BQ-075 |  |  | 12 | 13 | 13 | 0 | 0
24 | 0 | BQ-075 | INVOICE | 29 | 12 | 13 | 13 | -2850 | 0
24 | 0 | BQ-075 |  |  | 12 | 13 | 13 | 0 | 0
24 | 0 | BQ-075 | INVOICE | 30 | 12 | 13 | 13 | 2850 | 0
24 | 0 | BQ-075 |  |  | 12 | 13 | 13 | 0 | 0
24 | 0 | BQ-075 | OVERALL |  | 12 | 13 | 13 | 0 | 28500
24 | 0 | BQ-075 |  |  | 12 | 13 | 13 | 0 | 0
24 | 0 | BQ-075 |  |  | 12 | 13 | 13 | 0 | 0
24 | 0 | BQ-075 |  |  | 12 | 13 | 13 | 0 | 0
24 | 0 | BQ-075 |  |  | 12 | 13 | 13 | 0 | 0
24 | 0 | BQ-075 |  |  | 12 | 13 | 13 | 0 | 0
24 | 0 | BQ-075 |  |  | 12 | 13 | 13 | 0 | 0
24 | 0 | BQ-075 |  |  | 12 | 13 | 13 | 0 | 0
24 | 0 | BQ-075 |  |  | 12 | 13 | 13 | 0 | 0
25 | 1 | BQ-076 |  |  | 12 | 13 | 13 | 0 | 0
25 | 0 | BQ-076 |  |  | 12 | 13 | 13 | 0 | 0
25 | 0 | BQ-076 |  |  | 12 | 13 | 13 | 0 | 0
25 | 0 | BQ-076 | INVOICE | 17 | 12 | 13 | 13 | 12490.5 | 0
25 | 0 | BQ-076 |  |  | 12 | 13 | 13 | 0 | 0
25 | 0 | BQ-076 | INVOICE | 18 | 12 | 13 | 13 | 5677.5 | 0
25 | 0 | BQ-076 |  |  | 12 | 13 | 13 | 0 | 0
25 | 0 | BQ-076 | INVOICE | 27 | 12 | 13 | 13 | 2271 | 0
25 | 0 | BQ-076 |  |  | 12 | 13 | 13 | 0 | 0
25 | 0 | BQ-076 | INVOICE | 28 | 12 | 13 | 13 | 2271 | 0
25 | 0 | BQ-076 |  |  | 12 | 13 | 13 | 0 | 0
25 | 0 | BQ-076 | INVOICE | 29 | 12 | 13 | 13 | -2271 | 0
25 | 0 | BQ-076 |  |  | 12 | 13 | 13 | 0 | 0
25 | 0 | BQ-076 | INVOICE | 30 | 12 | 13 | 13 | 2271 | 0
25 | 0 | BQ-076 |  |  | 12 | 13 | 13 | 0 | 0
25 | 0 | BQ-076 | OVERALL |  | 12 | 13 | 13 | 0 | 22710
25 | 0 | BQ-076 |  |  | 12 | 15 | 15 | 0 | 0
25 | 0 | BQ-076 |  |  | 12 | 15 | 15 | 0 | 0
25 | 0 | BQ-076 |  |  | 12 | 15 | 15 | 0 | 0
25 | 0 | BQ-076 |  |  | 12 | 15 | 15 | 0 | 0
25 | 0 | BQ-076 |  |  | 12 | 15 | 15 | 0 | 0
25 | 0 | BQ-076 |  |  | 12 | 15 | 15 | 0 | 0
25 | 0 | BQ-076 |  |  | 12 | 15 | 15 | 0 | 0
25 | 0 | BQ-076 |  |  | 12 | 15 | 15 | 0 | 0
26 | 1 | BQ-077 |  |  | 14 | 15 | 15 | 0 | 0
26 | 0 | BQ-077 |  |  | 14 | 15 | 15 | 0 | 0
26 | 0 | BQ-077 |  |  | 14 | 15 | 15 | 0 | 0
26 | 0 | BQ-077 | INVOICE | 14 | 14 | 15 | 15 | 154 | 0
26 | 0 | BQ-077 |  |  | 14 | 15 | 15 | 0 | 0
26 | 0 | BQ-077 | INVOICE | 32 | 14 | 15 | 15 | 22 | 0
26 | 0 | BQ-077 |  |  | 14 | 15 | 15 | 0 | 0
26 | 0 | BQ-077 | OVERALL |  | 14 | 15 | 15 | 0 | 176
26 | 0 | BQ-077 |  |  | 14 | 20 | 20 | 0 | 0
26 | 0 | BQ-077 |  |  | 14 | 20 | 20 | 0 | 0
26 | 0 | BQ-077 |  |  | 14 | 20 | 20 | 0 | 0
26 | 0 | BQ-077 |  |  | 14 | 20 | 20 | 0 | 0
26 | 0 | BQ-077 |  |  | 14 | 20 | 20 | 0 | 0
26 | 0 | BQ-077 |  |  | 14 | 20 | 20 | 0 | 0
26 | 0 | BQ-077 |  |  | 14 | 20 | 20 | 0 | 0
26 | 0 | BQ-077 |  |  | 14 | 20 | 20 | 0 | 0
27 | 1 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 | INVOICE | 6 | 19 | 20 | 20 | 277078.75 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 | INVOICE | 8 | 19 | 20 | 20 | 436751.25 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 | INVOICE | 11 | 19 | 20 | 20 | 592450 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 | INVOICE | 13 | 19 | 20 | 20 | 231200 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 | INVOICE | 14 | 19 | 20 | 20 | 131784 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 | INVOICE | 17 | 19 | 20 | 20 | 39015 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 | INVOICE | 18 | 19 | 20 | 20 | 18785 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 | INVOICE | 20 | 19 | 20 | 20 | 27455 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 | INVOICE | 21 | 19 | 20 | 20 | 46240 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 | INVOICE | 22 | 19 | 20 | 20 | 34680 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 | INVOICE | 23 | 19 | 20 | 20 | 104618 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 | INVOICE | 24 | 19 | 20 | 20 | 77452 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 | INVOICE | 25 | 19 | 20 | 20 | 46818 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 | INVOICE | 26 | 19 | 20 | 20 | 118345.5 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 | INVOICE | 27 | 19 | 20 | 20 | 240014.5 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 | INVOICE | 28 | 19 | 20 | 20 | 72250 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 | INVOICE | 29 | 19 | 20 | 20 | 43350 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 | INVOICE | 31 | 19 | 20 | 20 | 289000 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 | INVOICE | 32 | 19 | 20 | 20 | 48263 | 0
27 | 0 | BQ-078 |  |  | 19 | 20 | 20 | 0 | 0
27 | 0 | BQ-078 | OVERALL |  | 19 | 20 | 20 | 0 | 2875550
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
27 | 0 | BQ-078 |  |  | 19 | 16 | 19 | 0 | 0
28 | 1 | BQ-079 |  |  | 15 | 16 | 16 | 0 | 0
28 | 0 | BQ-079 |  |  | 15 | 16 | 16 | 0 | 0
28 | 0 | BQ-079 |  |  | 15 | 16 | 16 | 0 | 0
28 | 0 | BQ-079 | INVOICE | 25 | 15 | 16 | 16 | 12045 | 0
28 | 0 | BQ-079 |  |  | 15 | 16 | 16 | 0 | 0
28 | 0 | BQ-079 | INVOICE | 28 | 15 | 16 | 16 | 3832.5 | 0
28 | 0 | BQ-079 |  |  | 15 | 16 | 16 | 0 | 0
28 | 0 | BQ-079 | INVOICE | 30 | 15 | 16 | 16 | 7482.5 | 0
28 | 0 | BQ-079 |  |  | 15 | 16 | 16 | 0 | 0
28 | 0 | BQ-079 |  |  | 15 | 16 | 16 | 0 | 0
28 | 0 | BQ-079 |  |  | 15 | 16 | 16 | 0 | 0
28 | 0 | BQ-079 |  |  | 15 | 16 | 16 | 0 | 0
28 | 0 | BQ-079 |  |  | 15 | 16 | 16 | 0 | 0
28 | 0 | BQ-079 | OVERALL |  | 15 | 16 | 16 | 0 | 23360
28 | 0 | BQ-079 |  |  | 15 | #REF! | #REF! | 0 | 0
28 | 0 | BQ-079 |  |  | 15 | #REF! | #REF! | 0 | 0
28 | 0 | BQ-079 |  |  | 15 | #REF! | #REF! | 0 | 0
28 | 0 | BQ-079 |  |  | 15 | #REF! | #REF! | 0 | 0
28 | 0 | BQ-079 |  |  | 15 | #REF! | #REF! | 0 | 0
28 | 0 | BQ-079 |  |  | 15 | #REF! | #REF! | 0 | 0
28 | 0 | BQ-079 |  |  | 15 | #REF! | #REF! | 0 | 0
28 | 0 | BQ-079 |  |  | 15 | #REF! | #REF! | 0 | 0
29 | 1 | BQ-080 |  |  | 15 | #REF! | #REF! | 0 | 0
29 | 0 | BQ-080 |  |  | 15 | #REF! | #REF! | 0 | 0
29 | 0 | BQ-080 |  |  | 15 | #REF! | #REF! | 0 | 0
29 | 0 | BQ-080 | INVOICE | 15 | 15 | #REF! | #REF! | #REF! | 0
29 | 0 | BQ-080 |  |  | 15 | #REF! | #REF! | 0 | 0
29 | 0 | BQ-080 | INVOICE | 30 | 15 | #REF! | #REF! | #REF! | 0
29 | 0 | BQ-080 |  |  | 15 | #REF! | #REF! | 0 | 0
29 | 0 | BQ-080 | INVOICE | 33 | 15 | #REF! | #REF! | #REF! | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | #REF! | 16 | #REF! | 0 | 0
#REF! | #REF! | #REF! | OVERALL |  | #REF! | 16 | #REF! | 0 | 101120
#REF! | 0 | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | 1 | BQ-081 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-081 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-081 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-081 | INVOICE | 15 | 14 | 15 | 15 | 669840 | 0
#REF! | 0 | BQ-081 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-081 | INVOICE | 25 | 14 | 15 | 15 | 133968 | 0
#REF! | 0 | BQ-081 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-081 | INVOICE | 33 | 14 | 15 | 15 | 22328 | 0
#REF! | 0 | BQ-081 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-081 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-081 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-081 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-081 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-081 | OVERALL |  | 14 | 15 | 15 | 0 | 826136
#REF! | 0 | BQ-081 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-081 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-081 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-081 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-081 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-081 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-081 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-081 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-082 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-082 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-082 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-082 | INVOICE | 15 | 14 | 15 | 15 | 501120 | 0
#REF! | 0 | BQ-082 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-082 | INVOICE | 25 | 14 | 15 | 15 | 100224 | 0
#REF! | 0 | BQ-082 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-082 | INVOICE | 33 | 14 | 15 | 15 | 16704 | 0
#REF! | 0 | BQ-082 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-082 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-082 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-082 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-082 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-082 | OVERALL |  | 14 | 15 | 15 | 0 | 618048
#REF! | 0 | BQ-082 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-082 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-082 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-082 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-082 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-082 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-082 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-082 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-083 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-083 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-083 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-083 | INVOICE | 15 | 14 | 15 | 15 | 298800 | 0
#REF! | 0 | BQ-083 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-083 | INVOICE | 25 | 14 | 15 | 15 | 59760 | 0
#REF! | 0 | BQ-083 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-083 | INVOICE | 33 | 14 | 15 | 15 | 9960 | 0
#REF! | 0 | BQ-083 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-083 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-083 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-083 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-083 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-083 | OVERALL |  | 14 | 15 | 15 | 0 | 368520
#REF! | 0 | BQ-083 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-083 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-083 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-083 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-083 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-083 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-083 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-083 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-084 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-084 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-084 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-084 | INVOICE | 15 | 14 | 15 | 15 | 225900 | 0
#REF! | 0 | BQ-084 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-084 | INVOICE | 25 | 14 | 15 | 15 | 45180 | 0
#REF! | 0 | BQ-084 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-084 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-084 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-084 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-084 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-084 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-084 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-084 | OVERALL |  | 14 | 15 | 15 | 0 | 271080
#REF! | 0 | BQ-084 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-084 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-084 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-084 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-084 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-084 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-084 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-084 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-085 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-085 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-085 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-085 | INVOICE | 15 | 16 | 16 | 16 | 292600 | 0
#REF! | 0 | BQ-085 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-085 | INVOICE | 25 | 16 | 16 | 16 | 86450 | 0
#REF! | 0 | BQ-085 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-085 | INVOICE | 33 | 16 | 16 | 16 | 33250 | 0
#REF! | 0 | BQ-085 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-085 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-085 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-085 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-085 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-085 | OVERALL |  | 16 | 16 | 16 | 0 | 412300
#REF! | 0 | BQ-085 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-085 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-085 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-085 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-085 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-085 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-085 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-085 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 2 | 17 | 16 | 17 | 3785100 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 3 | 17 | 16 | 17 | 2118028 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 4 | 17 | 16 | 17 | 792022 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 6 | 17 | 16 | 17 | 7326 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 10 | 17 | 16 | 17 | 247900 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 11 | 17 | 16 | 17 | 796680.9172 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 12 | 17 | 16 | 17 | 372035 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 13 | 17 | 16 | 17 | 242442.5 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 14 | 17 | 16 | 17 | 341343.5 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 15 | 17 | 16 | 17 | 307285 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 16 | 17 | 16 | 17 | 277833 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 17 | 17 | 16 | 17 | 96200 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 18 | 17 | 16 | 17 | 47156.5 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 19 | 17 | 16 | 17 | 38073 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 21 | 17 | 16 | 17 | 22866 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 22 | 17 | 16 | 17 | 292059.5 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 23 | 17 | 16 | 17 | 228438 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 24 | 17 | 16 | 17 | 134643 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 25 | 17 | 16 | 17 | 18777.5 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 26 | 17 | 16 | 17 | 10770.0828 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 27 | 17 | 16 | 17 | 2421132 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 28 | 17 | 16 | 17 | 112807.45 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 30 | 17 | 16 | 17 | 672364 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | INVOICE | 32 | 17 | 16 | 17 | 4704.55 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 | OVERALL |  | 17 | 16 | 17 | 0 | 13486407.5
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-086 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 1 | BQ-087 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-087 | INVOICE | 3 | 15 | 16 | 16 | 1379224 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-087 | INVOICE | 6 | 15 | 16 | 16 | 552552 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-087 | INVOICE | 17 | 15 | 16 | 16 | 97020 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-087 | INVOICE | 18 | 15 | 16 | 16 | 69300 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-087 | INVOICE | 19 | 15 | 16 | 16 | 2800 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-087 | INVOICE | 20 | 15 | 16 | 16 | 11340 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-087 | INVOICE | 21 | 15 | 16 | 16 | 155260 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-087 | INVOICE | 22 | 15 | 16 | 16 | 87752 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-087 | INVOICE | 23 | 15 | 16 | 16 | 96740 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-087 | INVOICE | 24 | 15 | 16 | 16 | 62608 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-087 | INVOICE | 25 | 15 | 16 | 16 | 11102 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-087 | INVOICE | 26 | 15 | 16 | 16 | 7308 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-087 | INVOICE | 27 | 15 | 16 | 16 | 940506 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-087 | INVOICE | 28 | 15 | 16 | 16 | 163464 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-087 | INVOICE | 30 | 15 | 16 | 16 | 116984 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-087 | INVOICE | 31 | 15 | 16 | 16 | 385364 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-087 | INVOICE | 32 | 15 | 16 | 16 | 156632 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-087 | OVERALL |  | 15 | 16 | 16 | 0 | 4552632
#REF! | 0 | BQ-087 |  |  | 15 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-087 |  |  | 15 | 20 | 20 | 0 | 0
#REF! | 1 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 | INVOICE | 5 | 19 | 20 | 20 | 27694.875 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 | INVOICE | 6 | 19 | 20 | 20 | 82387.5 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 | INVOICE | 7 | 19 | 20 | 20 | 182731.25 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 | INVOICE | 8 | 19 | 20 | 20 | 358068.75 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 | INVOICE | 9 | 19 | 20 | 20 | 197681.25 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 | INVOICE | 10 | 19 | 20 | 20 | 117975 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 | INVOICE | 11 | 19 | 20 | 20 | 66551.875 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 | INVOICE | 13 | 19 | 20 | 20 | 576886.375 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 | INVOICE | 14 | 19 | 20 | 20 | 31720 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 | INVOICE | 16 | 19 | 20 | 20 | 420720.625 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 | INVOICE | 17 | 19 | 20 | 20 | 209982.5 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 | INVOICE | 24 | 19 | 20 | 20 | 284050 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 | INVOICE | 27 | 19 | 20 | 20 | 253890 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 | INVOICE | 30 | 19 | 20 | 20 | 312260 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 | INVOICE | 31 | 19 | 20 | 20 | 168577.5 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 | INVOICE | 32 | 19 | 20 | 20 | 57671.25 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 | OVERALL |  | 19 | 20 | 20 | 0 | 3442010
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-088 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 1 | BQ-089 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-089 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-089 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-089 | INVOICE | 23 | 19 | 20 | 20 | 20800 | 0
#REF! | 0 | BQ-089 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-089 | INVOICE | 24 | 19 | 20 | 20 | 670800 | 0
#REF! | 0 | BQ-089 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-089 | INVOICE | 25 | 19 | 20 | 20 | 410978.75 | 0
#REF! | 0 | BQ-089 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-089 | INVOICE | 26 | 19 | 20 | 20 | 763571.25 | 0
#REF! | 0 | BQ-089 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-089 | INVOICE | 27 | 19 | 20 | 20 | 201825 | 0
#REF! | 0 | BQ-089 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-089 | INVOICE | 30 | 19 | 20 | 20 | 229775 | 0
#REF! | 0 | BQ-089 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-089 | INVOICE | 32 | 19 | 20 | 20 | 12431.25 | 0
#REF! | 0 | BQ-089 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-089 | OVERALL |  | 19 | 20 | 20 | 0 | 2341625
#REF! | 0 | BQ-089 |  |  | 19 | 18 | 19 | 0 | 0
#REF! | 0 | BQ-089 |  |  | 19 | 18 | 19 | 0 | 0
#REF! | 0 | BQ-089 |  |  | 19 | 18 | 19 | 0 | 0
#REF! | 0 | BQ-089 |  |  | 19 | 18 | 19 | 0 | 0
#REF! | 0 | BQ-089 |  |  | 19 | 18 | 19 | 0 | 0
#REF! | 0 | BQ-089 |  |  | 19 | 18 | 19 | 0 | 0
#REF! | 0 | BQ-089 |  |  | 19 | 18 | 19 | 0 | 0
#REF! | 0 | BQ-089 |  |  | 19 | 18 | 19 | 0 | 0
#REF! | 1 | BQ-090 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-090 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-090 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-090 | INVOICE | 16 | 17 | 18 | 18 | 137760 | 0
#REF! | 0 | BQ-090 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-090 | INVOICE | 23 | 17 | 18 | 18 | 413280 | 0
#REF! | 0 | BQ-090 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-090 | INVOICE | 27 | 17 | 18 | 18 | 15744 | 0
#REF! | 0 | BQ-090 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-090 | INVOICE | 30 | 17 | 18 | 18 | 39360 | 0
#REF! | 0 | BQ-090 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-090 | INVOICE | 32 | 17 | 18 | 18 | 15744 | 0
#REF! | 0 | BQ-090 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-090 | OVERALL |  | 17 | 18 | 18 | 0 | 621888
#REF! | 0 | BQ-090 |  |  | 17 | 21 | 21 | 0 | 0
#REF! | 0 | BQ-090 |  |  | 17 | 21 | 21 | 0 | 0
#REF! | 0 | BQ-090 |  |  | 17 | 21 | 21 | 0 | 0
#REF! | 0 | BQ-090 |  |  | 17 | 21 | 21 | 0 | 0
#REF! | 0 | BQ-090 |  |  | 17 | 21 | 21 | 0 | 0
#REF! | 0 | BQ-090 |  |  | 17 | 21 | 21 | 0 | 0
#REF! | 0 | BQ-090 |  |  | 17 | 21 | 21 | 0 | 0
#REF! | 0 | BQ-090 |  |  | 17 | 21 | 21 | 0 | 0
#REF! | 1 | BQ-091 |  |  | 20 | 21 | 21 | 0 | 0
#REF! | 0 | BQ-091 |  |  | 20 | 21 | 21 | 0 | 0
#REF! | 0 | BQ-091 |  |  | 20 | 21 | 21 | 0 | 0
#REF! | 0 | BQ-091 | INVOICE | 16 | 20 | 21 | 21 | 695296 | 0
#REF! | 0 | BQ-091 |  |  | 20 | 21 | 21 | 0 | 0
#REF! | 0 | BQ-091 | INVOICE | 27 | 20 | 21 | 21 | 10864 | 0
#REF! | 0 | BQ-091 |  |  | 20 | 21 | 21 | 0 | 0
#REF! | 0 | BQ-091 | INVOICE | 30 | 20 | 21 | 21 | 27160 | 0
#REF! | 0 | BQ-091 |  |  | 20 | 21 | 21 | 0 | 0
#REF! | 0 | BQ-091 | INVOICE | 32 | 20 | 21 | 21 | 184688 | 0
#REF! | 0 | BQ-091 |  |  | 20 | 21 | 21 | 0 | 0
#REF! | 0 | BQ-091 |  |  | 20 | 21 | 21 | 0 | 0
#REF! | 0 | BQ-091 |  |  | 20 | 21 | 21 | 0 | 0
#REF! | 0 | BQ-091 | OVERALL |  | 20 | 21 | 21 | 0 | 918008
#REF! | 0 | BQ-091 |  |  | 20 | 16 | 20 | 0 | 0
#REF! | 0 | BQ-091 |  |  | 20 | 16 | 20 | 0 | 0
#REF! | 0 | BQ-091 |  |  | 20 | 16 | 20 | 0 | 0
#REF! | 0 | BQ-091 |  |  | 20 | 16 | 20 | 0 | 0
#REF! | 0 | BQ-091 |  |  | 20 | 16 | 20 | 0 | 0
#REF! | 0 | BQ-091 |  |  | 20 | 16 | 20 | 0 | 0
#REF! | 0 | BQ-091 |  |  | 20 | 16 | 20 | 0 | 0
#REF! | 0 | BQ-091 |  |  | 20 | 16 | 20 | 0 | 0
#REF! | 1 | BQ-092 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-092 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-092 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-092 | INVOICE | 12 | 15 | 16 | 16 | 147793.8 | 0
#REF! | 0 | BQ-092 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-092 | INVOICE | 13 | 15 | 16 | 16 | 95010.3 | 0
#REF! | 0 | BQ-092 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-092 | INVOICE | 27 | 15 | 16 | 16 | 159470.15 | 0
#REF! | 0 | BQ-092 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-092 | INVOICE | 28 | 15 | 16 | 16 | 7197.75 | 0
#REF! | 0 | BQ-092 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-092 | INVOICE | 29 | 15 | 16 | 16 | 4798.5 | 0
#REF! | 0 | BQ-092 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-092 | INVOICE | 32 | 15 | 16 | 16 | 17994.375 | 0
#REF! | 0 | BQ-092 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-092 | OVERALL |  | 15 | 16 | 16 | 0 | 432264.875
#REF! | 0 | BQ-092 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-092 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-092 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-092 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-092 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-092 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-092 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-092 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-093 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-093 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-093 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-093 | INVOICE | 12 | 15 | 16 | 16 | 18480 | 0
#REF! | 0 | BQ-093 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-093 | INVOICE | 13 | 15 | 16 | 16 | 60060 | 0
#REF! | 0 | BQ-093 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-093 | INVOICE | 27 | 15 | 16 | 16 | -6930 | 0
#REF! | 0 | BQ-093 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-093 | INVOICE | 28 | 15 | 16 | 16 | 9240 | 0
#REF! | 0 | BQ-093 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-093 | INVOICE | 29 | 15 | 16 | 16 | 4410 | 0
#REF! | 0 | BQ-093 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-093 | INVOICE | 32 | 15 | 16 | 16 | 70770 | 0
#REF! | 0 | BQ-093 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-093 | OVERALL |  | 15 | 16 | 16 | 0 | 159180
#REF! | 0 | BQ-093 |  |  | 15 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-093 |  |  | 15 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-093 |  |  | 15 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-093 |  |  | 15 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-093 |  |  | 15 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-093 |  |  | 15 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-093 |  |  | 15 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-093 |  |  | 15 | 23 | 23 | 0 | 0
#REF! | 1 | BQ-094 |  |  | 22 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-094 | INVOICE | 9 | 22 | 23 | 23 | 763111.8 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-094 | INVOICE | 14 | 22 | 23 | 23 | 356118.84 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-094 | INVOICE | 17 | 22 | 23 | 23 | 23685.75 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-094 | INVOICE | 18 | 22 | 23 | 23 | 16747.5 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-094 | INVOICE | 19 | 22 | 23 | 23 | 29188.5 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-094 | INVOICE | 20 | 22 | 23 | 23 | 211910.25 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-094 | INVOICE | 21 | 22 | 23 | 23 | 19335.75 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-094 | INVOICE | 22 | 22 | 23 | 23 | 312288.24 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-094 | INVOICE | 23 | 22 | 23 | 23 | 319398.75 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-094 | INVOICE | 24 | 22 | 23 | 23 | 381425.4 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-094 | INVOICE | 25 | 22 | 23 | 23 | 66990 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-094 | INVOICE | 26 | 22 | 23 | 23 | 202797.87 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-094 | INVOICE | 27 | 22 | 23 | 23 | 761993.85 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-094 | INVOICE | 28 | 22 | 23 | 23 | 34256.25 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-094 | INVOICE | 29 | 22 | 23 | 23 | 53505 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-094 | INVOICE | 32 | 22 | 23 | 23 | 408030 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 23 | 23 | 0 | 0
#REF! | 0 | BQ-094 | OVERALL |  | 22 | 23 | 23 | 0 | 4048653.75
#REF! | 0 | BQ-094 |  |  | 22 | 19 | 22 | 0 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 19 | 22 | 0 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 19 | 22 | 0 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 19 | 22 | 0 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 19 | 22 | 0 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 19 | 22 | 0 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 19 | 22 | 0 | 0
#REF! | 0 | BQ-094 |  |  | 22 | 19 | 22 | 0 | 0
#REF! | 1 | BQ-095 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-095 | INVOICE | 17 | 18 | 19 | 19 | 12334.52 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-095 | INVOICE | 18 | 18 | 19 | 19 | 3265.02 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-095 | INVOICE | 19 | 18 | 19 | 19 | 11608.96 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-095 | INVOICE | 20 | 18 | 19 | 19 | 56874.01 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-095 | INVOICE | 21 | 18 | 19 | 19 | 247.35 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-095 | INVOICE | 22 | 18 | 19 | 19 | 26120.16 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-095 | INVOICE | 23 | 18 | 19 | 19 | 54862.23 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-095 | INVOICE | 24 | 18 | 19 | 19 | 20777.4 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-095 | INVOICE | 25 | 18 | 19 | 19 | 659.6 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-095 | INVOICE | 26 | 18 | 19 | 19 | 17223.805 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-095 | INVOICE | 27 | 18 | 19 | 19 | 10603.07 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-095 | INVOICE | 32 | 18 | 19 | 19 | 28486.475 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-095 | OVERALL |  | 18 | 19 | 19 | 0 | 243062.6
#REF! | 0 | BQ-095 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-095 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 1 | BQ-096 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-096 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-096 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-096 | INVOICE | 15 | 16 | 17 | 17 | 110940 | 0
#REF! | 0 | BQ-096 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-096 | INVOICE | 20 | 16 | 17 | 17 | 9245 | 0
#REF! | 0 | BQ-096 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-096 | INVOICE | 24 | 16 | 17 | 17 | 16271.2 | 0
#REF! | 0 | BQ-096 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-096 | INVOICE | 25 | 16 | 17 | 17 | 813.56 | 0
#REF! | 0 | BQ-096 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-096 | INVOICE | 27 | 16 | 17 | 17 | 29879.84 | 0
#REF! | 0 | BQ-096 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-096 | INVOICE | 28 | 16 | 17 | 17 | 1420.032 | 0
#REF! | 0 | BQ-096 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-096 | INVOICE | 32 | 16 | 17 | 17 | 7603.088 | 0
#REF! | 0 | BQ-096 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-096 | OVERALL |  | 16 | 17 | 17 | 0 | 176172.72
#REF! | 0 | BQ-096 |  |  | 16 | 14 | 16 | 0 | 0
#REF! | 0 | BQ-096 |  |  | 16 | 14 | 16 | 0 | 0
#REF! | 0 | BQ-096 |  |  | 16 | 14 | 16 | 0 | 0
#REF! | 0 | BQ-096 |  |  | 16 | 14 | 16 | 0 | 0
#REF! | 0 | BQ-096 |  |  | 16 | 14 | 16 | 0 | 0
#REF! | 0 | BQ-096 |  |  | 16 | 14 | 16 | 0 | 0
#REF! | 0 | BQ-096 |  |  | 16 | 14 | 16 | 0 | 0
#REF! | 0 | BQ-096 |  |  | 16 | 14 | 16 | 0 | 0
#REF! | 1 | BQ-097 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-097 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-097 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-097 | INVOICE | 15 | 13 | 14 | 14 | 1915488 | 0
#REF! | 0 | BQ-097 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-097 | INVOICE | 21 | 13 | 14 | 14 | 180928.8 | 0
#REF! | 0 | BQ-097 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-097 | INVOICE | 26 | 13 | 14 | 14 | 238975.2 | 0
#REF! | 0 | BQ-097 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-097 | INVOICE | 27 | 13 | 14 | 14 | 320436 | 0
#REF! | 0 | BQ-097 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-097 | INVOICE | 28 | 13 | 14 | 14 | 72090 | 0
#REF! | 0 | BQ-097 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-097 | INVOICE | 30 | 13 | 14 | 14 | 37800 | 0
#REF! | 0 | BQ-097 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-097 | INVOICE | 31 | 13 | 14 | 14 | 11988 | 0
#REF! | 0 | BQ-097 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-097 | OVERALL |  | 13 | 14 | 14 | 0 | 2814570
#REF! | 0 | BQ-097 |  |  | 13 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-097 |  |  | 13 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-097 |  |  | 13 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-097 |  |  | 13 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-097 |  |  | 13 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-097 |  |  | 13 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-097 |  |  | 13 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-097 |  |  | 13 | 13 | 13 | 0 | 0
#REF! | 1 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 | OVERALL |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-001 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 1 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 | OVERALL |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-002 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 1 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 | OVERALL |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-003 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 1 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 | OVERALL |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-004 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 1 | CR1-005 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-005 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-005 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-005 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-005 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-005 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-005 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-005 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-005 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-005 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-005 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-005 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-005 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-005 | OVERALL |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-005 |  |  | 12 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-005 |  |  | 12 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-005 |  |  | 12 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-005 |  |  | 12 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-005 |  |  | 12 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-005 |  |  | 12 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-005 |  |  | 12 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-005 |  |  | 12 | 17 | 17 | 0 | 0
#REF! | 1 | NBQ-006 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-006 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-006 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-006 | INVOICE | 27 | 16 | 17 | 17 | 1628 | 0
#REF! | 0 | NBQ-006 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-006 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-006 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-006 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-006 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-006 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-006 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-006 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-006 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-006 | OVERALL |  | 16 | 17 | 17 | 0 | 1628
#REF! | 0 | NBQ-006 |  |  | 16 | #REF! | #REF! | 0 | 0
#REF! | 0 | NBQ-006 |  |  | 16 | #REF! | #REF! | 0 | 0
#REF! | 0 | NBQ-006 |  |  | 16 | #REF! | #REF! | 0 | 0
#REF! | 0 | NBQ-006 |  |  | 16 | #REF! | #REF! | 0 | 0
#REF! | 0 | NBQ-006 |  |  | 16 | #REF! | #REF! | 0 | 0
#REF! | 0 | NBQ-006 |  |  | 16 | #REF! | #REF! | 0 | 0
#REF! | 0 | NBQ-006 |  |  | 16 | #REF! | #REF! | 0 | 0
#REF! | 0 | NBQ-006 |  |  | 16 | #REF! | #REF! | 0 | 0
#REF! | 1 | CR1-007 |  |  | 12 | #REF! | #REF! | 0 | 0
#REF! | 0 | CR1-007 |  |  | 12 | #REF! | #REF! | 0 | 0
#REF! | 0 | CR1-007 |  |  | 12 | #REF! | #REF! | 0 | 0
#REF! | 0 | CR1-007 | INVOICE | 33 | 12 | #REF! | #REF! | #REF! | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | #REF! | 13 | #REF! | 0 | 0
#REF! | #REF! | #REF! | OVERALL |  | #REF! | 13 | #REF! | 0 | 139200
#REF! | 0 | #REF! |  |  | #REF! | 16 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 16 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 16 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 16 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 16 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 16 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 16 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 16 | #REF! | 0 | 0
#REF! | 1 | BQ-098 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-098 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-098 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-098 | INVOICE | 13 | 15 | 16 | 16 | 14080 | 0
#REF! | 0 | BQ-098 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-098 | INVOICE | 31 | 15 | 16 | 16 | 5760 | 0
#REF! | 0 | BQ-098 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-098 | INVOICE | 32 | 15 | 16 | 16 | 640 | 0
#REF! | 0 | BQ-098 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-098 | OVERALL |  | 15 | 16 | 16 | 0 | 20480
#REF! | 0 | BQ-098 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-098 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-098 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-098 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-098 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-098 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-098 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-098 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 1 | BQ-099 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-099 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-099 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-099 | INVOICE | 17 | 18 | 19 | 19 | 1815 | 0
#REF! | 0 | BQ-099 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-099 | INVOICE | 18 | 18 | 19 | 19 | 363 | 0
#REF! | 0 | BQ-099 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-099 | INVOICE | 23 | 18 | 19 | 19 | 3267 | 0
#REF! | 0 | BQ-099 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-099 | INVOICE | 31 | 18 | 19 | 19 | 1650 | 0
#REF! | 0 | BQ-099 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-099 | INVOICE | 32 | 18 | 19 | 19 | -495 | 0
#REF! | 0 | BQ-099 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-099 | OVERALL |  | 18 | 19 | 19 | 0 | 6600
#REF! | 0 | BQ-099 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-099 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-099 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-099 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-099 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-099 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-099 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-099 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 1 | BQ-100 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-100 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-100 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-100 | INVOICE | 27 | 15 | 16 | 16 | 9240 | 0
#REF! | 0 | BQ-100 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-100 | INVOICE | 31 | 15 | 16 | 16 | 3780 | 0
#REF! | 0 | BQ-100 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-100 | INVOICE | 32 | 15 | 16 | 16 | 420 | 0
#REF! | 0 | BQ-100 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-100 | OVERALL |  | 15 | 16 | 16 | 0 | 13440
#REF! | 0 | BQ-100 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-100 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-100 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-100 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-100 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-100 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-100 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-100 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 1 | BQ-101 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-101 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-101 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-101 | INVOICE | 12 | 18 | 19 | 19 | 76769 | 0
#REF! | 0 | BQ-101 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-101 | INVOICE | 15 | 18 | 19 | 19 | 32901 | 0
#REF! | 0 | BQ-101 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-101 | INVOICE | 24 | 18 | 19 | 19 | 9970 | 0
#REF! | 0 | BQ-101 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-101 | INVOICE | 27 | 18 | 19 | 19 | -60318.5 | 0
#REF! | 0 | BQ-101 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-101 | INVOICE | 31 | 18 | 19 | 19 | 27417.5 | 0
#REF! | 0 | BQ-101 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-101 | INVOICE | 32 | 18 | 19 | 19 | 49351.5 | 0
#REF! | 0 | BQ-101 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-101 | OVERALL |  | 18 | 19 | 19 | 0 | 136090.5
#REF! | 0 | BQ-101 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-101 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-101 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-101 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-101 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-101 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-101 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-101 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 1 | BQ-102 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-102 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-102 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-102 | INVOICE | 15 | 16 | 17 | 17 | 20900 | 0
#REF! | 0 | BQ-102 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-102 | INVOICE | 27 | 16 | 17 | 17 | -10450 | 0
#REF! | 0 | BQ-102 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-102 | INVOICE | 31 | 16 | 17 | 17 | 7125 | 0
#REF! | 0 | BQ-102 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-102 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-102 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-102 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-102 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-102 | OVERALL |  | 16 | 17 | 17 | 0 | 17575
#REF! | 0 | BQ-102 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-102 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-102 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-102 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-102 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-102 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-102 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-102 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 1 | BQ-103 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-103 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-103 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-103 | INVOICE | 26 | 14 | 15 | 15 | 11880 | 0
#REF! | 0 | BQ-103 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-103 | INVOICE | 31 | 14 | 15 | 15 | 3780 | 0
#REF! | 0 | BQ-103 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-103 | OVERALL |  | 14 | 15 | 15 | 0 | 16740
#REF! | 0 | BQ-103 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-103 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-103 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-103 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-103 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-103 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-103 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-103 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 1 | BQ-104 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-104 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-104 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-104 | INVOICE | 20 | 16 | 17 | 17 | 124416 | 0
#REF! | 0 | BQ-104 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-104 | INVOICE | 25 | 16 | 17 | 17 | 145152 | 0
#REF! | 0 | BQ-104 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-104 | INVOICE | 26 | 16 | 17 | 17 | 145152 | 0
#REF! | 0 | BQ-104 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-104 | INVOICE | 27 | 16 | 17 | 17 | 82944 | 0
#REF! | 0 | BQ-104 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-104 | INVOICE | 29 | 16 | 17 | 17 | 27648 | 0
#REF! | 0 | BQ-104 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-104 | INVOICE | 30 | 16 | 17 | 17 | 13824 | 0
#REF! | 0 | BQ-104 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-104 | OVERALL |  | 16 | 17 | 17 | 0 | 539136
#REF! | 0 | BQ-104 |  |  | 16 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-104 |  |  | 16 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-104 |  |  | 16 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-104 |  |  | 16 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-104 |  |  | 16 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-104 |  |  | 16 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-104 |  |  | 16 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-104 |  |  | 16 | 18 | 18 | 0 | 0
#REF! | 1 | BQ-105 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-105 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-105 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-105 | INVOICE | 22 | 17 | 18 | 18 | 7040 | 0
#REF! | 0 | BQ-105 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-105 | INVOICE | 26 | 17 | 18 | 18 | 3520 | 0
#REF! | 0 | BQ-105 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-105 | INVOICE | 31 | 17 | 18 | 18 | 1760 | 0
#REF! | 0 | BQ-105 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-105 | INVOICE | 32 | 17 | 18 | 18 | 8160 | 0
#REF! | 0 | BQ-105 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-105 | OVERALL |  | 17 | 18 | 18 | 0 | 20480
#REF! | 0 | BQ-105 |  |  | 17 | 14 | 17 | 0 | 0
#REF! | 0 | BQ-105 |  |  | 17 | 14 | 17 | 0 | 0
#REF! | 0 | BQ-105 |  |  | 17 | 14 | 17 | 0 | 0
#REF! | 0 | BQ-105 |  |  | 17 | 14 | 17 | 0 | 0
#REF! | 0 | BQ-105 |  |  | 17 | 14 | 17 | 0 | 0
#REF! | 0 | BQ-105 |  |  | 17 | 14 | 17 | 0 | 0
#REF! | 0 | BQ-105 |  |  | 17 | 14 | 17 | 0 | 0
#REF! | 0 | BQ-105 |  |  | 17 | 14 | 17 | 0 | 0
#REF! | 1 | BQ-106 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-106 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-106 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-106 | INVOICE | 20 | 13 | 14 | 14 | 5060 | 0
#REF! | 0 | BQ-106 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-106 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-106 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-106 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-106 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-106 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-106 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-106 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-106 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-106 | OVERALL |  | 13 | 14 | 14 | 0 | 5060
#REF! | 0 | BQ-106 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-106 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-106 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-106 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-106 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-106 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-106 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-106 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-107 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-107 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-107 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-107 | INVOICE | 25 | 14 | 15 | 15 | 7920 | 0
#REF! | 0 | BQ-107 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-107 | INVOICE | 26 | 14 | 15 | 15 | 7920 | 0
#REF! | 0 | BQ-107 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-107 | INVOICE | 30 | 14 | 15 | 15 | 5760 | 0
#REF! | 0 | BQ-107 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-107 | INVOICE | 31 | 14 | 15 | 15 | 720 | 0
#REF! | 0 | BQ-107 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-107 | INVOICE | 32 | 14 | 15 | 15 | 720 | 0
#REF! | 0 | BQ-107 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-107 | OVERALL |  | 14 | 15 | 15 | 0 | 23040
#REF! | 0 | BQ-107 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-107 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-107 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-107 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-107 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-107 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-107 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-107 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-108 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-108 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-108 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-108 | INVOICE | 28 | 14 | 15 | 15 | 3920 | 0
#REF! | 0 | BQ-108 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-108 | INVOICE | 31 | 14 | 15 | 15 | 392 | 0
#REF! | 0 | BQ-108 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-108 | INVOICE | 32 | 14 | 15 | 15 | 168 | 0
#REF! | 0 | BQ-108 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-108 | OVERALL |  | 14 | 15 | 15 | 0 | 4480
#REF! | 0 | BQ-108 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-108 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-108 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-108 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-108 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-108 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-108 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-108 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-109 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-109 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-109 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-109 | INVOICE | 13 | 14 | 15 | 15 | 8690 | 0
#REF! | 0 | BQ-109 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-109 | INVOICE | 27 | 14 | 15 | 15 | 553 | 0
#REF! | 0 | BQ-109 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-109 | INVOICE | 29 | 14 | 15 | 15 | 6952 | 0
#REF! | 0 | BQ-109 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-109 | INVOICE | 31 | 14 | 15 | 15 | 2212 | 0
#REF! | 0 | BQ-109 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-109 | INVOICE | 32 | 14 | 15 | 15 | 1185 | 0
#REF! | 0 | BQ-109 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-109 | OVERALL |  | 14 | 15 | 15 | 0 | 19592
#REF! | 0 | BQ-109 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-109 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-109 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-109 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-109 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-109 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-109 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-109 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-110 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-110 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-110 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-110 | INVOICE | 27 | 14 | 15 | 15 | 2970 | 0
#REF! | 0 | BQ-110 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-110 | INVOICE | 31 | 14 | 15 | 15 | 618.75 | 0
#REF! | 0 | BQ-110 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-110 | INVOICE | 32 | 14 | 15 | 15 | 371.25 | 0
#REF! | 0 | BQ-110 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-110 | OVERALL |  | 14 | 15 | 15 | 0 | 3960
#REF! | 0 | BQ-110 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-110 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-110 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-110 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-110 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-110 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-110 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-110 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-111 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-111 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-111 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-111 | INVOICE | 16 | 14 | 15 | 15 | 4340 | 0
#REF! | 0 | BQ-111 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-111 | INVOICE | 31 | 14 | 15 | 15 | 434 | 0
#REF! | 0 | BQ-111 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-111 | INVOICE | 32 | 14 | 15 | 15 | 186 | 0
#REF! | 0 | BQ-111 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-111 | OVERALL |  | 14 | 15 | 15 | 0 | 4960
#REF! | 0 | BQ-111 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-111 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-111 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-111 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-111 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-111 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-111 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-111 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-112 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-112 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-112 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-112 | INVOICE | 13 | 14 | 15 | 15 | 4340 | 0
#REF! | 0 | BQ-112 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-112 | INVOICE | 31 | 14 | 15 | 15 | 434 | 0
#REF! | 0 | BQ-112 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-112 | OVERALL |  | 14 | 15 | 15 | 0 | 4960
#REF! | 0 | BQ-112 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-112 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-112 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-112 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-112 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-112 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-112 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-112 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-113 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-113 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-113 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-113 | INVOICE | 13 | 14 | 15 | 15 | 3410 | 0
#REF! | 0 | BQ-113 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-113 | INVOICE | 31 | 14 | 15 | 15 | 1085 | 0
#REF! | 0 | BQ-113 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-113 | OVERALL |  | 14 | 15 | 15 | 0 | 4960
#REF! | 0 | BQ-113 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-113 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-113 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-113 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-113 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-113 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-113 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-113 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-114 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-114 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-114 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-114 | INVOICE | 13 | 14 | 15 | 15 | 3080 | 0
#REF! | 0 | BQ-114 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-114 | INVOICE | 27 | 14 | 15 | 15 | 280 | 0
#REF! | 0 | BQ-114 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-114 | INVOICE | 31 | 14 | 15 | 15 | 840 | 0
#REF! | 0 | BQ-114 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-114 | OVERALL |  | 14 | 15 | 15 | 0 | 4340
#REF! | 0 | BQ-114 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-114 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-114 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-114 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-114 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-114 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-114 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-114 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-115 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-115 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-115 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-115 | INVOICE | 26 | 14 | 15 | 15 | 1017.5 | 0
#REF! | 0 | BQ-115 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-115 | INVOICE | 31 | 14 | 15 | 15 | 277.5 | 0
#REF! | 0 | BQ-115 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-115 | OVERALL |  | 14 | 15 | 15 | 0 | 1480
#REF! | 0 | BQ-115 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-115 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-115 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-115 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-115 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-115 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-115 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-115 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-116 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-116 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-116 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-116 | INVOICE | 14 | 14 | 15 | 15 | 1485 | 0
#REF! | 0 | BQ-116 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-116 | INVOICE | 27 | 14 | 15 | 15 | 472.5 | 0
#REF! | 0 | BQ-116 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-116 | INVOICE | 32 | 14 | 15 | 15 | 202.5 | 0
#REF! | 0 | BQ-116 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-116 | OVERALL |  | 14 | 15 | 15 | 0 | 2160
#REF! | 0 | BQ-116 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-116 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-116 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-116 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-116 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-116 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-116 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-116 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-117 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-117 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-117 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-117 | INVOICE | 14 | 14 | 15 | 15 | 154 | 0
#REF! | 0 | BQ-117 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-117 | INVOICE | 31 | 14 | 15 | 15 | 15.4 | 0
#REF! | 0 | BQ-117 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-117 | INVOICE | 32 | 14 | 15 | 15 | 6.6 | 0
#REF! | 0 | BQ-117 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-117 | OVERALL |  | 14 | 15 | 15 | 0 | 176
#REF! | 0 | BQ-117 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-117 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-117 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-117 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-117 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-117 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-117 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-117 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-118 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-118 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-118 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-118 | INVOICE | 25 | 15 | 16 | 16 | 20790 | 0
#REF! | 0 | BQ-118 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-118 | INVOICE | 30 | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-118 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-118 | INVOICE | 31 | 15 | 16 | 16 | 2970 | 0
#REF! | 0 | BQ-118 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-118 | OVERALL |  | 15 | 16 | 16 | 0 | 23760
#REF! | 0 | BQ-118 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-118 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-118 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-118 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-118 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-118 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-118 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-118 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-119 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-119 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-119 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-119 | INVOICE | 21 | 14 | 15 | 15 | 92400 | 0
#REF! | 0 | BQ-119 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-119 | INVOICE | 31 | 14 | 15 | 15 | 9240 | 0
#REF! | 0 | BQ-119 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-119 | OVERALL |  | 14 | 15 | 15 | 0 | 101640
#REF! | 0 | BQ-119 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-119 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-119 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-119 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-119 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-119 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-119 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-119 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-120 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-120 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-120 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-120 | INVOICE | 14 | 14 | 15 | 15 | 88 | 0
#REF! | 0 | BQ-120 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-120 | INVOICE | 27 | 14 | 15 | 15 | 28 | 0
#REF! | 0 | BQ-120 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-120 | INVOICE | 32 | 14 | 15 | 15 | 12 | 0
#REF! | 0 | BQ-120 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-120 | OVERALL |  | 14 | 15 | 15 | 0 | 128
#REF! | 0 | BQ-120 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-120 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-120 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-120 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-120 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-120 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-120 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-120 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-121 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-121 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-121 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-121 | INVOICE | 14 | 14 | 15 | 15 | 660 | 0
#REF! | 0 | BQ-121 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-121 | INVOICE | 27 | 14 | 15 | 15 | 210 | 0
#REF! | 0 | BQ-121 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-121 | INVOICE | 32 | 14 | 15 | 15 | 90 | 0
#REF! | 0 | BQ-121 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-121 | OVERALL |  | 14 | 15 | 15 | 0 | 960
#REF! | 0 | BQ-121 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-121 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-121 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-121 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-121 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-121 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-121 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-121 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-122 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-122 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-122 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-122 | INVOICE | 26 | 14 | 15 | 15 | 132 | 0
#REF! | 0 | BQ-122 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-122 | INVOICE | 31 | 14 | 15 | 15 | 42 | 0
#REF! | 0 | BQ-122 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-122 | INVOICE | 32 | 14 | 15 | 15 | 18 | 0
#REF! | 0 | BQ-122 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-122 | OVERALL |  | 14 | 15 | 15 | 0 | 192
#REF! | 0 | BQ-122 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-122 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-122 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-122 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-122 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-122 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-122 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-122 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-123 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-123 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-123 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-123 | INVOICE | 14 | 14 | 15 | 15 | 104.5 | 0
#REF! | 0 | BQ-123 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-123 | INVOICE | 27 | 14 | 15 | 15 | 33.25 | 0
#REF! | 0 | BQ-123 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-123 | INVOICE | 32 | 14 | 15 | 15 | 14.25 | 0
#REF! | 0 | BQ-123 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-123 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-123 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-123 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-123 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-123 | OVERALL |  | 14 | 15 | 15 | 0 | 152
#REF! | 0 | BQ-123 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-123 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-123 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-123 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-123 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-123 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-123 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-123 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-124 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-124 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-124 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-124 | INVOICE | 27 | 14 | 15 | 15 | 3312 | 0
#REF! | 0 | BQ-124 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-124 | INVOICE | 31 | 14 | 15 | 15 | 276 | 0
#REF! | 0 | BQ-124 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-124 | INVOICE | 32 | 14 | 15 | 15 | 92 | 0
#REF! | 0 | BQ-124 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-124 | OVERALL |  | 14 | 15 | 15 | 0 | 3680
#REF! | 0 | BQ-124 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-124 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-124 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-124 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-124 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-124 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-124 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-124 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-125 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-125 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-125 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-125 | INVOICE | 27 | 14 | 15 | 15 | 1656 | 0
#REF! | 0 | BQ-125 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-125 | INVOICE | 31 | 14 | 15 | 15 | 138 | 0
#REF! | 0 | BQ-125 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-125 | INVOICE | 32 | 14 | 15 | 15 | 46 | 0
#REF! | 0 | BQ-125 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-125 | OVERALL |  | 14 | 15 | 15 | 0 | 1840
#REF! | 0 | BQ-125 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-125 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-125 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-125 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-125 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-125 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-125 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-125 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-126 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-126 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-126 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-126 | INVOICE | 0 | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-126 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-126 | OVERALL |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-126 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-126 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-126 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-126 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-126 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-126 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-126 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-126 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-127 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-127 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-127 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-127 | INVOICE | 13 | 15 | 16 | 16 | 1430 | 0
#REF! | 0 | BQ-127 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-127 | INVOICE | 32 | 15 | 16 | 16 | 650 | 0
#REF! | 0 | BQ-127 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-127 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-127 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-127 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-127 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-127 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-127 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-127 | OVERALL |  | 15 | 16 | 16 | 0 | 2080
#REF! | 0 | BQ-127 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-127 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-127 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-127 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-127 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-127 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-127 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-127 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-128 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-128 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-128 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-128 | INVOICE | 15 | 15 | 16 | 16 | 61820 | 0
#REF! | 0 | BQ-128 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-128 | INVOICE | 27 | 15 | 16 | 16 | -30910 | 0
#REF! | 0 | BQ-128 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-128 | INVOICE | 31 | 15 | 16 | 16 | 30910 | 0
#REF! | 0 | BQ-128 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-128 | OVERALL |  | 15 | 16 | 16 | 0 | 87110
#REF! | 0 | BQ-128 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-128 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-128 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-128 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-128 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-128 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-128 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-128 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-129 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-129 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-129 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-129 | INVOICE | 15 | 14 | 15 | 15 | 2310 | 0
#REF! | 0 | BQ-129 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-129 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-129 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-129 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-129 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-129 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-129 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-129 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-129 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-129 | OVERALL |  | 14 | 15 | 15 | 0 | 2310
#REF! | 0 | BQ-129 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-129 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-129 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-129 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-129 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-129 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-129 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-129 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-130 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-130 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-130 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-130 | INVOICE | 15 | 14 | 15 | 15 | 1760 | 0
#REF! | 0 | BQ-130 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-130 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-130 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-130 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-130 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-130 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-130 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-130 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-130 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-130 | OVERALL |  | 14 | 15 | 15 | 0 | 1760
#REF! | 0 | BQ-130 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-130 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-130 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-130 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-130 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-130 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-130 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-130 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-131 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-131 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-131 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-131 | INVOICE | 15 | 14 | 15 | 15 | 1980 | 0
#REF! | 0 | BQ-131 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-131 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-131 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-131 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-131 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-131 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-131 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-131 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-131 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-131 | OVERALL |  | 14 | 15 | 15 | 0 | 1980
#REF! | 0 | BQ-131 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-131 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-131 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-131 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-131 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-131 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-131 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-131 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-132 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-132 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-132 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-132 | INVOICE | 13 | 15 | 16 | 16 | 63800 | 0
#REF! | 0 | BQ-132 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-132 | INVOICE | 33 | 15 | 16 | 16 | 26100 | 0
#REF! | 0 | BQ-132 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-132 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-132 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-132 | OVERALL |  | 15 | 16 | 16 | 0 | 89900
#REF! | 0 | BQ-132 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-132 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-132 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-132 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-132 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-132 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-132 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-132 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-133 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-133 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-133 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-133 | INVOICE | 12 | 15 | 16 | 16 | 1595 | 0
#REF! | 0 | BQ-133 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-133 | INVOICE | 27 | 15 | 16 | 16 | 6960 | 0
#REF! | 0 | BQ-133 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-133 | INVOICE | 32 | 15 | 16 | 16 | 145 | 0
#REF! | 0 | BQ-133 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-133 | OVERALL |  | 15 | 16 | 16 | 0 | 8700
#REF! | 0 | BQ-133 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-133 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-133 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-133 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-133 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-133 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-133 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-133 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-134 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-134 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-134 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-134 | INVOICE | 28 | 14 | 15 | 15 | 3080 | 0
#REF! | 0 | BQ-134 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-134 | INVOICE | 28 | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-134 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-134 | INVOICE | 31 | 14 | 15 | 15 | 980 | 0
#REF! | 0 | BQ-134 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-134 | OVERALL |  | 14 | 15 | 15 | 0 | 4480
#REF! | 0 | BQ-134 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-134 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-134 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-134 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-134 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-134 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-134 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-134 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-135 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-135 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-135 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-135 | INVOICE | 28 | 14 | 15 | 15 | 3080 | 0
#REF! | 0 | BQ-135 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-135 | INVOICE | 31 | 14 | 15 | 15 | 980 | 0
#REF! | 0 | BQ-135 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-135 | OVERALL |  | 14 | 15 | 15 | 0 | 4060
#REF! | 0 | BQ-135 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-135 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-135 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-135 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-135 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-135 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-135 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-135 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 1 | BQ-136 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-136 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-136 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-136 | INVOICE | 15 | 16 | 17 | 17 | 3552 | 0
#REF! | 0 | BQ-136 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-136 | INVOICE | 27 | 16 | 17 | 17 | -1776 | 0
#REF! | 0 | BQ-136 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-136 | INVOICE | 31 | 16 | 17 | 17 | 473.6 | 0
#REF! | 0 | BQ-136 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-136 | INVOICE | 32 | 16 | 17 | 17 | 2101.6 | 0
#REF! | 0 | BQ-136 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-136 | OVERALL |  | 16 | 17 | 17 | 0 | 4351.2
#REF! | 0 | BQ-136 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-136 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-136 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-136 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-136 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-136 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-136 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-136 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 1 | BQ-137 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-137 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-137 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-137 | INVOICE | 17 | 14 | 15 | 15 | 266090 | 0
#REF! | 0 | BQ-137 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-137 | INVOICE | 19 | 14 | 15 | 15 | 15340 | 0
#REF! | 0 | BQ-137 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-137 | INVOICE | 20 | 14 | 15 | 15 | 61065 | 0
#REF! | 0 | BQ-137 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-137 | INVOICE | 26 | 14 | 15 | 15 | -18585 | 0
#REF! | 0 | BQ-137 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-137 | INVOICE | 27 | 14 | 15 | 15 | 16520 | 0
#REF! | 0 | BQ-137 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-137 | INVOICE | 28 | 14 | 15 | 15 | 69620 | 0
#REF! | 0 | BQ-137 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-137 | INVOICE | 29 | 14 | 15 | 15 | 20060 | 0
#REF! | 0 | BQ-137 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-137 | INVOICE | 30 | 14 | 15 | 15 | 47790 | 0
#REF! | 0 | BQ-137 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-137 | OVERALL |  | 14 | 15 | 15 | 0 | 477900
#REF! | 0 | BQ-137 |  |  | 14 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-137 |  |  | 14 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-137 |  |  | 14 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-137 |  |  | 14 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-137 |  |  | 14 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-137 |  |  | 14 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-137 |  |  | 14 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-137 |  |  | 14 | 25 | 25 | 0 | 0
#REF! | 1 | BQ-138 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-138 | INVOICE | 17 | 24 | 25 | 25 | 383812 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-138 | INVOICE | 18 | 24 | 25 | 25 | 82368 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-138 | INVOICE | 19 | 24 | 25 | 25 | 74646 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-138 | INVOICE | 20 | 24 | 25 | 25 | 19305 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-138 | INVOICE | 24 | 24 | 25 | 25 | 275583 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-138 | INVOICE | 26 | 24 | 25 | 25 | -34749 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-138 | INVOICE | 27 | 24 | 25 | 25 | 246015 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-138 | INVOICE | 28 | 24 | 25 | 25 | 68640 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-138 | INVOICE | 31 | 24 | 25 | 25 | 15444 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-138 | INVOICE | 32 | 24 | 25 | 25 | 452936 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-138 | OVERALL |  | 24 | 25 | 25 | 0 | 1672000
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-138 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 1 | BQ-139 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-139 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-139 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-139 | INVOICE | 29 | 14 | 15 | 15 | 91350 | 0
#REF! | 0 | BQ-139 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-139 | INVOICE | 32 | 14 | 15 | 15 | 13050 | 0
#REF! | 0 | BQ-139 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-139 | OVERALL |  | 14 | 15 | 15 | 0 | 104400
#REF! | 0 | BQ-139 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-139 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-139 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-139 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-139 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-139 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-139 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-139 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-140 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-140 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-140 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-140 | INVOICE | 13 | 15 | 16 | 16 | 8580 | 0
#REF! | 0 | BQ-140 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-140 | INVOICE | 25 | 15 | 16 | 16 | 2340 | 0
#REF! | 0 | BQ-140 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-140 | INVOICE | 27 | 15 | 16 | 16 | 390 | 0
#REF! | 0 | BQ-140 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-140 | INVOICE | 32 | 15 | 16 | 16 | 1170 | 0
#REF! | 0 | BQ-140 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-140 | OVERALL |  | 15 | 16 | 16 | 0 | 12480
#REF! | 0 | BQ-140 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-140 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-140 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-140 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-140 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-140 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-140 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-140 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-141 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-141 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-141 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-141 | INVOICE | 13 | 15 | 16 | 16 | 5280 | 0
#REF! | 0 | BQ-141 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-141 | INVOICE | 32 | 15 | 16 | 16 | 2400 | 0
#REF! | 0 | BQ-141 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-141 | OVERALL |  | 15 | 16 | 16 | 0 | 7680
#REF! | 0 | BQ-141 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-141 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-141 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-141 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-141 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-141 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-141 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-141 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 1 | BQ-142 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-142 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-142 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-142 | INVOICE | 18 | 18 | 19 | 19 | 1089 | 0
#REF! | 0 | BQ-142 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-142 | INVOICE | 23 | 18 | 19 | 19 | 1633.5 | 0
#REF! | 0 | BQ-142 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-142 | INVOICE | 27 | 18 | 19 | 19 | 742.5 | 0
#REF! | 0 | BQ-142 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-142 | INVOICE | 31 | 18 | 19 | 19 | 495 | 0
#REF! | 0 | BQ-142 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-142 | INVOICE | 32 | 18 | 19 | 19 | 990 | 0
#REF! | 0 | BQ-142 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-142 | OVERALL |  | 18 | 19 | 19 | 0 | 4950
#REF! | 0 | BQ-142 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-142 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-142 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-142 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-142 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-142 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-142 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-142 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 1 | BQ-143 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-143 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-143 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-143 | INVOICE | 24 | 15 | 16 | 16 | 7975 | 0
#REF! | 0 | BQ-143 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-143 | INVOICE | 25 | 15 | 16 | 16 | 1740 | 0
#REF! | 0 | BQ-143 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-143 | INVOICE | 27 | 15 | 16 | 16 | 217.5 | 0
#REF! | 0 | BQ-143 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-143 | INVOICE | 32 | 15 | 16 | 16 | 870 | 0
#REF! | 0 | BQ-143 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-143 | OVERALL |  | 15 | 16 | 16 | 0 | 10585
#REF! | 0 | BQ-143 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-143 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-143 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-143 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-143 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-143 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-143 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-143 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-144 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-144 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-144 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-144 | INVOICE | 13 | 14 | 15 | 15 | 8690 | 0
#REF! | 0 | BQ-144 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-144 | INVOICE | 25 | 14 | 15 | 15 | 1659 | 0
#REF! | 0 | BQ-144 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-144 | INVOICE | 32 | 14 | 15 | 15 | 394.9842 | 0
#REF! | 0 | BQ-144 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-144 | OVERALL |  | 14 | 15 | 15 | 0 | 11060
#REF! | 0 | BQ-144 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-144 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-144 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-144 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-144 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-144 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-144 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-144 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-145 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-145 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-145 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-145 | INVOICE | 14 | 14 | 15 | 15 | 627 | 0
#REF! | 0 | BQ-145 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-145 | INVOICE | 25 | 14 | 15 | 15 | 199.5 | 0
#REF! | 0 | BQ-145 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-145 | INVOICE | 32 | 14 | 15 | 15 | 85.5 | 0
#REF! | 0 | BQ-145 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-145 | OVERALL |  | 14 | 15 | 15 | 0 | 912
#REF! | 0 | BQ-145 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-145 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-145 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-145 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-145 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-145 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-145 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-145 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-146 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-146 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-146 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-146 | INVOICE | 14 | 14 | 15 | 15 | 1320 | 0
#REF! | 0 | BQ-146 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-146 | INVOICE | 25 | 14 | 15 | 15 | 420 | 0
#REF! | 0 | BQ-146 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-146 | INVOICE | 32 | 14 | 15 | 15 | 180 | 0
#REF! | 0 | BQ-146 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-146 | OVERALL |  | 14 | 15 | 15 | 0 | 1920
#REF! | 0 | BQ-146 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-146 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-146 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-146 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-146 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-146 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-146 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-146 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-147 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-147 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-147 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-147 | INVOICE | 14 | 14 | 15 | 15 | 264 | 0
#REF! | 0 | BQ-147 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-147 | INVOICE | 25 | 14 | 15 | 15 | 84 | 0
#REF! | 0 | BQ-147 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-147 | INVOICE | 32 | 14 | 15 | 15 | 36 | 0
#REF! | 0 | BQ-147 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-147 | OVERALL |  | 14 | 15 | 15 | 0 | 384
#REF! | 0 | BQ-147 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-147 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-147 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-147 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-147 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-147 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-147 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-147 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-148 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-148 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-148 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-148 | INVOICE | 14 | 14 | 15 | 15 | 88 | 0
#REF! | 0 | BQ-148 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-148 | INVOICE | 25 | 14 | 15 | 15 | 28 | 0
#REF! | 0 | BQ-148 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-148 | INVOICE | 32 | 14 | 15 | 15 | 12 | 0
#REF! | 0 | BQ-148 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-148 | OVERALL |  | 14 | 15 | 15 | 0 | 128
#REF! | 0 | BQ-148 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-148 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-148 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-148 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-148 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-148 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-148 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-148 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-149 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-149 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-149 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-149 | INVOICE | 12 | 14 | 15 | 15 | 16800 | 0
#REF! | 0 | BQ-149 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-149 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-149 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-149 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-149 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-149 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-149 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-149 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-149 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-149 | OVERALL |  | 14 | 15 | 15 | 0 | 16800
#REF! | 0 | BQ-149 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-149 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-149 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-149 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-149 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-149 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-149 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-149 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-150 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-150 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-150 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-150 | INVOICE | 24 | 14 | 15 | 15 | 27720 | 0
#REF! | 0 | BQ-150 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-150 | INVOICE | 32 | 14 | 15 | 15 | 55440 | 0
#REF! | 0 | BQ-150 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-150 | OVERALL |  | 14 | 15 | 15 | 0 | 83160
#REF! | 0 | BQ-150 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-150 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-150 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-150 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-150 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-150 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-150 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-150 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-151 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-151 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-151 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-151 | INVOICE | 27 | 14 | 15 | 15 | 3312 | 0
#REF! | 0 | BQ-151 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-151 | INVOICE | 32 | 14 | 15 | 15 | 184 | 0
#REF! | 0 | BQ-151 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-151 | OVERALL |  | 14 | 15 | 15 | 0 | 3680
#REF! | 0 | BQ-151 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-151 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-151 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-151 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-151 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-151 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-151 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-151 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-152 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-152 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-152 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-152 | INVOICE | 27 | 14 | 15 | 15 | 1656 | 0
#REF! | 0 | BQ-152 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-152 | INVOICE | 32 | 14 | 15 | 15 | 184 | 0
#REF! | 0 | BQ-152 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-152 | OVERALL |  | 14 | 15 | 15 | 0 | 1840
#REF! | 0 | BQ-152 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-152 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-152 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-152 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-152 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-152 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-152 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-152 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-153 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-153 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-153 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-153 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-153 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-153 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-153 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-153 | OVERALL |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-153 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-153 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-153 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-153 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-153 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-153 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-153 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-153 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-154 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-154 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-154 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-154 | INVOICE | 26 | 14 | 15 | 15 | 4340 | 0
#REF! | 0 | BQ-154 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-154 | INVOICE | 32 | 14 | 15 | 15 | 620 | 0
#REF! | 0 | BQ-154 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-154 | OVERALL |  | 14 | 15 | 15 | 0 | 4960
#REF! | 0 | BQ-154 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-154 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-154 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-154 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-154 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-154 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-154 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-154 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-155 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-155 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-155 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-155 | INVOICE | 28 | 14 | 15 | 15 | 990 | 0
#REF! | 0 | BQ-155 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-155 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-155 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-155 | OVERALL |  | 14 | 15 | 15 | 0 | 990
#REF! | 0 | BQ-155 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-155 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-155 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-155 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-155 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-155 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-155 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-155 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-156 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-156 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-156 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-156 | INVOICE | 14 | 14 | 15 | 15 | 1155 | 0
#REF! | 0 | BQ-156 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-156 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-156 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-156 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-156 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-156 | OVERALL |  | 14 | 15 | 15 | 0 | 1155
#REF! | 0 | BQ-156 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-156 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-156 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-156 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-156 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-156 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-156 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-156 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-157 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-157 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-157 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-157 | INVOICE | 13 | 14 | 15 | 15 | 13580 | 0
#REF! | 0 | BQ-157 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-157 | INVOICE | 32 | 14 | 15 | 15 | 1940 | 0
#REF! | 0 | BQ-157 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-157 | OVERALL |  | 14 | 15 | 15 | 0 | 15520
#REF! | 0 | BQ-157 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-157 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-157 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-157 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-157 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-157 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-157 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-157 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-158 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-158 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-158 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-158 | INVOICE | 10 | 14 | 15 | 15 | 106400 | 0
#REF! | 0 | BQ-158 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-158 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-158 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-158 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-158 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-158 | OVERALL |  | 14 | 15 | 15 | 0 | 106400
#REF! | 0 | BQ-158 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-158 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-158 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-158 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-158 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-158 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-158 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-158 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-159 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-159 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-159 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-159 | INVOICE | 21 | 14 | 15 | 15 | 92400 | 0
#REF! | 0 | BQ-159 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-159 | INVOICE | 31 | 14 | 15 | 15 | 9240 | 0
#REF! | 0 | BQ-159 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-159 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-159 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-159 | OVERALL |  | 14 | 15 | 15 | 0 | 101640
#REF! | 0 | BQ-159 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-159 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-159 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-159 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-159 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-159 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-159 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-159 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-160 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-160 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-160 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-160 | INVOICE | 12 | 14 | 15 | 15 | 910 | 0
#REF! | 0 | BQ-160 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-160 | INVOICE | 31 | 14 | 15 | 15 | 91 | 0
#REF! | 0 | BQ-160 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-160 | OVERALL |  | 14 | 15 | 15 | 0 | 1001
#REF! | 0 | BQ-160 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-160 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-160 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-160 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-160 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-160 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-160 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-160 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-161 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-161 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-161 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-161 | INVOICE | 25 | 15 | 16 | 16 | 20790 | 0
#REF! | 0 | BQ-161 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-161 | INVOICE | 30 | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-161 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-161 | INVOICE | 31 | 15 | 16 | 16 | 2970 | 0
#REF! | 0 | BQ-161 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-161 | OVERALL |  | 15 | 16 | 16 | 0 | 23760
#REF! | 0 | BQ-161 |  |  | 15 | 13 | 15 | 0 | 0
#REF! | 0 | BQ-161 |  |  | 15 | 13 | 15 | 0 | 0
#REF! | 0 | BQ-161 |  |  | 15 | 13 | 15 | 0 | 0
#REF! | 0 | BQ-161 |  |  | 15 | 13 | 15 | 0 | 0
#REF! | 0 | BQ-161 |  |  | 15 | 13 | 15 | 0 | 0
#REF! | 0 | BQ-161 |  |  | 15 | 13 | 15 | 0 | 0
#REF! | 0 | BQ-161 |  |  | 15 | 13 | 15 | 0 | 0
#REF! | 0 | BQ-161 |  |  | 15 | 13 | 15 | 0 | 0
#REF! | 1 | BQ-162 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-162 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-162 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-162 | INVOICE | 17 | 12 | 13 | 13 | 12490.5 | 0
#REF! | 0 | BQ-162 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-162 | INVOICE | 18 | 12 | 13 | 13 | 5677.5 | 0
#REF! | 0 | BQ-162 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-162 | INVOICE | 24 | 12 | 13 | 13 | 2271 | 0
#REF! | 0 | BQ-162 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-162 | INVOICE | 30 | 12 | 13 | 13 | 2271 | 0
#REF! | 0 | BQ-162 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-162 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-162 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-162 | OVERALL |  | 12 | 13 | 13 | 0 | 22710
#REF! | 0 | BQ-162 |  |  | 12 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-162 |  |  | 12 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-162 |  |  | 12 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-162 |  |  | 12 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-162 |  |  | 12 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-162 |  |  | 12 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-162 |  |  | 12 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-162 |  |  | 12 | 20 | 20 | 0 | 0
#REF! | 1 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 | INVOICE | 8 | 19 | 20 | 20 | 197730 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 | INVOICE | 9 | 19 | 20 | 20 | 380250 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 | INVOICE | 11 | 19 | 20 | 20 | 479700 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 | INVOICE | 13 | 19 | 20 | 20 | 187200 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 | INVOICE | 14 | 19 | 20 | 20 | 106704 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 | INVOICE | 15 | 19 | 20 | 20 | 28080 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 | INVOICE | 17 | 19 | 20 | 20 | 31590 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 | INVOICE | 18 | 19 | 20 | 20 | 15210 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 | INVOICE | 21 | 19 | 20 | 20 | 22230 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 | INVOICE | 22 | 19 | 20 | 20 | 72072 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 | INVOICE | 23 | 19 | 20 | 20 | 56628 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 | INVOICE | 24 | 19 | 20 | 20 | 29250 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 | INVOICE | 25 | 19 | 20 | 20 | 37908 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 | INVOICE | 26 | 19 | 20 | 20 | 114192.0029 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 | INVOICE | 27 | 19 | 20 | 20 | 202878 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 | INVOICE | 29 | 19 | 20 | 20 | 58500 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 | INVOICE | 30 | 19 | 20 | 20 | 27378 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 | INVOICE | 31 | 19 | 20 | 20 | 175500 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 | INVOICE | 32 | 19 | 20 | 20 | 70200 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 20 | 20 | 0 | 0
#REF! | 0 | BQ-163 | OVERALL |  | 19 | 20 | 20 | 0 | 2316600.0029
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 0 | BQ-163 |  |  | 19 | 14 | 19 | 0 | 0
#REF! | 1 | CR1-008 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-008 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-008 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-008 | INVOICE | 27 | 13 | 14 | 14 | 13044.45 | 0
#REF! | 0 | CR1-008 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-008 | INVOICE | 28 | 13 | 14 | 14 | 11671.35 | 0
#REF! | 0 | CR1-008 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-008 | INVOICE | 31 | 13 | 14 | 14 | 2746.2 | 0
#REF! | 0 | CR1-008 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-008 | OVERALL |  | 13 | 14 | 14 | 0 | 27462
#REF! | 0 | CR1-008 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-008 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-008 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-008 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-008 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-008 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-008 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-008 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 1 | CR1-009 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-009 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-009 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-009 | INVOICE | 28 | 14 | 15 | 15 | 24715.8 | 0
#REF! | 0 | CR1-009 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-009 | INVOICE | 31 | 14 | 15 | 15 | 2746.2 | 0
#REF! | 0 | CR1-009 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-009 | OVERALL |  | 14 | 15 | 15 | 0 | 27462
#REF! | 0 | CR1-009 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-009 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-009 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-009 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-009 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-009 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-009 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-009 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 1 | CR1-010 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-010 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-010 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-010 | INVOICE | 28 | 12 | 13 | 13 | 15549.98 | 0
#REF! | 0 | CR1-010 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-010 | INVOICE | 29 | 12 | 13 | 13 | 21522.82 | 0
#REF! | 0 | CR1-010 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-010 | INVOICE | 31 | 12 | 13 | 13 | 4119.2 | 0
#REF! | 0 | CR1-010 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-010 | OVERALL |  | 12 | 13 | 13 | 0 | 41192
#REF! | 0 | CR1-010 |  |  | 12 | #REF! | #REF! | 0 | 0
#REF! | 0 | CR1-010 |  |  | 12 | #REF! | #REF! | 0 | 0
#REF! | 0 | CR1-010 |  |  | 12 | #REF! | #REF! | 0 | 0
#REF! | 0 | CR1-010 |  |  | 12 | #REF! | #REF! | 0 | 0
#REF! | 0 | CR1-010 |  |  | 12 | #REF! | #REF! | 0 | 0
#REF! | 0 | CR1-010 |  |  | 12 | #REF! | #REF! | 0 | 0
#REF! | 0 | CR1-010 |  |  | 12 | #REF! | #REF! | 0 | 0
#REF! | 0 | CR1-010 |  |  | 12 | #REF! | #REF! | 0 | 0
#REF! | 1 | CR1-011 |  |  | 12 | #REF! | #REF! | 0 | 0
#REF! | 0 | CR1-011 |  |  | 12 | #REF! | #REF! | 0 | 0
#REF! | 0 | CR1-011 |  |  | 12 | #REF! | #REF! | 0 | 0
#REF! | 0 | CR1-011 | INVOICE | 30 | 12 | #REF! | #REF! | #REF! | 0
#REF! | 0 | CR1-011 |  |  | 12 | #REF! | #REF! | 0 | 0
#REF! | 0 | CR1-011 | INVOICE | 33 | 12 | #REF! | #REF! | #REF! | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | #REF! | 13 | #REF! | 0 | 0
#REF! | #REF! | #REF! | OVERALL |  | #REF! | 13 | #REF! | 0 | 13731
#REF! | 0 | #REF! |  |  | #REF! | 13 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 13 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 13 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 13 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 13 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 13 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 13 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 13 | #REF! | 0 | 0
#REF! | 1 | CR1-012 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-012 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-012 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-012 | INVOICE | 29 | 12 | 13 | 13 | 24715.8 | 0
#REF! | 0 | CR1-012 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-012 | INVOICE | 31 | 12 | 13 | 13 | 2746.2 | 0
#REF! | 0 | CR1-012 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-012 | OVERALL |  | 12 | 13 | 13 | 0 | 27462
#REF! | 0 | CR1-012 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-012 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-012 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-012 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-012 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-012 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-012 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-012 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 1 | CR1-013 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-013 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-013 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-013 | INVOICE | 30 | 23 | 24 | 24 | 13181.52 | 0
#REF! | 0 | CR1-013 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-013 | INVOICE | 31 | 23 | 24 | 24 | 9336.91 | 0
#REF! | 0 | CR1-013 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-013 | INVOICE | 32 | 23 | 24 | 24 | 32404.57 | 0
#REF! | 0 | CR1-013 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-013 | OVERALL |  | 23 | 24 | 24 | 0 | 54923
#REF! | 0 | CR1-013 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | CR1-013 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | CR1-013 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | CR1-013 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | CR1-013 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | CR1-013 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | CR1-013 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | CR1-013 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 1 | CR1-014 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-014 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-014 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-014 | INVOICE | 31 | 13 | 14 | 14 | 29658.6 | 0
#REF! | 0 | CR1-014 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-014 | INVOICE | 32 | 13 | 14 | 14 | 3295.4 | 0
#REF! | 0 | CR1-014 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-014 | OVERALL |  | 13 | 14 | 14 | 0 | 32954
#REF! | 0 | CR1-014 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-014 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-014 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-014 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-014 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-014 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-014 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-014 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 1 | CR1-015 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-015 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-015 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-015 | INVOICE | 27 | 13 | 14 | 14 | 16614.4 | 0
#REF! | 0 | CR1-015 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-015 | INVOICE | 30 | 13 | 14 | 14 | 10572.8 | 0
#REF! | 0 | CR1-015 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-015 | INVOICE | 31 | 13 | 14 | 14 | 3020.8 | 0
#REF! | 0 | CR1-015 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-015 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-015 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-015 | OVERALL |  | 13 | 14 | 14 | 0 | 30208
#REF! | 0 | CR1-015 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-015 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-015 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-015 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-015 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-015 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-015 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-015 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 1 | CR1-016 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-016 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-016 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-016 | INVOICE | 31 | 15 | 16 | 16 | 1647.75 | 0
#REF! | 0 | CR1-016 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-016 | INVOICE | 32 | 15 | 16 | 16 | 4998.175 | 0
#REF! | 0 | CR1-016 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-016 | OVERALL |  | 15 | 16 | 16 | 0 | 9886.5
#REF! | 0 | CR1-016 |  |  | 15 | 14 | 15 | 0 | 0
#REF! | 0 | CR1-016 |  |  | 15 | 14 | 15 | 0 | 0
#REF! | 0 | CR1-016 |  |  | 15 | 14 | 15 | 0 | 0
#REF! | 0 | CR1-016 |  |  | 15 | 14 | 15 | 0 | 0
#REF! | 0 | CR1-016 |  |  | 15 | 14 | 15 | 0 | 0
#REF! | 0 | CR1-016 |  |  | 15 | 14 | 15 | 0 | 0
#REF! | 0 | CR1-016 |  |  | 15 | 14 | 15 | 0 | 0
#REF! | 0 | CR1-016 |  |  | 15 | 14 | 15 | 0 | 0
#REF! | 1 | CR1-017 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-017 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-017 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-017 | INVOICE | 31 | 13 | 14 | 14 | 1235.7 | 0
#REF! | 0 | CR1-017 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-017 | INVOICE | 32 | 13 | 14 | 14 | 7002.3 | 0
#REF! | 0 | CR1-017 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-017 | OVERALL |  | 13 | 14 | 14 | 0 | 8238
#REF! | 0 | CR1-017 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-017 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-017 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-017 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-017 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-017 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-017 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-017 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 1 | NBQ-018 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-018 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-018 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-018 | INVOICE | 27 | 15 | 16 | 16 | 1595 | 0
#REF! | 0 | NBQ-018 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-018 | INVOICE | 32 | 15 | 16 | 16 | 725 | 0
#REF! | 0 | NBQ-018 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-018 | OVERALL |  | 15 | 16 | 16 | 0 | 2320
#REF! | 0 | NBQ-018 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-018 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-018 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-018 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-018 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-018 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-018 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-018 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 1 | NBQ-019 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-019 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-019 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-019 | INVOICE | 27 | 14 | 15 | 15 | 1738 | 0
#REF! | 0 | NBQ-019 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-019 | INVOICE | 32 | 14 | 15 | 15 | 790 | 0
#REF! | 0 | NBQ-019 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-019 | OVERALL |  | 14 | 15 | 15 | 0 | 2528
#REF! | 0 | NBQ-019 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-019 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-019 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-019 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-019 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-019 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-019 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-019 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | NBQ-020 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-020 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-020 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-020 | INVOICE | 27 | 14 | 15 | 15 | 104.5 | 0
#REF! | 0 | NBQ-020 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-020 | INVOICE | 32 | 14 | 15 | 15 | 47.5 | 0
#REF! | 0 | NBQ-020 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-020 | OVERALL |  | 14 | 15 | 15 | 0 | 152
#REF! | 0 | NBQ-020 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-020 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-020 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-020 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-020 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-020 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-020 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-020 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | NBQ-021 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-021 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-021 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-021 | INVOICE | 27 | 14 | 15 | 15 | 660 | 0
#REF! | 0 | NBQ-021 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-021 | INVOICE | 32 | 14 | 15 | 15 | 300 | 0
#REF! | 0 | NBQ-021 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-021 | OVERALL |  | 14 | 15 | 15 | 0 | 960
#REF! | 0 | NBQ-021 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-021 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-021 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-021 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-021 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-021 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-021 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-021 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | NBQ-022 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-022 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-022 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-022 | INVOICE | 27 | 14 | 15 | 15 | 88 | 0
#REF! | 0 | NBQ-022 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-022 | INVOICE | 32 | 14 | 15 | 15 | 40 | 0
#REF! | 0 | NBQ-022 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-022 | OVERALL |  | 14 | 15 | 15 | 0 | 128
#REF! | 0 | NBQ-022 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-022 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-022 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-022 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-022 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-022 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-022 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-022 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-164 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-164 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-164 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-164 | INVOICE | 13 | 15 | 16 | 16 | 14080 | 0
#REF! | 0 | BQ-164 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-164 | INVOICE | 27 | 15 | 16 | 16 | 8720 | 0
#REF! | 0 | BQ-164 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-164 | INVOICE | 28 | 15 | 16 | 16 | 7920 | 0
#REF! | 0 | BQ-164 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-164 | OVERALL |  | 15 | 16 | 16 | 0 | 30720
#REF! | 0 | BQ-164 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-164 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-164 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-164 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-164 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-164 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-164 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-164 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 1 | BQ-165 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-165 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-165 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-165 | INVOICE | 18 | 18 | 19 | 19 | 3633 | 0
#REF! | 0 | BQ-165 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-165 | INVOICE | 27 | 18 | 19 | 19 | 4410.75 | 0
#REF! | 0 | BQ-165 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-165 | INVOICE | 31 | 18 | 19 | 19 | 990 | 0
#REF! | 0 | BQ-165 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-165 | INVOICE | 33 | 18 | 19 | 19 | -123.75 | 0
#REF! | 0 | BQ-165 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-165 | OVERALL |  | 18 | 19 | 19 | 0 | 8910
#REF! | 0 | BQ-165 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-165 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-165 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-165 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-165 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-165 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-165 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 0 | BQ-165 |  |  | 18 | 16 | 18 | 0 | 0
#REF! | 1 | BQ-166 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-166 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-166 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-166 | INVOICE | 27 | 15 | 16 | 16 | 12180 | 0
#REF! | 0 | BQ-166 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-166 | INVOICE | 28 | 15 | 16 | 16 | 1260 | 0
#REF! | 0 | BQ-166 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-166 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-166 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-166 | OVERALL |  | 15 | 16 | 16 | 0 | 13440
#REF! | 0 | BQ-166 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-166 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-166 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-166 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-166 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-166 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-166 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-166 |  |  | 15 | 19 | 19 | 0 | 0
#REF! | 1 | BQ-167 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-167 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-167 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-167 | INVOICE | 12 | 18 | 19 | 19 | 76769 | 0
#REF! | 0 | BQ-167 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-167 | INVOICE | 15 | 18 | 19 | 19 | 32901 | 0
#REF! | 0 | BQ-167 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-167 | INVOICE | 24 | 18 | 19 | 19 | 19940 | 0
#REF! | 0 | BQ-167 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-167 | INVOICE | 27 | 18 | 19 | 19 | 84495.75 | 0
#REF! | 0 | BQ-167 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-167 | INVOICE | 31 | 18 | 19 | 19 | 1246.25 | 0
#REF! | 0 | BQ-167 |  |  | 18 | 19 | 19 | 0 | 0
#REF! | 0 | BQ-167 | OVERALL |  | 18 | 19 | 19 | 0 | 215352
#REF! | 0 | BQ-167 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-167 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-167 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-167 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-167 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-167 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-167 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 0 | BQ-167 |  |  | 18 | 17 | 18 | 0 | 0
#REF! | 1 | BQ-168 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-168 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-168 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-168 | INVOICE | 15 | 16 | 17 | 17 | 20900 | 0
#REF! | 0 | BQ-168 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-168 | INVOICE | 27 | 16 | 17 | 17 | 23275 | 0
#REF! | 0 | BQ-168 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-168 | INVOICE | 31 | 16 | 17 | 17 | 1425 | 0
#REF! | 0 | BQ-168 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-168 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-168 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-168 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-168 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-168 | OVERALL |  | 16 | 17 | 17 | 0 | 45600
#REF! | 0 | BQ-168 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-168 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-168 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-168 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-168 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-168 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-168 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-168 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 1 | BQ-169 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-169 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-169 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-169 | INVOICE | 26 | 14 | 15 | 15 | 11880 | 0
#REF! | 0 | BQ-169 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-169 | INVOICE | 32 | 14 | 15 | 15 | 5940 | 0
#REF! | 0 | BQ-169 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-169 | OVERALL |  | 14 | 15 | 15 | 0 | 25110
#REF! | 0 | BQ-169 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-169 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-169 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-169 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-169 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-169 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-169 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-169 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 1 | BQ-170 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-170 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-170 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-170 | INVOICE | 20 | 16 | 17 | 17 | 124416 | 0
#REF! | 0 | BQ-170 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-170 | INVOICE | 25 | 16 | 17 | 17 | 373248 | 0
#REF! | 0 | BQ-170 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-170 | INVOICE | 27 | 16 | 17 | 17 | 290304 | 0
#REF! | 0 | BQ-170 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-170 | INVOICE | 30 | 16 | 17 | 17 | 20736 | 0
#REF! | 0 | BQ-170 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-170 | INVOICE | 31 | 16 | 17 | 17 | 20736 | 0
#REF! | 0 | BQ-170 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-170 | OVERALL |  | 16 | 17 | 17 | 0 | 829440
#REF! | 0 | BQ-170 |  |  | 16 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-170 |  |  | 16 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-170 |  |  | 16 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-170 |  |  | 16 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-170 |  |  | 16 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-170 |  |  | 16 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-170 |  |  | 16 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-170 |  |  | 16 | 18 | 18 | 0 | 0
#REF! | 1 | BQ-171 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-171 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-171 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-171 | INVOICE | 22 | 17 | 18 | 18 | 7040 | 0
#REF! | 0 | BQ-171 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-171 | INVOICE | 26 | 17 | 18 | 18 | 3520 | 0
#REF! | 0 | BQ-171 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-171 | INVOICE | 27 | 17 | 18 | 18 | 20160 | 0
#REF! | 0 | BQ-171 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-171 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-171 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-171 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-171 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-171 | OVERALL |  | 17 | 18 | 18 | 0 | 30720
#REF! | 0 | BQ-171 |  |  | 17 | 14 | 17 | 0 | 0
#REF! | 0 | BQ-171 |  |  | 17 | 14 | 17 | 0 | 0
#REF! | 0 | BQ-171 |  |  | 17 | 14 | 17 | 0 | 0
#REF! | 0 | BQ-171 |  |  | 17 | 14 | 17 | 0 | 0
#REF! | 0 | BQ-171 |  |  | 17 | 14 | 17 | 0 | 0
#REF! | 0 | BQ-171 |  |  | 17 | 14 | 17 | 0 | 0
#REF! | 0 | BQ-171 |  |  | 17 | 14 | 17 | 0 | 0
#REF! | 0 | BQ-171 |  |  | 17 | 14 | 17 | 0 | 0
#REF! | 1 | BQ-172 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-172 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-172 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-172 | INVOICE | 20 | 13 | 14 | 14 | 5060 | 0
#REF! | 0 | BQ-172 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-172 | INVOICE | 28 | 13 | 14 | 14 | 2530 | 0
#REF! | 0 | BQ-172 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-172 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-172 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-172 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-172 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-172 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-172 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-172 | OVERALL |  | 13 | 14 | 14 | 0 | 7590
#REF! | 0 | BQ-172 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-172 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-172 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-172 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-172 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-172 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-172 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-172 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-173 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-173 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-173 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-173 | INVOICE | 25 | 14 | 15 | 15 | 15840 | 0
#REF! | 0 | BQ-173 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-173 | INVOICE | 28 | 14 | 15 | 15 | 7920 | 0
#REF! | 0 | BQ-173 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-173 | INVOICE | 30 | 14 | 15 | 15 | 9720 | 0
#REF! | 0 | BQ-173 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-173 | INVOICE | 31 | 14 | 15 | 15 | 1080 | 0
#REF! | 0 | BQ-173 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-173 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-173 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-173 | OVERALL |  | 14 | 15 | 15 | 0 | 34560
#REF! | 0 | BQ-173 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-173 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-173 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-173 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-173 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-173 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-173 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-173 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-174 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-174 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-174 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-174 | INVOICE | 27 | 14 | 15 | 15 | 6468 | 0
#REF! | 0 | BQ-174 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-174 | INVOICE | 31 | 14 | 15 | 15 | 252 | 0
#REF! | 0 | BQ-174 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-174 | OVERALL |  | 14 | 15 | 15 | 0 | 6720
#REF! | 0 | BQ-174 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-174 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-174 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-174 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-174 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-174 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-174 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-174 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-175 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-175 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-175 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-175 | INVOICE | 13 | 14 | 15 | 15 | 8690 | 0
#REF! | 0 | BQ-175 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-175 | INVOICE | 27 | 14 | 15 | 15 | 14299 | 0
#REF! | 0 | BQ-175 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-175 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-175 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-175 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-175 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-175 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-175 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-175 | OVERALL |  | 14 | 15 | 15 | 0 | 22989
#REF! | 0 | BQ-175 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-175 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-175 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-175 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-175 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-175 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-175 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-175 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-176 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-176 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-176 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-176 | INVOICE | 27 | 14 | 15 | 15 | 2970 | 0
#REF! | 0 | BQ-176 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-176 | INVOICE | 28 | 14 | 15 | 15 | 990 | 0
#REF! | 0 | BQ-176 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-176 | OVERALL |  | 14 | 15 | 15 | 0 | 3960
#REF! | 0 | BQ-176 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-176 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-176 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-176 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-176 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-176 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-176 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-176 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-177 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-177 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-177 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-177 | INVOICE | 16 | 14 | 15 | 15 | 4340 | 0
#REF! | 0 | BQ-177 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-177 | INVOICE | 28 | 14 | 15 | 15 | 434 | 0
#REF! | 0 | BQ-177 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-177 | INVOICE | 31 | 14 | 15 | 15 | 186 | 0
#REF! | 0 | BQ-177 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-177 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-177 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-177 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-177 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-177 | OVERALL |  | 14 | 15 | 15 | 0 | 4960
#REF! | 0 | BQ-177 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-177 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-177 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-177 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-177 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-177 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-177 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-177 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-178 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-178 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-178 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-178 | INVOICE | 13 | 14 | 15 | 15 | 4340 | 0
#REF! | 0 | BQ-178 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-178 | INVOICE | 28 | 14 | 15 | 15 | 5208 | 0
#REF! | 0 | BQ-178 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-178 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-178 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-178 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-178 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-178 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-178 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-178 | OVERALL |  | 14 | 15 | 15 | 0 | 9548
#REF! | 0 | BQ-178 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-178 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-178 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-178 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-178 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-178 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-178 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-178 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-179 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-179 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-179 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-179 | INVOICE | 13 | 14 | 15 | 15 | 3080 | 0
#REF! | 0 | BQ-179 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-179 | INVOICE | 27 | 14 | 15 | 15 | 280 | 0
#REF! | 0 | BQ-179 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-179 | INVOICE | 28 | 14 | 15 | 15 | 1120 | 0
#REF! | 0 | BQ-179 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-179 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-179 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-179 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-179 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-179 | OVERALL |  | 14 | 15 | 15 | 0 | 4480
#REF! | 0 | BQ-179 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-179 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-179 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-179 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-179 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-179 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-179 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-179 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-180 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-180 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-180 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-180 | INVOICE | 26 | 14 | 15 | 15 | 1017.5 | 0
#REF! | 0 | BQ-180 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-180 | INVOICE | 28 | 14 | 15 | 15 | 323.75 | 0
#REF! | 0 | BQ-180 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-180 | INVOICE | 31 | 14 | 15 | 15 | 138.75 | 0
#REF! | 0 | BQ-180 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-180 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-180 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-180 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-180 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-180 | OVERALL |  | 14 | 15 | 15 | 0 | 1480
#REF! | 0 | BQ-180 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-180 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-180 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-180 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-180 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-180 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-180 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-180 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-181 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-181 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-181 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-181 | INVOICE | 14 | 14 | 15 | 15 | 1485 | 0
#REF! | 0 | BQ-181 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-181 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-181 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-181 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-181 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-181 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-181 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-181 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-181 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-181 | OVERALL |  | 14 | 15 | 15 | 0 | 1485
#REF! | 0 | BQ-181 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-181 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-181 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-181 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-181 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-181 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-181 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-181 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-182 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-182 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-182 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-182 | INVOICE | 14 | 14 | 15 | 15 | 154 | 0
#REF! | 0 | BQ-182 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-182 | INVOICE | 31 | 14 | 15 | 15 | 22 | 0
#REF! | 0 | BQ-182 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-182 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-182 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-182 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-182 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-182 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-182 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-182 | OVERALL |  | 14 | 15 | 15 | 0 | 176
#REF! | 0 | BQ-182 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-182 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-182 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-182 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-182 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-182 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-182 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-182 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-183 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-183 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-183 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-183 | INVOICE | 25 | 15 | 16 | 16 | 20790 | 0
#REF! | 0 | BQ-183 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-183 | INVOICE | 31 | 15 | 16 | 16 | -20790 | 0
#REF! | 0 | BQ-183 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-183 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-183 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-183 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-183 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-183 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-183 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-183 | OVERALL |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-183 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-183 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-183 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-183 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-183 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-183 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-183 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-183 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-184 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-184 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-184 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-184 | INVOICE | 21 | 14 | 15 | 15 | 92400 | 0
#REF! | 0 | BQ-184 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-184 | INVOICE | 31 | 14 | 15 | 15 | 9240 | 0
#REF! | 0 | BQ-184 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-184 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-184 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-184 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-184 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-184 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-184 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-184 | OVERALL |  | 14 | 15 | 15 | 0 | 101640
#REF! | 0 | BQ-184 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-184 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-184 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-184 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-184 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-184 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-184 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-184 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-185 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-185 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-185 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-185 | INVOICE | 14 | 14 | 15 | 15 | 88 | 0
#REF! | 0 | BQ-185 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-185 | INVOICE | 27 | 14 | 15 | 15 | 28 | 0
#REF! | 0 | BQ-185 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-185 | INVOICE | 31 | 14 | 15 | 15 | 12 | 0
#REF! | 0 | BQ-185 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-185 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-185 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-185 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-185 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-185 | OVERALL |  | 14 | 15 | 15 | 0 | 128
#REF! | 0 | BQ-185 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-185 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-185 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-185 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-185 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-185 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-185 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-185 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-186 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-186 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-186 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-186 | INVOICE | 14 | 14 | 15 | 15 | 660 | 0
#REF! | 0 | BQ-186 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-186 | INVOICE | 27 | 14 | 15 | 15 | 210 | 0
#REF! | 0 | BQ-186 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-186 | INVOICE | 31 | 14 | 15 | 15 | 90 | 0
#REF! | 0 | BQ-186 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-186 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-186 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-186 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-186 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-186 | OVERALL |  | 14 | 15 | 15 | 0 | 960
#REF! | 0 | BQ-186 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-186 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-186 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-186 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-186 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-186 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-186 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-186 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-187 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-187 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-187 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-187 | INVOICE | 14 | 14 | 15 | 15 | 132 | 0
#REF! | 0 | BQ-187 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-187 | INVOICE | 31 | 14 | 15 | 15 | 60 | 0
#REF! | 0 | BQ-187 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-187 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-187 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-187 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-187 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-187 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-187 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-187 | OVERALL |  | 14 | 15 | 15 | 0 | 192
#REF! | 0 | BQ-187 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-187 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-187 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-187 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-187 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-187 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-187 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-187 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-188 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-188 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-188 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-188 | INVOICE | 14 | 14 | 15 | 15 | 104.5 | 0
#REF! | 0 | BQ-188 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-188 | INVOICE | 27 | 14 | 15 | 15 | 33.25 | 0
#REF! | 0 | BQ-188 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-188 | INVOICE | 31 | 14 | 15 | 15 | 14.25 | 0
#REF! | 0 | BQ-188 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-188 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-188 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-188 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-188 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-188 | OVERALL |  | 14 | 15 | 15 | 0 | 152
#REF! | 0 | BQ-188 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-188 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-188 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-188 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-188 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-188 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-188 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-188 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-189 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-189 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-189 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-189 | INVOICE | 27 | 14 | 15 | 15 | 3312 | 0
#REF! | 0 | BQ-189 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-189 | INVOICE | 28 | 14 | 15 | 15 | 368 | 0
#REF! | 0 | BQ-189 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-189 | OVERALL |  | 14 | 15 | 15 | 0 | 3680
#REF! | 0 | BQ-189 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-189 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-189 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-189 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-189 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-189 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-189 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-189 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-190 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-190 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-190 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-190 | INVOICE | 27 | 14 | 15 | 15 | 1656 | 0
#REF! | 0 | BQ-190 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-190 | INVOICE | 28 | 14 | 15 | 15 | 184 | 0
#REF! | 0 | BQ-190 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-190 | OVERALL |  | 14 | 15 | 15 | 0 | 1840
#REF! | 0 | BQ-190 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-190 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-190 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-190 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-190 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-190 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-190 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-190 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-191 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-191 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-191 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-191 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-191 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-191 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-191 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-191 | OVERALL |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-191 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-191 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-191 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-191 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-191 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-191 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-191 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-191 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-192 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-192 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-192 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-192 | INVOICE | 13 | 15 | 16 | 16 | 1430 | 0
#REF! | 0 | BQ-192 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-192 | INVOICE | 27 | 15 | 16 | 16 | 455 | 0
#REF! | 0 | BQ-192 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-192 | INVOICE | 28 | 15 | 16 | 16 | 260 | 0
#REF! | 0 | BQ-192 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-192 | INVOICE | 31 | 15 | 16 | 16 | -65 | 0
#REF! | 0 | BQ-192 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-192 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-192 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-192 | OVERALL |  | 15 | 16 | 16 | 0 | 2080
#REF! | 0 | BQ-192 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-192 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-192 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-192 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-192 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-192 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-192 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-192 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-193 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-193 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-193 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-193 | INVOICE | 15 | 15 | 16 | 16 | 61820 | 0
#REF! | 0 | BQ-193 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-193 | INVOICE | 27 | 15 | 16 | 16 | 60415 | 0
#REF! | 0 | BQ-193 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-193 | INVOICE | 28 | 15 | 16 | 16 | 4215 | 0
#REF! | 0 | BQ-193 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-193 | INVOICE | 29 | 15 | 16 | 16 | -4215 | 0
#REF! | 0 | BQ-193 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-193 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-193 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-193 | OVERALL |  | 15 | 16 | 16 | 0 | 122235
#REF! | 0 | BQ-193 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-193 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-193 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-193 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-193 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-193 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-193 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-193 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-194 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-194 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-194 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-194 | INVOICE | 26 | 14 | 15 | 15 | 2310 | 0
#REF! | 0 | BQ-194 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-194 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-194 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-194 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-194 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-194 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-194 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-194 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-194 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-194 | OVERALL |  | 14 | 15 | 15 | 0 | 2310
#REF! | 0 | BQ-194 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-194 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-194 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-194 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-194 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-194 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-194 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-194 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-195 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-195 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-195 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-195 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-195 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-195 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-195 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-195 | OVERALL |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-195 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-195 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-195 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-195 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-195 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-195 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-195 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-195 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-196 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-196 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-196 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-196 | INVOICE | 15 | 14 | 15 | 15 | 1980 | 0
#REF! | 0 | BQ-196 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-196 | INVOICE | 28 | 14 | 15 | 15 | 990 | 0
#REF! | 0 | BQ-196 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-196 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-196 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-196 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-196 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-196 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-196 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-196 | OVERALL |  | 14 | 15 | 15 | 0 | 2970
#REF! | 0 | BQ-196 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-196 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-196 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-196 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-196 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-196 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-196 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-196 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-197 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-197 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-197 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-197 | INVOICE | 12 | 15 | 16 | 16 | 1595 | 0
#REF! | 0 | BQ-197 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-197 | INVOICE | 27 | 15 | 16 | 16 | 6887.5 | 0
#REF! | 0 | BQ-197 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-197 | INVOICE | 28 | 15 | 16 | 16 | 217.5 | 0
#REF! | 0 | BQ-197 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-197 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-197 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-197 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-197 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-197 | OVERALL |  | 15 | 16 | 16 | 0 | 8700
#REF! | 0 | BQ-197 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-197 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-197 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-197 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-197 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-197 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-197 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-197 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-198 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-198 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-198 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-198 | INVOICE | 27 | 14 | 15 | 15 | 6090 | 0
#REF! | 0 | BQ-198 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-198 | INVOICE | 31 | 14 | 15 | 15 | 630 | 0
#REF! | 0 | BQ-198 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-198 | OVERALL |  | 14 | 15 | 15 | 0 | 6720
#REF! | 0 | BQ-198 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-198 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-198 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-198 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-198 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-198 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-198 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-198 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-199 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-199 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-199 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-199 | INVOICE | 27 | 14 | 15 | 15 | 6090 | 0
#REF! | 0 | BQ-199 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-199 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-199 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-199 | OVERALL |  | 14 | 15 | 15 | 0 | 6090
#REF! | 0 | BQ-199 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-199 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-199 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-199 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-199 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-199 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-199 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-199 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 1 | BQ-200 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-200 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-200 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-200 | INVOICE | 15 | 16 | 17 | 17 | 3552 | 0
#REF! | 0 | BQ-200 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-200 | INVOICE | 27 | 16 | 17 | 17 | -1776 | 0
#REF! | 0 | BQ-200 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-200 | INVOICE | 31 | 16 | 17 | 17 | 532.8 | 0
#REF! | 0 | BQ-200 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-200 | INVOICE | 32 | 16 | 17 | 17 | 888 | 0
#REF! | 0 | BQ-200 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-200 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-200 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-200 | OVERALL |  | 16 | 17 | 17 | 0 | 3196.8
#REF! | 0 | BQ-200 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-200 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-200 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-200 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-200 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-200 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-200 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | BQ-200 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 1 | BQ-201 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-201 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-201 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-201 | INVOICE | 18 | 14 | 15 | 15 | 266090 | 0
#REF! | 0 | BQ-201 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-201 | INVOICE | 24 | 14 | 15 | 15 | 144402.5 | 0
#REF! | 0 | BQ-201 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-201 | INVOICE | 27 | 14 | 15 | 15 | 19617.5 | 0
#REF! | 0 | BQ-201 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-201 | INVOICE | 30 | 14 | 15 | 15 | 47790 | 0
#REF! | 0 | BQ-201 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-201 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-201 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-201 | OVERALL |  | 14 | 15 | 15 | 0 | 477900
#REF! | 0 | BQ-201 |  |  | 14 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-201 |  |  | 14 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-201 |  |  | 14 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-201 |  |  | 14 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-201 |  |  | 14 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-201 |  |  | 14 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-201 |  |  | 14 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-201 |  |  | 14 | 25 | 25 | 0 | 0
#REF! | 1 | BQ-202 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-202 | INVOICE | 21 | 24 | 25 | 25 | 279136 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-202 | INVOICE | 22 | 24 | 25 | 25 | 116688 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-202 | INVOICE | 23 | 24 | 25 | 25 | 51480 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-202 | INVOICE | 24 | 24 | 25 | 25 | 41184 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-202 | INVOICE | 25 | 24 | 25 | 25 | 307758 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-202 | INVOICE | 26 | 24 | 25 | 25 | 39897 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-202 | INVOICE | 27 | 24 | 25 | 25 | 210837 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-202 | INVOICE | 28 | 24 | 25 | 25 | 243540 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-202 | INVOICE | 29 | 24 | 25 | 25 | 21340 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-202 | INVOICE | 31 | 24 | 25 | 25 | 172700 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-202 | INVOICE | 32 | 24 | 25 | 25 | 240240 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 25 | 25 | 0 | 0
#REF! | 0 | BQ-202 | OVERALL |  | 24 | 25 | 25 | 0 | 1742400
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 0 | BQ-202 |  |  | 24 | 15 | 24 | 0 | 0
#REF! | 1 | NBQ-023 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-023 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-023 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-023 | INVOICE | 28 | 14 | 15 | 15 | 4495 | 0
#REF! | 0 | NBQ-023 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-023 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-023 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-023 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-023 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-023 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-023 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-023 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-023 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-023 | OVERALL |  | 14 | 15 | 15 | 0 | 4495
#REF! | 0 | NBQ-023 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-023 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-023 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-023 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-023 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-023 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-023 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-023 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 | OVERALL |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-024 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | NBQ-025 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-025 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-025 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-025 | INVOICE | 27 | 14 | 15 | 15 | 18850 | 0
#REF! | 0 | NBQ-025 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-025 | INVOICE | 29 | 14 | 15 | 15 | 72500 | 0
#REF! | 0 | NBQ-025 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-025 | INVOICE | 32 | 14 | 15 | 15 | 13050 | 0
#REF! | 0 | NBQ-025 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-025 | OVERALL |  | 14 | 15 | 15 | 0 | 104400
#REF! | 0 | NBQ-025 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-025 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-025 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-025 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-025 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-025 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-025 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-025 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | CR1-026 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-026 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-026 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-026 | INVOICE | 27 | 14 | 15 | 15 | 292500 | 0
#REF! | 0 | CR1-026 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-026 | INVOICE | 28 | 14 | 15 | 15 | 47500 | 0
#REF! | 0 | CR1-026 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-026 | INVOICE | 29 | 14 | 15 | 15 | -47500 | 0
#REF! | 0 | CR1-026 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-026 | INVOICE | 30 | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-026 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-026 | OVERALL |  | 14 | 15 | 15 | 0 | 360000
#REF! | 0 | CR1-026 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-026 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-026 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-026 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-026 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-026 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-026 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-026 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 1 | CR1-027 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-027 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-027 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-027 | INVOICE | 30 | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-027 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-027 | OVERALL |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-027 |  |  | 12 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-027 |  |  | 12 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-027 |  |  | 12 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-027 |  |  | 12 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-027 |  |  | 12 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-027 |  |  | 12 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-027 |  |  | 12 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-027 |  |  | 12 | 15 | 15 | 0 | 0
#REF! | 1 | CR1-028 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-028 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-028 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-028 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-028 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-028 | OVERALL |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-028 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-028 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-028 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-028 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-028 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-028 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-028 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-028 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 1 | CR1-029 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-029 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-029 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-029 | INVOICE | 27 | 16 | 17 | 17 | 532597.8 | 0
#REF! | 0 | CR1-029 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-029 | INVOICE | 29 | 16 | 17 | 17 | 6157.2 | 0
#REF! | 0 | CR1-029 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-029 | INVOICE | 30 | 16 | 17 | 17 | 61572 | 0
#REF! | 0 | CR1-029 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-029 | OVERALL |  | 16 | 17 | 17 | 0 | 600327
#REF! | 0 | CR1-029 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | CR1-029 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | CR1-029 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | CR1-029 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | CR1-029 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | CR1-029 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | CR1-029 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 0 | CR1-029 |  |  | 16 | 15 | 16 | 0 | 0
#REF! | 1 | CR1-030 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-030 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-030 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-030 | INVOICE | 31 | 14 | 15 | 15 | 49800 | 0
#REF! | 0 | CR1-030 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-030 | OVERALL |  | 14 | 15 | 15 | 0 | 49800
#REF! | 0 | CR1-030 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-030 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-030 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-030 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-030 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-030 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-030 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-030 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 1 | CR1-031 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-031 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-031 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-031 | INVOICE | 27 | 12 | 13 | 13 | 675000 | 0
#REF! | 0 | CR1-031 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-031 | INVOICE | 28 | 12 | 13 | 13 | 191643.75 | 0
#REF! | 0 | CR1-031 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-031 | INVOICE | 30 | 12 | 13 | 13 | 96293.75 | 0
#REF! | 0 | CR1-031 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-031 | INVOICE | 31 | 12 | 13 | 13 | 30250 | 0
#REF! | 0 | CR1-031 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-031 | OVERALL |  | 12 | 13 | 13 | 0 | 993187.5
#REF! | 0 | CR1-031 |  |  | 12 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-031 |  |  | 12 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-031 |  |  | 12 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-031 |  |  | 12 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-031 |  |  | 12 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-031 |  |  | 12 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-031 |  |  | 12 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-031 |  |  | 12 | 15 | 15 | 0 | 0
#REF! | 1 | CR1-032 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-032 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-032 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-032 | INVOICE | 29 | 14 | 15 | 15 | 259056 | 0
#REF! | 0 | CR1-032 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-032 | INVOICE | 32 | 14 | 15 | 15 | 8784 | 0
#REF! | 0 | CR1-032 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-032 | OVERALL |  | 14 | 15 | 15 | 0 | 267840
#REF! | 0 | CR1-032 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-032 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-032 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-032 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-032 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-032 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-032 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-032 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-203 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-203 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-203 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-203 | INVOICE | 13 | 15 | 16 | 16 | 8580 | 0
#REF! | 0 | BQ-203 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-203 | INVOICE | 27 | 15 | 16 | 16 | 2730 | 0
#REF! | 0 | BQ-203 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-203 | INVOICE | 28 | 15 | 16 | 16 | 1170 | 0
#REF! | 0 | BQ-203 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-203 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-203 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-203 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-203 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-203 | OVERALL |  | 15 | 16 | 16 | 0 | 12480
#REF! | 0 | BQ-203 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-203 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-203 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-203 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-203 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-203 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-203 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-203 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-204 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-204 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-204 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-204 | INVOICE | 13 | 15 | 16 | 16 | 5280 | 0
#REF! | 0 | BQ-204 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-204 | INVOICE | 27 | 15 | 16 | 16 | 1680 | 0
#REF! | 0 | BQ-204 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-204 | INVOICE | 28 | 15 | 16 | 16 | 720 | 0
#REF! | 0 | BQ-204 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-204 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-204 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-204 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-204 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-204 | OVERALL |  | 15 | 16 | 16 | 0 | 7680
#REF! | 0 | BQ-204 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-204 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-204 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-204 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-204 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-204 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-204 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-204 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 1 | BQ-205 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-205 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-205 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-205 | INVOICE | 23 | 17 | 18 | 18 | 2722.5 | 0
#REF! | 0 | BQ-205 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-205 | INVOICE | 27 | 17 | 18 | 18 | 1237.5 | 0
#REF! | 0 | BQ-205 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-205 | INVOICE | 28 | 17 | 18 | 18 | 495 | 0
#REF! | 0 | BQ-205 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-205 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-205 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-205 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-205 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-205 | OVERALL |  | 17 | 18 | 18 | 0 | 4455
#REF! | 0 | BQ-205 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-205 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-205 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-205 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-205 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-205 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-205 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | BQ-205 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 1 | BQ-206 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-206 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-206 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-206 | INVOICE | 24 | 15 | 16 | 16 | 7975 | 0
#REF! | 0 | BQ-206 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-206 | INVOICE | 27 | 15 | 16 | 16 | 2247.5 | 0
#REF! | 0 | BQ-206 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-206 | INVOICE | 28 | 15 | 16 | 16 | 652.5 | 0
#REF! | 0 | BQ-206 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-206 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-206 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-206 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-206 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-206 | OVERALL |  | 15 | 16 | 16 | 0 | 10875
#REF! | 0 | BQ-206 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-206 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-206 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-206 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-206 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-206 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-206 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-206 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-207 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-207 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-207 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-207 | INVOICE | 13 | 14 | 15 | 15 | 8690 | 0
#REF! | 0 | BQ-207 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-207 | INVOICE | 27 | 14 | 15 | 15 | 2449 | 0
#REF! | 0 | BQ-207 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-207 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-207 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-207 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-207 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-207 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-207 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-207 | OVERALL |  | 14 | 15 | 15 | 0 | 11139
#REF! | 0 | BQ-207 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-207 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-207 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-207 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-207 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-207 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-207 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-207 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-208 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-208 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-208 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-208 | INVOICE | 14 | 14 | 15 | 15 | 627 | 0
#REF! | 0 | BQ-208 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-208 | INVOICE | 27 | 14 | 15 | 15 | -76 | 0
#REF! | 0 | BQ-208 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-208 | INVOICE | 31 | 14 | 15 | 15 | 57 | 0
#REF! | 0 | BQ-208 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-208 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-208 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-208 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-208 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-208 | OVERALL |  | 14 | 15 | 15 | 0 | 608
#REF! | 0 | BQ-208 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-208 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-208 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-208 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-208 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-208 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-208 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-208 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-209 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-209 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-209 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-209 | INVOICE | 14 | 14 | 15 | 15 | 1320 | 0
#REF! | 0 | BQ-209 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-209 | INVOICE | 27 | 14 | 15 | 15 | 420 | 0
#REF! | 0 | BQ-209 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-209 | INVOICE | 31 | 14 | 15 | 15 | 180 | 0
#REF! | 0 | BQ-209 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-209 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-209 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-209 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-209 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-209 | OVERALL |  | 14 | 15 | 15 | 0 | 1920
#REF! | 0 | BQ-209 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-209 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-209 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-209 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-209 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-209 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-209 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-209 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-210 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-210 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-210 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-210 | INVOICE | 14 | 14 | 15 | 15 | 264 | 0
#REF! | 0 | BQ-210 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-210 | INVOICE | 31 | 14 | 15 | 15 | 120 | 0
#REF! | 0 | BQ-210 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-210 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-210 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-210 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-210 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-210 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-210 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-210 | OVERALL |  | 14 | 15 | 15 | 0 | 384
#REF! | 0 | BQ-210 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-210 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-210 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-210 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-210 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-210 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-210 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-210 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-211 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-211 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-211 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-211 | INVOICE | 14 | 14 | 15 | 15 | 88 | 0
#REF! | 0 | BQ-211 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-211 | INVOICE | 27 | 14 | 15 | 15 | 28 | 0
#REF! | 0 | BQ-211 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-211 | INVOICE | 28 | 14 | 15 | 15 | 88 | 0
#REF! | 0 | BQ-211 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-211 | INVOICE | 31 | 14 | 15 | 15 | 52 | 0
#REF! | 0 | BQ-211 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-211 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-211 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-211 | OVERALL |  | 14 | 15 | 15 | 0 | 256
#REF! | 0 | BQ-211 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-211 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-211 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-211 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-211 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-211 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-211 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-211 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-212 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-212 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-212 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-212 | INVOICE | 12 | 14 | 15 | 15 | 16800 | 0
#REF! | 0 | BQ-212 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-212 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-212 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-212 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-212 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-212 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-212 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-212 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-212 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-212 | OVERALL |  | 14 | 15 | 15 | 0 | 16800
#REF! | 0 | BQ-212 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-212 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-212 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-212 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-212 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-212 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-212 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-212 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-213 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-213 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-213 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-213 | INVOICE | 24 | 14 | 15 | 15 | 27720 | 0
#REF! | 0 | BQ-213 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-213 | INVOICE | 32 | 14 | 15 | 15 | 55440 | 0
#REF! | 0 | BQ-213 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-213 | OVERALL |  | 14 | 15 | 15 | 0 | 83160
#REF! | 0 | BQ-213 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-213 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-213 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-213 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-213 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-213 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-213 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-213 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-214 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-214 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-214 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-214 | INVOICE | 27 | 14 | 15 | 15 | 3312 | 0
#REF! | 0 | BQ-214 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-214 | INVOICE | 28 | 14 | 15 | 15 | 184 | 0
#REF! | 0 | BQ-214 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-214 | OVERALL |  | 14 | 15 | 15 | 0 | 3496
#REF! | 0 | BQ-214 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-214 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-214 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-214 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-214 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-214 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-214 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-214 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-215 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-215 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-215 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-215 | INVOICE | 27 | 14 | 15 | 15 | 1656 | 0
#REF! | 0 | BQ-215 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-215 | INVOICE | 28 | 14 | 15 | 15 | 184 | 0
#REF! | 0 | BQ-215 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-215 | OVERALL |  | 14 | 15 | 15 | 0 | 1840
#REF! | 0 | BQ-215 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-215 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-215 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-215 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-215 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-215 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-215 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-215 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-216 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-216 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-216 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-216 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-216 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-216 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-216 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-216 | OVERALL |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-216 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-216 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-216 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-216 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-216 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-216 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-216 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-216 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-217 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-217 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-217 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-217 | INVOICE | 16 | 14 | 15 | 15 | 4340 | 0
#REF! | 0 | BQ-217 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-217 | INVOICE | 28 | 14 | 15 | 15 | 434 | 0
#REF! | 0 | BQ-217 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-217 | INVOICE | 32 | 14 | 15 | 15 | 186 | 0
#REF! | 0 | BQ-217 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-217 | OVERALL |  | 14 | 15 | 15 | 0 | 4960
#REF! | 0 | BQ-217 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-217 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-217 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-217 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-217 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-217 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-217 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-217 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-218 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-218 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-218 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-218 | INVOICE | 28 | 15 | 16 | 16 | 990 | 0
#REF! | 0 | BQ-218 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-218 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-218 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-218 | OVERALL |  | 15 | 16 | 16 | 0 | 990
#REF! | 0 | BQ-218 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-218 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-218 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-218 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-218 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-218 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-218 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-218 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-219 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-219 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-219 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-219 | INVOICE | 14 | 14 | 15 | 15 | 1155 | 0
#REF! | 0 | BQ-219 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-219 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-219 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-219 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-219 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-219 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-219 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-219 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-219 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-219 | OVERALL |  | 14 | 15 | 15 | 0 | 1155
#REF! | 0 | BQ-219 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-219 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-219 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-219 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-219 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-219 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-219 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-219 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-220 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-220 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-220 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-220 | INVOICE | 13 | 14 | 15 | 15 | 13580 | 0
#REF! | 0 | BQ-220 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-220 | INVOICE | 28 | 14 | 15 | 15 | 1358 | 0
#REF! | 0 | BQ-220 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-220 | INVOICE | 32 | 14 | 15 | 15 | 582 | 0
#REF! | 0 | BQ-220 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-220 | OVERALL |  | 14 | 15 | 15 | 0 | 15520
#REF! | 0 | BQ-220 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-220 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-220 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-220 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-220 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-220 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-220 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-220 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-221 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-221 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-221 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-221 | INVOICE | 10 | 14 | 15 | 15 | 106400 | 0
#REF! | 0 | BQ-221 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-221 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-221 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-221 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-221 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-221 | OVERALL |  | 14 | 15 | 15 | 0 | 106400
#REF! | 0 | BQ-221 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-221 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-221 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-221 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-221 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-221 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-221 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-221 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-222 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-222 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-222 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-222 | INVOICE | 21 | 14 | 15 | 15 | 92400 | 0
#REF! | 0 | BQ-222 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-222 | INVOICE | 31 | 14 | 15 | 15 | 9240 | 0
#REF! | 0 | BQ-222 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-222 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-222 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-222 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-222 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-222 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-222 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-222 | OVERALL |  | 14 | 15 | 15 | 0 | 101640
#REF! | 0 | BQ-222 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-222 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-222 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-222 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-222 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-222 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-222 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-222 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | BQ-223 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-223 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-223 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-223 | INVOICE | 12 | 14 | 15 | 15 | 910 | 0
#REF! | 0 | BQ-223 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-223 | INVOICE | 31 | 14 | 15 | 15 | 91 | 0
#REF! | 0 | BQ-223 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-223 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-223 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-223 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-223 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-223 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-223 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-223 | OVERALL |  | 14 | 15 | 15 | 0 | 1001
#REF! | 0 | BQ-223 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-223 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-223 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-223 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-223 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-223 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-223 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-223 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-224 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-224 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-224 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-224 | INVOICE | 25 | 15 | 16 | 16 | 20790 | 0
#REF! | 0 | BQ-224 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-224 | INVOICE | 30 | 15 | 16 | 16 | 2970 | 0
#REF! | 0 | BQ-224 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-224 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-224 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-224 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-224 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-224 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-224 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-224 | OVERALL |  | 15 | 16 | 16 | 0 | 23760
#REF! | 0 | BQ-224 |  |  | 15 | 13 | 15 | 0 | 0
#REF! | 0 | BQ-224 |  |  | 15 | 13 | 15 | 0 | 0
#REF! | 0 | BQ-224 |  |  | 15 | 13 | 15 | 0 | 0
#REF! | 0 | BQ-224 |  |  | 15 | 13 | 15 | 0 | 0
#REF! | 0 | BQ-224 |  |  | 15 | 13 | 15 | 0 | 0
#REF! | 0 | BQ-224 |  |  | 15 | 13 | 15 | 0 | 0
#REF! | 0 | BQ-224 |  |  | 15 | 13 | 15 | 0 | 0
#REF! | 0 | BQ-224 |  |  | 15 | 13 | 15 | 0 | 0
#REF! | 1 | BQ-225 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-225 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-225 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-225 | INVOICE | 17 | 12 | 13 | 13 | 12490.5 | 0
#REF! | 0 | BQ-225 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-225 | INVOICE | 24 | 12 | 13 | 13 | 2271 | 0
#REF! | 0 | BQ-225 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-225 | INVOICE | 25 | 12 | 13 | 13 | 5677.5 | 0
#REF! | 0 | BQ-225 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-225 | INVOICE | 30 | 12 | 13 | 13 | 2271 | 0
#REF! | 0 | BQ-225 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-225 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-225 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-225 | OVERALL |  | 12 | 13 | 13 | 0 | 22710
#REF! | 0 | BQ-225 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-225 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-225 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-225 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-225 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-225 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-225 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-225 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 1 | BQ-226 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-226 | INVOICE | 21 | 23 | 24 | 24 | 509535 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-226 | INVOICE | 22 | 23 | 24 | 24 | 403650 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-226 | INVOICE | 23 | 23 | 24 | 24 | 114075 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-226 | INVOICE | 24 | 23 | 24 | 24 | 176816.25 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-226 | INVOICE | 25 | 23 | 24 | 24 | 93453.75 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-226 | INVOICE | 26 | 23 | 24 | 24 | 325845 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-226 | INVOICE | 27 | 23 | 24 | 24 | 345091.5 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-226 | INVOICE | 28 | 23 | 24 | 24 | 58500 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-226 | INVOICE | 29 | 23 | 24 | 24 | 55633.5 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-226 | INVOICE | 31 | 23 | 24 | 24 | 210600 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | BQ-226 | OVERALL |  | 23 | 24 | 24 | 0 | 2316600
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | BQ-226 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 1 | CR1-033 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-033 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-033 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-033 | INVOICE | 27 | 13 | 14 | 14 | 24715.8 | 0
#REF! | 0 | CR1-033 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-033 | INVOICE | 31 | 13 | 14 | 14 | 2746.2 | 0
#REF! | 0 | CR1-033 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-033 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-033 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-033 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-033 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-033 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-033 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-033 | OVERALL |  | 13 | 14 | 14 | 0 | 27462
#REF! | 0 | CR1-033 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-033 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-033 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-033 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-033 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-033 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-033 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-033 |  |  | 13 | 15 | 15 | 0 | 0
#REF! | 1 | CR1-034 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-034 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-034 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-034 | INVOICE | 27 | 14 | 15 | 15 | 24715.8 | 0
#REF! | 0 | CR1-034 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-034 | INVOICE | 31 | 14 | 15 | 15 | 2746.2 | 0
#REF! | 0 | CR1-034 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | CR1-034 | OVERALL |  | 14 | 15 | 15 | 0 | 27462
#REF! | 0 | CR1-034 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-034 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-034 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-034 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-034 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-034 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-034 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 0 | CR1-034 |  |  | 14 | 13 | 14 | 0 | 0
#REF! | 1 | CR1-035 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-035 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-035 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-035 | INVOICE | 27 | 12 | 13 | 13 | 37072.8 | 0
#REF! | 0 | CR1-035 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-035 | INVOICE | 31 | 12 | 13 | 13 | 4119.2 | 0
#REF! | 0 | CR1-035 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-035 | OVERALL |  | 12 | 13 | 13 | 0 | 41192
#REF! | 0 | CR1-035 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-035 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-035 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-035 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-035 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-035 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-035 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-035 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 1 | CR1-036 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-036 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-036 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-036 | INVOICE | 27 | 12 | 13 | 13 | 12357.9 | 0
#REF! | 0 | CR1-036 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-036 | INVOICE | 31 | 12 | 13 | 13 | 1373.1 | 0
#REF! | 0 | CR1-036 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-036 | OVERALL |  | 12 | 13 | 13 | 0 | 13731
#REF! | 0 | CR1-036 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-036 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-036 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-036 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-036 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-036 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-036 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-036 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 1 | CR1-037 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-037 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-037 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-037 | INVOICE | 27 | 12 | 13 | 13 | 24715.8 | 0
#REF! | 0 | CR1-037 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-037 | INVOICE | 31 | 12 | 13 | 13 | 2746.2 | 0
#REF! | 0 | CR1-037 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | CR1-037 | OVERALL |  | 12 | 13 | 13 | 0 | 27462
#REF! | 0 | CR1-037 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-037 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-037 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-037 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-037 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-037 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-037 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-037 |  |  | 12 | 24 | 24 | 0 | 0
#REF! | 1 | CR1-038 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-038 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-038 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-038 | INVOICE | 27 | 23 | 24 | 24 | 49430.7 | 0
#REF! | 0 | CR1-038 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-038 | INVOICE | 31 | 23 | 24 | 24 | 5492.3 | 0
#REF! | 0 | CR1-038 |  |  | 23 | 24 | 24 | 0 | 0
#REF! | 0 | CR1-038 | OVERALL |  | 23 | 24 | 24 | 0 | 54923
#REF! | 0 | CR1-038 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | CR1-038 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | CR1-038 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | CR1-038 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | CR1-038 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | CR1-038 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | CR1-038 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 0 | CR1-038 |  |  | 23 | 14 | 23 | 0 | 0
#REF! | 1 | CR1-039 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-039 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-039 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-039 | INVOICE | 27 | 13 | 14 | 14 | 29658.6 | 0
#REF! | 0 | CR1-039 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-039 | INVOICE | 31 | 13 | 14 | 14 | 3295.4 | 0
#REF! | 0 | CR1-039 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-039 | OVERALL |  | 13 | 14 | 14 | 0 | 32954
#REF! | 0 | CR1-039 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-039 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-039 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-039 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-039 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-039 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-039 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-039 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 1 | CR1-040 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-040 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-040 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-040 | INVOICE | 27 | 13 | 14 | 14 | 24166.4 | 0
#REF! | 0 | CR1-040 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-040 | INVOICE | 28 | 13 | 14 | 14 | 3020.8 | 0
#REF! | 0 | CR1-040 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-040 | INVOICE | 31 | 13 | 14 | 14 | 3020.8 | 0
#REF! | 0 | CR1-040 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-040 | OVERALL |  | 13 | 14 | 14 | 0 | 30208
#REF! | 0 | CR1-040 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-040 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-040 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-040 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-040 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-040 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-040 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-040 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 1 | CR1-041 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-041 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-041 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-041 | INVOICE | 27 | 15 | 16 | 16 | 8788 | 0
#REF! | 0 | CR1-041 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-041 | INVOICE | 28 | 15 | 16 | 16 | 1098.5 | 0
#REF! | 0 | CR1-041 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-041 | INVOICE | 31 | 15 | 16 | 16 | 1098.5 | 0
#REF! | 0 | CR1-041 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-041 | OVERALL |  | 15 | 16 | 16 | 0 | 10985
#REF! | 0 | CR1-041 |  |  | 15 | 14 | 15 | 0 | 0
#REF! | 0 | CR1-041 |  |  | 15 | 14 | 15 | 0 | 0
#REF! | 0 | CR1-041 |  |  | 15 | 14 | 15 | 0 | 0
#REF! | 0 | CR1-041 |  |  | 15 | 14 | 15 | 0 | 0
#REF! | 0 | CR1-041 |  |  | 15 | 14 | 15 | 0 | 0
#REF! | 0 | CR1-041 |  |  | 15 | 14 | 15 | 0 | 0
#REF! | 0 | CR1-041 |  |  | 15 | 14 | 15 | 0 | 0
#REF! | 0 | CR1-041 |  |  | 15 | 14 | 15 | 0 | 0
#REF! | 1 | CR1-042 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-042 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-042 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-042 | INVOICE | 27 | 13 | 14 | 14 | 6590.4 | 0
#REF! | 0 | CR1-042 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-042 | INVOICE | 30 | 13 | 14 | 14 | 823.8 | 0
#REF! | 0 | CR1-042 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-042 | INVOICE | 31 | 13 | 14 | 14 | 823.8 | 0
#REF! | 0 | CR1-042 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | CR1-042 | OVERALL |  | 13 | 14 | 14 | 0 | 8238
#REF! | 0 | CR1-042 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-042 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-042 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-042 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-042 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-042 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-042 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-042 |  |  | 13 | 16 | 16 | 0 | 0
#REF! | 1 | NBQ-043 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-043 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-043 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-043 | INVOICE | 27 | 15 | 16 | 16 | 2102.5 | 0
#REF! | 0 | NBQ-043 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-043 | INVOICE | 28 | 15 | 16 | 16 | 217.5 | 0
#REF! | 0 | NBQ-043 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-043 | OVERALL |  | 15 | 16 | 16 | 0 | 2320
#REF! | 0 | NBQ-043 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-043 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-043 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-043 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-043 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-043 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-043 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-043 |  |  | 15 | 15 | 15 | 0 | 0
#REF! | 1 | NBQ-044 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-044 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-044 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-044 | INVOICE | 27 | 14 | 15 | 15 | 2291 | 0
#REF! | 0 | NBQ-044 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-044 | INVOICE | 31 | 14 | 15 | 15 | 158 | 0
#REF! | 0 | NBQ-044 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-044 | INVOICE | 32 | 14 | 15 | 15 | 79 | 0
#REF! | 0 | NBQ-044 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-044 | OVERALL |  | 14 | 15 | 15 | 0 | 2528
#REF! | 0 | NBQ-044 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-044 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-044 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-044 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-044 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-044 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-044 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-044 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | NBQ-045 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-045 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-045 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-045 | INVOICE | 27 | 14 | 15 | 15 | 137.75 | 0
#REF! | 0 | NBQ-045 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-045 | INVOICE | 31 | 14 | 15 | 15 | 9.5 | 0
#REF! | 0 | NBQ-045 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-045 | INVOICE | 32 | 14 | 15 | 15 | 4.75 | 0
#REF! | 0 | NBQ-045 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-045 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-045 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-045 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-045 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-045 | OVERALL |  | 14 | 15 | 15 | 0 | 152
#REF! | 0 | NBQ-045 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-045 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-045 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-045 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-045 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-045 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-045 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-045 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | NBQ-046 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-046 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-046 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-046 | INVOICE | 27 | 14 | 15 | 15 | 870 | 0
#REF! | 0 | NBQ-046 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-046 | INVOICE | 31 | 14 | 15 | 15 | 60 | 0
#REF! | 0 | NBQ-046 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-046 | INVOICE | 32 | 14 | 15 | 15 | 30 | 0
#REF! | 0 | NBQ-046 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-046 | OVERALL |  | 14 | 15 | 15 | 0 | 960
#REF! | 0 | NBQ-046 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-046 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-046 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-046 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-046 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-046 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-046 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-046 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | NBQ-047 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-047 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-047 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-047 | INVOICE | 28 | 14 | 15 | 15 | 88 | 0
#REF! | 0 | NBQ-047 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-047 | INVOICE | 31 | 14 | 15 | 15 | 40 | 0
#REF! | 0 | NBQ-047 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-047 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-047 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-047 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-047 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-047 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-047 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-047 | OVERALL |  | 14 | 15 | 15 | 0 | 128
#REF! | 0 | NBQ-047 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-047 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-047 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-047 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-047 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-047 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-047 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-047 |  |  | 14 | 16 | 16 | 0 | 0
#REF! | 1 | NBQ-048 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-048 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-048 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-048 | INVOICE | 28 | 15 | 16 | 16 | 1760 | 0
#REF! | 0 | NBQ-048 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-048 | INVOICE | 31 | 15 | 16 | 16 | 800 | 0
#REF! | 0 | NBQ-048 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-048 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-048 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-048 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-048 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-048 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-048 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-048 | OVERALL |  | 15 | 16 | 16 | 0 | 2560
#REF! | 0 | NBQ-048 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-048 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-048 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-048 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-048 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-048 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-048 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-048 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 1 | NBQ-049 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-049 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-049 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-049 | INVOICE | 27 | 17 | 18 | 18 | 907.5 | 0
#REF! | 0 | NBQ-049 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-049 | INVOICE | 31 | 17 | 18 | 18 | 577.5 | 0
#REF! | 0 | NBQ-049 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-049 | INVOICE | 32 | 17 | 18 | 18 | 165 | 0
#REF! | 0 | NBQ-049 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-049 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-049 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-049 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-049 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-049 | OVERALL |  | 17 | 18 | 18 | 0 | 1650
#REF! | 0 | NBQ-049 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | NBQ-049 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | NBQ-049 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | NBQ-049 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | NBQ-049 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | NBQ-049 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | NBQ-049 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 0 | NBQ-049 |  |  | 17 | 16 | 17 | 0 | 0
#REF! | 1 | BQ-227 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-227 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-227 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-227 | INVOICE | 27 | 15 | 16 | 16 | 3850 | 0
#REF! | 0 | BQ-227 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-227 | OVERALL |  | 15 | 16 | 16 | 0 | 3850
#REF! | 0 | BQ-227 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-227 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-227 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-227 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-227 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-227 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-227 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-227 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 1 | BQ-228 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-228 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-228 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-228 | INVOICE | 23 | 17 | 18 | 18 | 907.5 | 0
#REF! | 0 | BQ-228 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-228 | INVOICE | 27 | 17 | 18 | 18 | 907.5 | 0
#REF! | 0 | BQ-228 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-228 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-228 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-228 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-228 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-228 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-228 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | BQ-228 | OVERALL |  | 17 | 18 | 18 | 0 | 1815
#REF! | 0 | BQ-228 |  |  | 17 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-228 |  |  | 17 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-228 |  |  | 17 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-228 |  |  | 17 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-228 |  |  | 17 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-228 |  |  | 17 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-228 |  |  | 17 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-228 |  |  | 17 | 17 | 17 | 0 | 0
#REF! | 1 | BQ-229 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-229 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-229 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-229 | INVOICE | 27 | 16 | 17 | 17 | 27417.5 | 0
#REF! | 0 | BQ-229 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-229 | INVOICE | 32 | 16 | 17 | 17 | 7477.5 | 0
#REF! | 0 | BQ-229 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-229 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-229 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-229 | OVERALL |  | 16 | 17 | 17 | 0 | 34895
#REF! | 0 | BQ-229 |  |  | 16 | 14 | 16 | 0 | 0
#REF! | 0 | BQ-229 |  |  | 16 | 14 | 16 | 0 | 0
#REF! | 0 | BQ-229 |  |  | 16 | 14 | 16 | 0 | 0
#REF! | 0 | BQ-229 |  |  | 16 | 14 | 16 | 0 | 0
#REF! | 0 | BQ-229 |  |  | 16 | 14 | 16 | 0 | 0
#REF! | 0 | BQ-229 |  |  | 16 | 14 | 16 | 0 | 0
#REF! | 0 | BQ-229 |  |  | 16 | 14 | 16 | 0 | 0
#REF! | 0 | BQ-229 |  |  | 16 | 14 | 16 | 0 | 0
#REF! | 1 | BQ-230 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-230 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-230 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-230 | INVOICE | 22 | 13 | 14 | 14 | 2530 | 0
#REF! | 0 | BQ-230 |  |  | 13 | 14 | 14 | 0 | 0
#REF! | 0 | BQ-230 | OVERALL |  | 13 | 14 | 14 | 0 | 2530
#REF! | 0 | BQ-230 |  |  | 13 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-230 |  |  | 13 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-230 |  |  | 13 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-230 |  |  | 13 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-230 |  |  | 13 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-230 |  |  | 13 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-230 |  |  | 13 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-230 |  |  | 13 | 17 | 17 | 0 | 0
#REF! | 1 | BQ-231 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-231 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-231 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-231 | INVOICE | 27 | 16 | 17 | 17 | 114353.25 | 0
#REF! | 0 | BQ-231 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-231 | INVOICE | 32 | 16 | 17 | 17 | 31187.25 | 0
#REF! | 0 | BQ-231 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-231 | OVERALL |  | 16 | 17 | 17 | 0 | 145540.5
#REF! | 0 | BQ-231 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-231 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-231 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-231 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-231 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-231 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-231 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | BQ-231 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 1 | CR1-050 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-050 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-050 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-050 | INVOICE | 27 | 16 | 17 | 17 | 21725 | 0
#REF! | 0 | CR1-050 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | CR1-050 | OVERALL |  | 16 | 17 | 17 | 0 | 21725
#REF! | 0 | CR1-050 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-050 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-050 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-050 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-050 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-050 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-050 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | CR1-050 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-232 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-232 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-232 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-232 | INVOICE | 13 | 15 | 16 | 16 | 1430 | 0
#REF! | 0 | BQ-232 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-232 | INVOICE | 25 | 15 | 16 | 16 | 390 | 0
#REF! | 0 | BQ-232 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-232 | INVOICE | 27 | 15 | 16 | 16 | 5720 | 0
#REF! | 0 | BQ-232 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-232 | INVOICE | 28 | 15 | 16 | 16 | 780 | 0
#REF! | 0 | BQ-232 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-232 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-232 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-232 | OVERALL |  | 15 | 16 | 16 | 0 | 8320
#REF! | 0 | BQ-232 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-232 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-232 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-232 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-232 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-232 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-232 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-232 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 1 | BQ-233 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-233 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-233 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-233 | INVOICE | 12 | 15 | 16 | 16 | 14355 | 0
#REF! | 0 | BQ-233 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-233 | INVOICE | 25 | 15 | 16 | 16 | 3915 | 0
#REF! | 0 | BQ-233 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-233 | INVOICE | 28 | 15 | 16 | 16 | 2610 | 0
#REF! | 0 | BQ-233 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-233 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-233 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-233 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-233 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-233 | OVERALL |  | 15 | 16 | 16 | 0 | 20880
#REF! | 0 | BQ-233 |  |  | 15 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-233 |  |  | 15 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-233 |  |  | 15 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-233 |  |  | 15 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-233 |  |  | 15 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-233 |  |  | 15 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-233 |  |  | 15 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-233 |  |  | 15 | #REF! | #REF! | 0 | 0
#REF! | 1 | BQ-234 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-234 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-234 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-234 | INVOICE | 13 | 14 | #REF! | #REF! | #REF! | 0
#REF! | 0 | BQ-234 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-234 | INVOICE | 25 | 14 | #REF! | #REF! | #REF! | 0
#REF! | 0 | BQ-234 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-234 | INVOICE | 28 | 14 | #REF! | #REF! | #REF! | 0
#REF! | 0 | BQ-234 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-234 | INVOICE | 33 | 14 | #REF! | #REF! | #REF! | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | #REF! | #REF! | OVERALL |  | #REF! | 15 | #REF! | 0 | 15168
#REF! | 0 | #REF! |  |  | #REF! | #REF! | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | #REF! | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | #REF! | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | #REF! | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | #REF! | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | #REF! | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | #REF! | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | #REF! | #REF! | 0 | 0
#REF! | 1 | BQ-235 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-235 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-235 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-235 | INVOICE | 14 | 14 | #REF! | #REF! | #REF! | 0
#REF! | 0 | BQ-235 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-235 | INVOICE | 25 | 14 | #REF! | #REF! | #REF! | 0
#REF! | 0 | BQ-235 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-235 | INVOICE | 28 | 14 | #REF! | #REF! | #REF! | 0
#REF! | 0 | BQ-235 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-235 | INVOICE | 33 | 14 | #REF! | #REF! | #REF! | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | #REF! | #REF! | OVERALL |  | #REF! | 15 | #REF! | 0 | 3840
#REF! | 0 | #REF! |  |  | #REF! | #REF! | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | #REF! | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | #REF! | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | #REF! | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | #REF! | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | #REF! | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | #REF! | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | #REF! | #REF! | 0 | 0
#REF! | 1 | BQ-236 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-236 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-236 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-236 | INVOICE | 14 | 14 | #REF! | #REF! | #REF! | 0
#REF! | 0 | BQ-236 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-236 | INVOICE | 25 | 14 | #REF! | #REF! | #REF! | 0
#REF! | 0 | BQ-236 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-236 | INVOICE | 28 | 14 | #REF! | #REF! | #REF! | 0
#REF! | 0 | BQ-236 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-236 | INVOICE | 33 | 14 | #REF! | #REF! | #REF! | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | #REF! | #REF! | OVERALL |  | #REF! | 15 | #REF! | 0 | 768
#REF! | 0 | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | 1 | BQ-237 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-237 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-237 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-237 | INVOICE | 14 | 14 | 15 | 15 | 1254 | 0
#REF! | 0 | BQ-237 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-237 | INVOICE | 25 | 14 | 15 | 15 | 365.75 | 0
#REF! | 0 | BQ-237 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-237 | INVOICE | 28 | 14 | 15 | 15 | -619.48 | 0
#REF! | 0 | BQ-237 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-237 | INVOICE | 29 | 14 | 15 | 15 | -69.27 | 0
#REF! | 0 | BQ-237 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-237 | INVOICE | 33 | 14 | 15 | 15 | 133 | 0
#REF! | 0 | BQ-237 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | BQ-237 | OVERALL |  | 14 | 15 | 15 | 0 | 1064
#REF! | 0 | BQ-237 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-237 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-237 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-237 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-237 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-237 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-237 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-237 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 1 | BQ-238 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-238 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-238 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-238 | INVOICE | 14 | 14 | #REF! | #REF! | #REF! | 0
#REF! | 0 | BQ-238 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-238 | INVOICE | 25 | 14 | #REF! | #REF! | #REF! | 0
#REF! | 0 | BQ-238 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-238 | INVOICE | 27 | 14 | #REF! | #REF! | #REF! | 0
#REF! | 0 | BQ-238 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-238 | INVOICE | 33 | 14 | #REF! | #REF! | #REF! | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | #REF! | #REF! | OVERALL |  | #REF! | 15 | #REF! | 0 | 256
#REF! | 0 | #REF! |  |  | #REF! | 16 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 16 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 16 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 16 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 16 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 16 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 16 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 16 | #REF! | 0 | 0
#REF! | 1 | BQ-239 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-239 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-239 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-239 | INVOICE | 27 | 15 | 16 | 16 | 20790 | 0
#REF! | 0 | BQ-239 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-239 | INVOICE | 31 | 15 | 16 | 16 | 2970 | 0
#REF! | 0 | BQ-239 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-239 | OVERALL |  | 15 | 16 | 16 | 0 | 23760
#REF! | 0 | BQ-239 |  |  | 15 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-239 |  |  | 15 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-239 |  |  | 15 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-239 |  |  | 15 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-239 |  |  | 15 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-239 |  |  | 15 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-239 |  |  | 15 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-239 |  |  | 15 | #REF! | #REF! | 0 | 0
#REF! | 1 | BQ-240 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-240 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-240 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-240 | INVOICE | 25 | 14 | #REF! | #REF! | #REF! | 0
#REF! | 0 | BQ-240 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-240 | INVOICE | 26 | 14 | #REF! | #REF! | #REF! | 0
#REF! | 0 | BQ-240 |  |  | 14 | #REF! | #REF! | 0 | 0
#REF! | 0 | BQ-240 | INVOICE | 33 | 14 | #REF! | #REF! | #REF! | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | #REF! | 15 | #REF! | 0 | 0
#REF! | #REF! | #REF! | OVERALL |  | #REF! | 15 | #REF! | 0 | 176
#REF! | 0 | #REF! |  |  | #REF! | 13 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 13 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 13 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 13 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 13 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 13 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 13 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 13 | #REF! | 0 | 0
#REF! | 0 | #REF! |  |  | #REF! | 13 | #REF! | 0 | 0
#REF! | 1 | BQ-242 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-242 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-242 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-242 | INVOICE | 0 | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-242 |  |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-242 | OVERALL |  | 12 | 13 | 13 | 0 | 0
#REF! | 0 | BQ-242 |  |  | 12 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-242 |  |  | 12 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-242 |  |  | 12 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-242 |  |  | 12 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-242 |  |  | 12 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-242 |  |  | 12 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-242 |  |  | 12 | 16 | 16 | 0 | 0
#REF! | 0 | BQ-242 |  |  | 12 | 16 | 16 | 0 | 0
#REF! | 1 | NBQ-051 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-051 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-051 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-051 | INVOICE | 12 | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-051 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-051 | INVOICE | 25 | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-051 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-051 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-051 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-051 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-051 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-051 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-051 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-051 | OVERALL |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-051 |  |  | 15 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-051 |  |  | 15 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-051 |  |  | 15 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-051 |  |  | 15 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-051 |  |  | 15 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-051 |  |  | 15 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-051 |  |  | 15 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-051 |  |  | 15 | 17 | 17 | 0 | 0
#REF! | 1 | NBQ-052 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-052 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-052 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-052 | INVOICE | 0 | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-052 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-052 | OVERALL |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-052 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-052 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-052 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-052 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-052 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-052 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-052 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-052 |  |  | 16 | 16 | 16 | 0 | 0
#REF! | 1 | NBQ-053 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-053 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-053 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-053 | INVOICE | 0 | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-053 |  |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-053 | OVERALL |  | 15 | 16 | 16 | 0 | 0
#REF! | 0 | NBQ-053 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-053 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-053 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-053 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-053 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-053 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-053 |  |  | 15 | 18 | 18 | 0 | 0
#REF! | 1 | NBQ-054 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-054 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-054 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-054 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-054 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-054 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-054 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-054 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-054 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-054 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-054 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-054 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-054 |  |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-054 | OVERALL |  | 17 | 18 | 18 | 0 | 0
#REF! | 0 | NBQ-054 |  |  | 17 | 15 | 17 | 0 | 0
#REF! | 0 | NBQ-054 |  |  | 17 | 15 | 17 | 0 | 0
#REF! | 0 | NBQ-054 |  |  | 17 | 15 | 17 | 0 | 0
#REF! | 0 | NBQ-054 |  |  | 17 | 15 | 17 | 0 | 0
#REF! | 0 | NBQ-054 |  |  | 17 | 15 | 17 | 0 | 0
#REF! | 0 | NBQ-054 |  |  | 17 | 15 | 17 | 0 | 0
#REF! | 0 | NBQ-054 |  |  | 17 | 15 | 17 | 0 | 0
#REF! | 0 | NBQ-054 |  |  | 17 | 15 | 17 | 0 | 0
#REF! | 1 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 | OVERALL |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-055 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | NBQ-056 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-056 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-056 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-056 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-056 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-056 | OVERALL |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-056 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-056 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-056 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-056 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-056 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-056 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-056 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-056 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 1 | NBQ-057 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-057 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-057 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-057 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-057 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-057 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-057 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-057 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-057 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-057 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-057 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-057 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-057 |  |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-057 | OVERALL |  | 14 | 15 | 15 | 0 | 0
#REF! | 0 | NBQ-057 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-057 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-057 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-057 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-057 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-057 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-057 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-057 |  |  | 14 | 17 | 17 | 0 | 0
#REF! | 1 | NBQ-058 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-058 | OVERALL |  | 16 | 17 | 17 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0
#REF! | 0 | NBQ-058 |  |  | 16 | 8 | 16 | 0 | 0

## #invoices (hidden)
Month ITEMS , |  |  | Invoice #1 |  | Invoice #2 |  | Invoice #3 |  | Invoice #4 |  | Invoice #5 |  | Invoice #6 |  | Invoice #7 |  | Invoice #8 |  | Invoice #9 |  | Invoice #10 |  | Invoice #11 |  | Invoice #12 |  | Invoice #13 |  | Invoice #14 |  | Invoice #15 |  | Invoice #16 |  | Invoice #17 |  | Invoice #18 |  | Invoice #19 |  | Invoice #20 |  | Invoice #21 |  | Invoice #22 |  | Invoice #23 |  | Invoice #24 |  | Invoice #25 |  | Invoice #26
|  |  | Total Invoice #1 = |  | Total Invoice #2 = |  | Total Invoice #3 = |  | Total Invoice #4 = |  | Total Invoice #5 = |  | Total Invoice #6 = |  | Total Invoice #7 = |  | Total Invoice #8 = |  | Total Invoice #9 = |  | Total Invoice #10 = |  | Total Invoice #11 = |  | Total Invoice #12 = |  | Total Invoice #13 = |  | Total Invoice #14 = |  | Total Invoice #15 = |  | Total Invoice #16 = |  | Total Invoice #17 = |  | Total Invoice #18 = |  | Total Invoice #19 = |  | Total Invoice #20 = |  | Total Invoice #21 = |  | Total Invoice #22 = |  | Total Invoice #23 = |  | Total Invoice #24 = |  | Total Invoice #25 = |  | Total Invoice #26 =
|  |  | 1704000 |  | 3785100 |  | 4349252 |  | 792022 |  | 437934.88 |  | 1244507.8864 |  | 660913.07 |  | 1040368.18 |  | 1341043.05 |  | 655184.09 |  | 1968855.525 |  | 805396.3455 |  | 2512042.775 |  | 1018412.01 |  | 4848061.7273 |  | 1557649.625 |  | 1260121.245 |  | 542487.02 |  | 345906.46 |  | 772965.3509 |  | 1610118.9 |  | 1361919.9 |  | 1502642.48 |  | 3630224.75 |  | 2621847.425 |  | 2896276.3078 |  |  | 45265253.0028
|  |  | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple
|  |  | 0 | 1704000 | 3785100 | 0 | 3497252 | 852000 | 792022 | 0 | 0 | 437934.88 | 559878 | 684629.8864 | 0 | 660913.07 | 0 | 1040368.18 | 891080.55 | 449962.5 | 242050 | 413134.09 | 918689.045 | 1050166.48 | 395106.8 | 410289.5455 | 1486363.275 | 1025679.5 | 430746.34 | 587665.67 | 4431889 | 416172.7273 | 928930.375 | 628719.25 | 460456.12 | 799665.125 | 392035.52 | 150451.5 | 40797.46 | 305109 | 382499.11 | 390466.2409 | 307005.75 | 1303113.15 | 552815.9 | 809104 | 834143.73 | 668498.75 | 1515762.9 | 2114461.85 | 934723.5 | 1687123.925 | 678176.7328 | 2218099.575 | 45265253.0028 | 42368976.695 | 75325412 | 60.09%
D-001 | DD | التصاميم التفصيلية وتصاميم المرحلة الثالثة Stage 3 Design Package |  | 1704000 |  |  |  | 852000 |  |  |  | 284000 | [42 empty] | 2840000 | 2840000
D-002 | E&D | الهندسة والتصميم IFC, Shop drawings and Stage 4 drawings | [9 empty] | 126240 |  | 325163.6364 |  | 478181.82 |  | 47818.18 |  |  |  | 76509.09 |  | 33472.73 |  | 38254.5455 |  |  |  | 26778.17 |  | 86072.7273 | [9 empty] | 23909.0909 | [11 empty] | 315600 | 1577999.99 | 1577999.99
D-003 | TRA | تدريب المشغلين وموظفي الصيانة Training of Operators and Maintenance Personnel | [52 empty] | 0 | 0
BQ-001 | CRNCS | محمول شبكة مركزي مع جميع الكابلات ذات الصلة والملحقات والأجهزة التمهيدية وأجهزة الشبكة Central Redundant Network Core Switch with all related cabling, accessories, prepherals and network devices | [24 empty] | 364000 | [24 empty] | 31200 |  |  | 395200 | 395200
BQ-002 | GNS | محول شبكة جيجابايت مع جميع الكابلات ذات الصلة والملحقات والأجهزة التمهيدية وأجهزة الشبكة Gigabit Network Switch with all related cabling, accessories, prepherals and network devices | [24 empty] | 41160 |  |  |  | 96040 | [20 empty] | 11760 |  |  | 148960 | 148960
BQ-003 | FEC | كابينة المعدات الميدانية بما في ذلك جميع إمدادات الطاقة وكابلات الطاقة والبيانات إلى FEC وجميع المعدات الأمنية والمفاتيح الصناعية ولوحات التصحيح و CBs و TB وجميع الملحقات الكهربائية والاتصالات ذات الصلة وجميع الأعمال اللازمة لإكمال البند. Field Equipment cabinets including all power supplies, power and data cabling to the FEC and all security equipment, Industrial switches, patch panels, CBs, TBs, and all related electrical and communications accessories and all necessary work to complete the item. | [39 empty] | 54510 |  | 4740 |  |  |  |  | 782100 | 14220 | 13035 | 44437.5 |  | 117315 | 1030357.5 | 1030357.5
BQ-004 | FBB | توريد وتركيب واختبار جميع أعمال الألياف الضوئية للشبكة الرئيسية والتوزيع (بما في ذلك جميع كابلات Fo ، الملحقات ، OSP ، معدات شبكة توزيع الألياف ، الخزائن ، الرفوف ، لوحات التصحيح ، توزيع الطاقة ، حفر الخنادق ، أعمال الحفر ، الأعمال المدنية ، التركيب ، الإنهاء ، الاختبار والتشغيل) وجميع الأعمال اللازمة لإكمال البند Supply and installation, testing and commissioning of Fiber back bone and distribution (including all Fo cabling, accessories, OSP, fiber distribution network equipment, Cabinets, Racks, patch panels, power distribution, trenching, earthwork, civilworks, installation, termination, testing and commissioning) and all necessary work to complete the item | [24 empty] | 454041.6 | [12 empty] | 153600 |  | 38400 | [5 empty] | 33792 |  | 412800 |  | 422899.2 | 135176 | 277545.6 | 1928254.4 | 1928254.4
BQ-005 | APF (4) | سياج مضاد للأفراد من الفئة 4 Category 4 Anti-personnel Fence | [52 empty] | 0 | 0
BQ-006 | ASL | الإنارة الأمنية للمنطقة (بما في ذلك جميع كابلات الطاقة وتركيبات الإضاءة وشبكات التوزيع والألواح والملحقات وجميع الأعمال الكهربائية والتحكمية والمدنية والأرضية ذات الصلة وجميع الأعمال اللازمة لإكمال هذا العنصر) Area Security Lighting (including all power cabling, lighting fixtures, distribution network, panels, accessories and all related electrical, control, civil and earth work and all necessary work to complete this item) | [52 empty] | 0 | 0
BQ-007 | CEFXVA | كاميرا ثابتة خارجية مع خاصية تحليل الفيديو ( CEFXVA ) Fixed Camera with Video Analytics | [52 empty] | 0 | 0
BQ-008 | CEPZ | كاميرا متحركة خارجية ( CEPZ ) Camera External PTZ | [52 empty] | 0 | 0
BQ-009 | TVPL | عمود كاميرا CCTV Pole | [52 empty] | 0 | 0
BQ-010 | CEFX | كاميرا ثابتة خارجية ( CEFX ) External Fixed Camera | [52 empty] | 0 | 0
BQ-011 | TVPL | عمود كاميرا CCTV Pole | [52 empty] | 0 | 0
BQ-012 | CEPZ | كاميرا متحركة خارجية ( CEPZ ) External PTZ Camera | [52 empty] | 0 | 0
BQ-013 | SGMD | بوابة منزلقة آلية ( SGMD ) Motorized Sliding Gate | [52 empty] | 0 | 0
BQ-014 | RAB | حاجز الذراع الكهربائي ( RAB ) Raise Arm Barrier | [52 empty] | 0 | 0
BQ-015 | SLP | حساس استشعار أرضي ( SLP ) Safety Loop | [52 empty] | 0 | 0
BQ-016 | ROBK | مصدات طريق ( ROBK ) Road blocker | [52 empty] | 0 | 0
BQ-017 | TLTS | إشارات مرور Traffic Lights | [52 empty] | 0 | 0
BQ-018 | VSHM | مطبات التحكم في السرعة Speed Humps | [52 empty] | 0 | 0
BQ-019 | RBCP | لوحة تحكم في مصدات الطريق ( RBCP ) Road Blocker Cabinet Panel | [52 empty] | 0 | 0
BQ-020 | RBCS | مفتاح تحكم في مصدات الطريق ( RBCS ) Road Blocker Control Switch | [52 empty] | 0 | 0
BQ-021 | CRPK | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | [52 empty] | 0 | 0
BQ-022 | ICCP | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intecom Call Panel | [52 empty] | 0 | 0
BQ-023 | ISSW | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻠﻧﻅﺎﻡ الأﻣﻧﻲ ISS ISS Work Station | [52 empty] | 0 | 0
BQ-024 | ALPW | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Workstation | [52 empty] | 0 | 0
BQ-025 | UVSW | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻧﻅﺎﻡ ﻟﻔﺣﺹ ﺍﺳﻔﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ UVSS UVSW Workstation | [52 empty] | 0 | 0
BQ-026 | ICMU | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺭﺋﻳﺳﻳﺔ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intercom Master Unit | [52 empty] | 0 | 0
BQ-027 | CTKB | ﻟﻭﺣﺔ ﻣﻔﺎﺗﻳﺢ ﺍﻟﺩﻭﺍﺋﺭ ﺍﻟﺗﻠﻔﺯﻳﻭﻧﻳﺔ ﺍﻟﻣﻐﻠﻘﺔ ( CTKB ) CCTV Keyboard | [52 empty] | 0 | 0
BQ-028 | SPAS | ﺟﻬﺎﺯ ﺇﻧﺫﺍﺭ ﺻﻭﺗﻲ ﺿﻭﺋﻲ ( SPAS ) CCTV Keyboard | [52 empty] | 0 | 0
BQ-029 | EAB | ﺯﺭ ﺇﻧﺫﺍﺭ ﺍﻟﻁﻭﺍﺭﺉ ( EAB ) Emergency Alarm Button | [52 empty] | 0 | 0
BQ-030 | UPS | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required work and materials to complete this item | [52 empty] | 0 | 0
BQ-031 | HHED | ﺟﻬﺎﺯ ﻛﺷﻑ ﻣﺗﻔﺟﺭﺍﺕ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ Hand-Held Explosive Detector | [52 empty] | 0 | 0
BQ-032 | EPB | ﺯﺭ ﺍﻟﺿﻐﻁ ﻟﻠﺧﺭﻭﺝ ( EPB ) | [52 empty] | 0 | 0
BQ-033 | GEL | Exit Push Buttonﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) | [52 empty] | 0 | 0
BQ-034 | EBGU | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) | [52 empty] | 0 | 0
BQ-035 | DMC | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | [52 empty] | 0 | 0
BQ-036 | TEL | ﻫﺎﺗﻑ ( TEL ) Telephone | [52 empty] | 0 | 0
BQ-037 | HTL | ﺍﻟﺧﻁ ﺍﻟﺳﺎﺧﻥ Hot Line | [52 empty] | 0 | 0
BQ-038 | HHR | ﺭﺍﺩﻳﻭ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ ( HHR ) Hand Held Radio | [52 empty] | 0 | 0
BQ-039 | CIDX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺩﺍﺧﻠﻳﺔ ﻋﻠﻰ ﺷﻛﻝ ﻗﺑﺔ ( CIDX ) Internal Fixed Mini Dome Camera | [52 empty] | 0 | 0
BQ-040 | ALPC | ﻛﺎﻣﻳﺭﺍ ﻣﻊ ﺍﻻﻧﺎﺭﺓ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Camera | [52 empty] | 0 | 0
BQ-041 | ALPB | ﺟﻬﺎﺯ ﺍﻧﺫﺍﺭ ﺿﻭﺋﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Beacon | [52 empty] | 0 | 0
BQ-042 | ALPS | ﺟﻬﺎﺯ ﺍﻧﺫﺍﺭ ﺻﻭﺗﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Sounder | [52 empty] | 0 | 0
BQ-043 | ALPL | ﺣﺳﺎﺱ ﺍﺳﺗﺷﻌﺎﺭ ﺍﺭﺿﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Loop Sensor | [52 empty] | 0 | 0
BQ-044 | UVSC | ﻛﺎﻣﻳﺭﺍ ﻟﻧﻅﺎﻡ ﻓﺣﺹ ﺍﺳﻔﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ UVSS UVSS Camera | [52 empty] | 0 | 0
BQ-045 | AUCS | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | [52 empty] | 0 | 0
BQ-046 | PBRAB | ﻟﻭﺣﺔ ﺗﺣﻛﻡ ﻓﻲ ﺣﺎﺟﺯ ﺍﻟﺫﺭﺍﻉ ﺍﻟﻛﻬﺭﺑﺎﺋﻲ ( RAB ) Raise Arm Barrier Control Switch | [52 empty] | 0 | 0
BQ-047 | PBSG | ﻣﻔﺗﺎﺡ ﺍﻟﺗﺣﻛﻡ ﻓﻲ ﺍﻟﺑﻭﺍﺑﺔ ﺍﻟﻣﻧﺯﻟﻘﺔ Sliding Gate Control Switch | [52 empty] | 0 | 0
BQ-048 | SBD | ﻋﻣﻭﺩ ﺛﺎﺑﺕ ﻟﻣﻧﻊ ﺩﺧﻭﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ - ﺗﺻﻧﻳﻑ -ASTM M50-P1 Crash Rated Static Bollard (ASTM M50-P1 Rated) | [52 empty] | 0 | 0
BQ-049 | OVW | ﻧﻘﻁﺔ ﺍﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﻌﺳﻛﺭﻳﺔ Over Watch | [52 empty] | 0 | 0
BQ-050 | CGH | بناء ﻭﺗﺟﻬﻳﺯﻏﺭﻓﺔ ﺍﻟﺣﺭﺍﺳﺔ ﻣﻊ مظلة ونظام الإنارة لنقاط التفتيش Construction of Gatehouse with sunshade and checkpoint lighting system | [52 empty] | 0 | 0
BQ-051 | AUCS | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | [52 empty] | 0 | 0
BQ-052 | CRPK | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | [52 empty] | 0 | 0
BQ-053 | GEL | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Generic Electric Lock | [52 empty] | 0 | 0
BQ-054 | EBGU | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) Emergency Break Glass Unit | [52 empty] | 0 | 0
BQ-055 | DMC | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | [52 empty] | 0 | 0
BQ-056 | UPS | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required | [52 empty] | 0 | 0
BQ-057 | DLSD | ﺑﺎﺏ ﺣﺩﻳﺩﻱ ﻣﻔﺻﻠﻲ ﺫﻭ ﺩﺭﻓﺗﻳﻥ ﻣﺗﻭﺍﻓﻖ ﻣﻊ DLSD ) SEC-09 ) Double Leaf Steal Door (compliant with SEC 09 "Doors") | [52 empty] | 0 | 0
BQ-058 | CS | بناء ﻣﺑﻧﻰ ﺍﻟﺩﻋﻡ Construction of Support Building | [52 empty] | 0 | 0
BQ-059 | CIDX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺩﺍﺧﻠﻳﺔ ﻋﻠﻰ ﺷﻛﻝ ﻗﺑﺔ ( CIDX ) Internal Fixed Mini Dome Camera | [24 empty] | 1430 | [24 empty] | 390 |  |  | 1820 | 1820
BQ-060 | CEFX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ ( CEFX ) External Fixed Camera | [24 empty] | 3520 | [24 empty] | 480 |  |  | 4000 | 4000
BQ-061 | AUCS | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | [22 empty] | 22330 | [26 empty] | 6090 |  |  | 28420 | 28420
BQ-062 | ICCP | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intecom Call Panel | [52 empty] | 0 | 0
BQ-063 | CRPK | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | [24 empty] | 24332 | [24 empty] | 7742 |  |  | 32074 | 32074
BQ-064 | GEL | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Generic Electric Lock | [26 empty] | 4620 | [22 empty] | 1470 |  |  | 6090 | 6090
BQ-065 | EBGU | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) Emergency Break Glass Unit | [26 empty] | 924 | [22 empty] | 294 |  |  | 1218 | 1218
BQ-066 | DMC | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | [26 empty] | 940.5 | [22 empty] | 233.415 |  |  | 1173.915 | 1173.915
BQ-067 | UPS | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required | [50 empty] | 68320 |  | 68320 | 68320
BQ-068 | ISSW | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻠﻧﻅﺎﻡ ﺍﻻﻣﻧﻲ ISS Work Station | [30 empty] | 13020 | [21 empty] | 13020 | 13020
BQ-069 | ICMU | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺭﺋﻳﺳﻳﺔ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intercom Master Unit | [24 empty] | 9240 | [27 empty] | 9240 | 9240
BQ-070 | CTKB | ﻟﻭﺣﺔ ﻣﻔﺎﺗﻳﺢ ﺍﻟﺩﻭﺍﺋﺭ ﺍﻟﺗﻠﻔﺯﻳﻭﻧﻳﺔ ﺍﻟﻣﻐﻠﻘﺔ ( CTKB ) CCTV Keyboard | [50 empty] | 3885 |  | 3885 | 3885
BQ-071 | TEL | ﻫﺎﺗﻑ ( TEL ) Telephone | [52 empty] | 0 | 0
BQ-072 | HTL | ﺍﻟﺧﻁ ﺍﻟﺳﺎﺧﻥ Hot Line | [52 empty] | 0 | 0
BQ-073 | HHR | ﺭﺍﺩﻳﻭ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ ( HHR ) Hand Held Radio | [52 empty] | 0 | 0
BQ-074 | SBD | ﻋﻣﻭﺩ ﺛﺎﺑﺕ ﻟﻣﻧﻊ ﺩﺧﻭﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ - ﺗﺻﻧﻳﻑ -ASTM M50-P1 Crash Rated Static Bollard (ASTM M50-P1 Rated) | [32 empty] | 45430 |  |  |  |  | 20650 | [14 empty] | 66080 | 66080
BQ-075 | SLSD | ﺑﺎﺏ ﺣﺩﻳﺩﻱ ﻣﻔﺻﻠﻲ ﺫﻭ ﺩﺭﻓﺔ ﻭﺍﺣﺩﺓ ﻣﺗﻭﺍﻓﻖ ﻣﻊ SLSD ) SEC-09 ) | [32 empty] | 15675 |  | 7125 | [17 empty] | 22800 | 22800
BQ-076 | DLSD | ﺑﺎﺏ ﺣﺩﻳﺩﻱ ﻣﻔﺻﻠﻲ ﺫﻭ ﺩﺭﻓﺗﻳﻥ ﻣﺗﻭﺍﻓﻖ ﻣﻊ DLSD ) SEC-09 ) Double Leaf Steal Door (compliant with SEC 09 "Doors") | [32 empty] | 12490.5 |  | 5677.5 | [17 empty] | 18168 | 18168
BQ-077 | EAB | ﺯﺭ ﺇﻧﺫﺍﺭ ﺍﻟﻁﻭﺍﺭﺉ ( EAB ) Emergency Alarm Button | [26 empty] | 154 | [25 empty] | 154 | 154
BQ-078 | CSCC | يشمل إنشاء مبنى جديد لمركز التحكم الأمني ​​، كل ما يلزم من أعمال مدنية وإنشائية و MEP والكهربائية والمعمارية والإضاءة وتكييف الهواء والأثاث ونظام الحماية من الحرائق والاتصالات والعمل وما إلى ذلك وجميع الأعمال اللازمة المطلوبة لإكمال هذا العنصر. Construction of new security control center building include, all necessary Civil, structural, MEP, Electrical, architectural, lighting, AC, furniture , fire protection system, communication, work etc. and all necessary work required to complete this item. | [11 empty] | 277078.75 |  |  |  | 436751.25 |  |  |  |  | 216750 | 375700 |  |  | 43350 | 187850 | 24709.5 | 107074.5 |  |  |  |  | 10837.5 | 28177.5 |  | 18785 |  |  | 8670 | 18785 | 8670 | 37570 | 6502.5 | 28177.5 | 23842.5 | 80775.5 | 17340 | 60112 | 13005 | 33813 | 33813 | 84532.5 | 2182672.5 | 2182672.5
BQ-079 |  | ﺷﺎﺷﺔ ﺟﺩﺍﺭﻳﺔ (ﻓﻳﺩﻳﻭ ﻭﻭﻝ) Operator Dual Screens | [48 empty] | 12045 |  |  |  | 12045 | 12045
BQ-080 |  | شاشة جدارية ونظام المراقبة بما في ذلك جميع حوامل الشاشات ، وأجهزة التحكم ، وعصا التحكم ، ولوحات مفاتيح الدوائر التلفزيونية المغلقة ، وما إلى ذلك ... (كمية العناصر بناءً على تصميم المقاول وفقًا لـ HCIS) ، Video Wall and monitoring System including all screens brackets, Controllers, Joysticks, CCTV keyboards, etc... (QTY of items based on contractor's design as per HCIS), | [28 empty] | 69520 | [23 empty] | 69520 | 69520
BQ-081 |  | الخوادم والبرمجيات لإدارة ﺍﻟﻧﻅﺎﻡ ﺍﻷﻣﻧﻲ المركزي Fully redundant Central SMS (servers & software) | [28 empty] | 669840 | [20 empty] | 133968 |  |  | 803808 | 803808
BQ-082 |  | الخوادم والبرمجيات ﻟﻧﻅﺎﻡ ﺍﻟﺩﺍﺭﺍﺕ ﺍﻟﺗﻠﻔﻳﺯﻳﻭﻧﺔ ﺍﻟﻣﻐﻠﻘﺔ ﺍﻟﻣﺭﻛﺯﻱ Fully redundant Central CCTV (servers & software) | [28 empty] | 501120 | [20 empty] | 100224 |  |  | 601344 | 601344
BQ-083 |  | الخوادم والبرمجيات ﻟﻧﻅﺎﻡ ﺍﻟﺗﺣﻛﻡ ﻓﻲ ﺍﻟﺩﺧﻭﻝ ﺍﻟﻣﺭﻛﺯﻱ Fully redundant Central ACS (servers & software) | [28 empty] | 298800 | [20 empty] | 59760 |  |  | 358560 | 358560
BQ-084 |  | الخوادم والبرمجيات ﻟﻧﻅﺎﻡ ﺍﻧﺫﺍﺭ ﺍﻻﺧﺗﺭﺍﻕ ﺍﻟﻣﺣﻳﻁﻲ ﺍﻟﻣﺭﻛﺯﻱ Fully redundant Central PIDS (servers & software) | [28 empty] | 225900 | [20 empty] | 45180 |  |  | 271080 | 271080
BQ-085 |  | نظام تسجيل فيديو مكرر بالكامل ( أجهزة وبرامج ) وفقًا لمتطلبات تسجيل HCIS Fully redundant Video Recording system (Hardware & Software) as per HCIS recording requirements | [28 empty] | 292600 | [20 empty] | 86450 |  |  | 379050 | 379050
BQ-086 | APF (1) | ﺳﻳﺎﺝ ﻣﺿﺎﺩ ﻟﻸﻓﺭﺍﺩ ﺍﻟﻔﺋﺔ 1 Category 1 Anti-personnel Fence |  |  | 3785100 |  | 2118028 |  | 792022 |  |  |  | 7326 | [8 empty] | 247900 | 505305.92 | 291375 |  | 372035 |  | 242442.5 |  | 341343.5 |  | 307285 |  | 277833 |  | 96200 |  | 47156.5 |  | 38073 |  |  |  | 22866 |  | 292059.5 |  | 228438 |  | 134643 |  | 18777.5 | 10770.0828 |  | 10176979.5028 | 10176979.5028
BQ-087 | AVB | Anti Vehcile Barrier حاجز مضاد المركبات |  |  |  |  | 1379224 | [5 empty] | 552552 | [22 empty] | 97020 |  | 69300 |  | 2800 |  | 11340 |  | 155260 |  | 87752 |  | 96740 |  | 62608 |  | 11102 |  | 7308 | 2533006 | 2533006
BQ-088 | IPR | ﻁﺭﻳﻖ ﺍﻟﺩﻭﺭﻳات الداخلية Inner Patrol Road | [9 empty] | 27694.88 |  | 82387.5 |  | 182731.25 |  | 358068.75 | 127968.75 | 69712.5 | 29250 | 88725 | 21133.125 | 45418.75 |  |  | 133599.375 | 443287 | 5947.5 | 25772.5 |  |  | 69834.375 | 350886.25 | 38341.85 | 171640.625 | [13 empty] | 284050 |  |  |  |  | 2556449.98 | 2556449.98
BQ-089 | OPR | ﻁﺭﻳﻖ ﺍﻟﺩﻭﺭﻳﺎﺕ الخارجية Outer Patrol Road | [44 empty] | 3900 | 16900 | 132112.5 | 538687.5 | 81217.5 | 329761.25 | 93795 | 669776.25 | 1866150 | 1866150
BQ-090 | LRTC | ﻛﺎﻣﻳﺭﺍ ﺣﺭﺍﺭﻳﺔ ﻁﻭﻳﻠﺔ ﺍﻟﻣﺩﻯ ( LRTC ) Long Range Thermal Camera | [30 empty] | 137760 | [13 empty] | 413280 | [7 empty] | 551040 | 551040
BQ-091 | RAD | الرادار Radar | [30 empty] | 695296 | [21 empty] | 695296 | 695296
BQ-092 | CEFX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ External Fixed Camera | [22 empty] | 147793.8 |  | 95010.3 | [27 empty] | 242804.1 | 242804.1
BQ-093 | CEPZ | ﻛﺎﻣﻳﺭﺍ ﻣﺗﺣﺭﻛﺔ ﺧﺎﺭﺟﻳﺔ Camera External PTZ | [22 empty] | 18480 |  | 60060 | [27 empty] | 78540 | 78540
BQ-094 | PSL | ﺍﻻﻧﺎﺭﺓ ﺍﻷﻣﻧﻳﺔ ﺍﻟﻣﺣﻳﻁﺔ Perimeter Security Lighting system (including all power cabling, lighting fixtures, distribution network, panels, accessories and all related electrical, control, civil and earth work and all necessary work to complete this item) | [16 empty] | 763111.8 | [9 empty] | 356118.84 | [5 empty] | 23685.75 |  | 16747.5 |  | 29188.5 |  | 22250.25 | 189660 | 14115.75 | 5220 | 312288.24 |  | 319398.75 |  | 169580.4 | 211845 |  | 66990 | 50874.12 | 151923.75 | 2702998.65 | 2702998.65
BQ-095 | TVPL | عمود كاميرا CCTV Pole | [32 empty] | 12334.52 |  | 3265.02 |  | 11608.96 |  | 31561.86 | 25312.15 |  | 247.35 | 26120.16 |  | 51151.98 | 3710.25 |  | 20777.4 |  | 659.6 | 4897.53 | 12326.275 | 203973.055 | 203973.055
BQ-096 | PVS | الموجات الدقيقة ( المايكروويف ) Microwaves | [28 empty] | 110940 | [10 empty] | 9245 | [7 empty] | 16271.2 |  | 813.56 |  |  | 137269.76 | 137269.76
BQ-097 | PFS | مستشعرات الألياف الضوئية Sensorized Fiber | [28 empty] | 1915488 | [12 empty] | 180928.8 | [9 empty] | 238975.2 | 2335392 | 2335392
BQ-098 | CEFX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ ( CEFX ) External Fixed Camera | [24 empty] | 14080 | [27 empty] | 14080 | 14080
BQ-099 | TVPL | عمود كاميرا CCTV Pole | [32 empty] | 1815 |  | 363 | [9 empty] | 3267 | [7 empty] | 5445 | 5445
BQ-100 | CEPZ | كاميرا متحركة خارجية ( CEPZ ) External PTZ Camera | [52 empty] | 0 | 0
BQ-101 | SGMD | بوابة منزلقة آلية ( SGMD ) Motorized Swing Gate | [22 empty] | 76769 | [5 empty] | 32901 | [18 empty] | 9970 |  |  |  |  | 119640 | 119640
BQ-102 | RAB | حاجز الذراع الكهربائي ( RAB ) Raise Arm Barrier | [28 empty] | 20900 | [23 empty] | 20900 | 20900
BQ-103 | SLP | حساس استشعار أرضي ( SLP ) Safety Loop | [50 empty] | 11880 |  | 11880 | 11880
BQ-104 | ROBK | مصدات طريق ( ROBK ) Road blocker | [38 empty] | 124416 | [9 empty] | 145152 |  | 145152 |  | 414720 | 414720
BQ-105 | TLTS | إشارات مرور Traffic Lights | [42 empty] | 7040 | [7 empty] | 3520 |  | 10560 | 10560
BQ-106 | VSHM | مطبات التحكم في السرعة Speed Humps | [38 empty] | 5060 | [13 empty] | 5060 | 5060
BQ-107 | RBCP | لوحة تحكم في مصدات الطريق ( RBCP ) Road Blocker Cabinet Panel | [48 empty] | 7920 |  | 7920 |  | 15840 | 15840
BQ-108 | RBCS | مفتاح تحكم في مصدات الطريق ( RBCS ) Road Blocker Control Switch | [52 empty] | 0 | 0
BQ-109 | CRPK | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | [24 empty] | 8690 | [27 empty] | 8690 | 8690
BQ-110 | ICCP | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intecom Call Panel | [52 empty] | 0 | 0
BQ-111 | ISSW | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻠﻧﻅﺎﻡ الأﻣﻧﻲ ISS ISS Work Station | [30 empty] | 4340 | [21 empty] | 4340 | 4340
BQ-112 | ALPW | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Workstation | [24 empty] | 4340 | [27 empty] | 4340 | 4340
BQ-113 | UVSW | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻧﻅﺎﻡ ﻟﻔﺣﺹ ﺍﺳﻔﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ UVSS | [24 empty] | 3410 | [27 empty] | 3410 | 3410
BQ-114 | ICMU | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺭﺋﻳﺳﻳﺔ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intercom Master Unit | [24 empty] | 3080 | [27 empty] | 3080 | 3080
BQ-115 | CTKB | ﻟﻭﺣﺔ ﻣﻔﺎﺗﻳﺢ ﺍﻟﺩﻭﺍﺋﺭ ﺍﻟﺗﻠﻔﺯﻳﻭﻧﻳﺔ ﺍﻟﻣﻐﻠﻘﺔ ( CTKB ) CCTV Keyboard | [50 empty] | 1017.5 |  | 1017.5 | 1017.5
BQ-116 | SPAS | ﺟﻬﺎﺯ ﺇﻧﺫﺍﺭ ﺻﻭﺗﻲ ﺿﻭﺋﻲ ( SPAS ) Flashing Sounder | [26 empty] | 1485 | [25 empty] | 1485 | 1485
BQ-117 | EAB | ﺯﺭ ﺇﻧﺫﺍﺭ ﺍﻟﻁﻭﺍﺭﺉ ( EAB ) Emergency Alarm Button | [26 empty] | 154 | [25 empty] | 154 | 154
BQ-118 | UPS | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required work and materials to complete this item | [48 empty] | 20790 |  |  |  | 20790 | 20790
BQ-119 | HHED | ﺟﻬﺎﺯ ﻛﺷﻑ ﻣﺗﻔﺟﺭﺍﺕ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ Hand-Held Explosive Detector | [40 empty] | 92400 | [11 empty] | 92400 | 92400
BQ-120 | EPB | ﺯﺭ ﺍﻟﺿﻐﻁ ﻟﻠﺧﺭﻭﺝ ( EPB ) Exit Push Button | [26 empty] | 88 | [25 empty] | 88 | 88
BQ-121 | GEL | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Electric Lock | [26 empty] | 660 | [25 empty] | 660 | 660
BQ-122 | EBGU | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) Emergency Break Glass Unit | [50 empty] | 132 |  | 132 | 132
BQ-123 | DMC | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | [26 empty] | 104.5 | [25 empty] | 104.5 | 104.5
BQ-124 | TEL | ﻫﺎﺗﻑ ( TEL ) Telephone | [52 empty] | 0 | 0
BQ-125 | HTL | ﺍﻟﺧﻁ ﺍﻟﺳﺎﺧﻥ Hot Line | [52 empty] | 0 | 0
BQ-126 | HHR | ﺭﺍﺩﻳﻭ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ ( HHR ) Hand Held Radio | [52 empty] | 0 | 0
BQ-127 | CIDX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺩﺍﺧﻠﻳﺔ ﻋﻠﻰ ﺷﻛﻝ ﻗﺑﺔ ( CIDX ) Internal Fixed Mini Dome Camera | [24 empty] | 1430 | [27 empty] | 1430 | 1430
BQ-128 | ALPC | ﻛﺎﻣﻳﺭﺍ ﻣﻊ ﺍﻻﻧﺎﺭﺓ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Camera | [28 empty] | 61820 | [23 empty] | 61820 | 61820
BQ-129 | ALPB | ﺟﻬﺎﺯ ﺍﻧﺫﺍﺭ ﺿﻭﺋﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Beacon | [28 empty] | 2310 | [23 empty] | 2310 | 2310
BQ-130 | ALPS | ﺟﻬﺎﺯ ﺍﻧﺫﺍﺭ ﺻﻭﺗﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Sounder | [28 empty] | 1760 | [23 empty] | 1760 | 1760
BQ-131 | ALPL | ﺣﺳﺎﺱ ﺍﺳﺗﺷﻌﺎﺭ ﺍﺭﺿﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR | [28 empty] | 1980 | [23 empty] | 1980 | 1980
BQ-132 | UVSC | ﻛﺎﻣﻳﺭﺍ ﻟﻧﻅﺎﻡ ﻓﺣﺹ ﺍﺳﻔﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ UVSS | [24 empty] | 63800 | [27 empty] | 63800 | 63800
BQ-133 | AUCS | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | [22 empty] | 1595 | [29 empty] | 1595 | 1595
BQ-134 | PBRAB | ﻟﻭﺣﺔ ﺗﺣﻛﻡ ﻓﻲ ﺣﺎﺟﺯ ﺍﻟﺫﺭﺍﻉ ﺍﻟﻛﻬﺭﺑﺎﺋﻲ ( RAB ) Raise Arm Barrier Control Switch | [52 empty] | 0 | 0
BQ-135 | PBSG | ﻣﻔﺗﺎﺡ ﺍﻟﺗﺣﻛﻡ ﻓﻲ ﺍﻟﺑﻭﺍﺑﺔ ﺍﻟﻣﻧﺯﻟﻘﺔ Swing Gate Control Switch | [52 empty] | 0 | 0
BQ-136 | PVS | الموجات الدقيقة ( المايكروويف ) Microwaves | [28 empty] | 3552 | [23 empty] | 3552 | 3552
BQ-137 | SBD | ﻋﻣﻭﺩ ﺛﺎﺑﺕ ﻟﻣﻧﻊ ﺩﺧﻭﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ - ﺗﺻﻧﻳﻑ - Crash Rated Static Bollard (ASTM M50-P1 Rated)ASTM M50-P1 | [32 empty] | 266090 |  |  |  |  | 15340 | 61065 | [11 empty] | -3245 | -15340 | 323910 | 323910
BQ-138 | CGH | بناء ﻭﺗﺟﻬﻳﺯﻏﺭﻓﺔ ﺍﻟﺣﺭﺍﺳﺔ ﻣﻊ مظلة ونظام الإنارة لنقاط التفتيش Construction of Gatehouse with sunshade and checkpoint lighting system | [33 empty] | 383812 | 82368 |  |  | 74646 |  | 19305 | [6 empty] | 264000 | 11583 |  |  |  | -34749 | 800965 | 800965
BQ-139 | OVW | ﻧﻘﻁﺔ ﺍﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﻌﺳﻛﺭﻳﺔ Over Watch | [52 empty] | 0 | 0
BQ-140 | CIDX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺩﺍﺧﻠﻳﺔ ﻋﻠﻰ ﺷﻛﻝ ﻗﺑﺔ ( CIDX ) Internal Fixed Mini Dome Camera | [24 empty] | 8580 | [24 empty] | 2340 |  |  | 10920 | 10920
BQ-141 | CEFX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ ( CEFX ) External Fixed Camera | [24 empty] | 5280 | [27 empty] | 5280 | 5280
BQ-142 | TVPL | عمود كاميرا CCTV Pole | [34 empty] | 1089 | [9 empty] | 1633.5 | [7 empty] | 2722.5 | 2722.5
BQ-143 | WAFC | ﻛﺎﻣﻳﺭﺍﺕ ﺛﺎﺑﺗﺔ ﺑﺯﺍﻭﻳﺔ ﻭﺍﺳﻌﺔ Wide Angle Fixed Cameras | [46 empty] | 7975 |  |  | 1740 |  |  | 9715 | 9715
BQ-144 | CRPK | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | [24 empty] | 8690 | [24 empty] | 1659 |  |  | 10349 | 10349
BQ-145 | DMC | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | [26 empty] | 627 | [22 empty] | 199.5 |  |  | 826.5 | 826.5
BQ-146 | GEL | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Electric Lock | [26 empty] | 1320 | [22 empty] | 420 |  |  | 1740 | 1740
BQ-147 | EBGU | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) Emergency Break Glass Unit | [26 empty] | 264 | [22 empty] | 84 |  |  | 348 | 348
BQ-148 | EPB | ﺯﺭ ﺍﻟﺿﻐﻁ ﻟﻠﺧﺭﻭﺝ ( EPB ) Exit Push Button | [26 empty] | 88 | [22 empty] | 28 |  |  | 116 | 116
BQ-149 | WTMD | ﺟﻬﺎﺯ ﺍﻟﻛﺷﻑ ﻋﻥ ﺍﻟﻣﻌﺎﺩﻥ ﺑﺎﻟﻣﺭﻭﺭ ( WTMD ) Walk Through Metal Detector | [22 empty] | 16800 | [29 empty] | 16800 | 16800
BQ-150 | FHTS | ﺑﺎﺏ ﺩﻭﺍﺭ ﻛﺎﻣﻝ ﺍﻻﺭﺗﻔﺎﻉ ( FHTS ) Full Height Turnstile | [46 empty] | 27720 | [5 empty] | 27720 | 27720
BQ-151 | TEL | ﻫﺎﺗﻑ ( TEL ) Telephone | [52 empty] | 0 | 0
BQ-152 | HTL | ﺍﻟﺧﻁ ﺍﻟﺳﺎﺧﻥ Hot Line | [52 empty] | 0 | 0
BQ-153 | HHR | ﺭﺍﺩﻳﻭ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ ( HHR ) Hand Held Radio | [52 empty] | 0 | 0
BQ-154 | IDW | ﻣﺣﻁﺔ ﻋﻣﻝ ﺑﻁﺎﻗﺔ ﺍﻟﻬﻭﻳﺔ ID Workstation | [50 empty] | 4340 |  | 4340 | 4340
BQ-155 | IDC | ﻛﺎﻣﻳﺭﺍ ﺭﻗﻣﻳﺔ ﻟﺑﻁﺎﻗﺔ ﺍﻟﻬﻭﻳﺔ ID Digital Camera | [52 empty] | 0 | 0
BQ-156 | ER | ﻗﺎﺭﺉ ﺍﻟﺗﺳﺟﻳﻝ Enrollment Reader | [26 empty] | 1155 | [25 empty] | 1155 | 1155
BQ-157 | CP | ﻁﺎﺑﻌﺔ ﺍﻟﺑﻁﺎﻗﺔ Card Printer | [24 empty] | 13580 | [27 empty] | 13580 | 13580
BQ-158 | BXRY | ﻣﺎﺳﺣﺔ ﺍﻷﻣﺗﻌﺔ ﺑﺎﻷﺷﻌﺔ ﺍﻟﺳﻳﻧﻳﺔ X-Ray Baggage Scanner | [18 empty] | 106400 | [33 empty] | 106400 | 106400
BQ-159 | HHED | ﺟﻬﺎﺯ ﻛﺷﻑ ﻣﺗﻔﺟﺭﺍﺕ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ Hand-Held Explosive Detector | [40 empty] | 92400 | [11 empty] | 92400 | 92400
BQ-160 | HHMD | ﺟﻬﺎﺯ ﻛﺷﻑ ﺍﻟﻣﻌﺎﺩﻥ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ Hand-Held Metal detector | [22 empty] | 910 | [29 empty] | 910 | 910
BQ-161 | UPS | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required | [48 empty] | 20790 |  |  |  | 20790 | 20790
BQ-162 | DLSD | ﺑﺎﺏ ﺣﺩﻳﺩﻱ ﻣﻔﺻﻠﻲ ﺫﻭ ﺩﺭﻓﺗﻳﻥ ﻣﺗﻭﺍﻓﻖ ﻣﻊ DLSD ) SEC-09 ) Double Leaf Steel Door (Compliant with SEC-09 "Doors")8 | [32 empty] | 12490.5 |  | 5677.5 | [12 empty] | 2271 |  |  |  |  | 20439 | 20439
BQ-163 | CSB | بناء ﻣﺑﻧﻰ ﺍﻟﺗﻔﺗﻳﺵ ﻭﻣﺭﻛﺯ ﺍﻟﺯﻭﺍﺭ Construction of Search Facility & Vistor Center | [15 empty] | 197730 |  | 380250 |  |  | 175500 | 304200 |  |  | 35100 | 152100 | 20007 | 86697 | 5265 | 22815 |  |  | 8775 | 22815 |  | 15210 |  |  |  |  | 7020 | 15210 | 15795 | 56277 | 14040 | 42588 | 14040 | 15210 | 10530 | 27378 | 27378 | 86814 | 1758744 | 1758744
BQ-164 | CEFX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ ( CEFX ) External Fixed Camera | [24 empty] | 14080 | [27 empty] | 14080 | 14080
BQ-165 | TVPL | عمود كاميرا CCTV Pole | [34 empty] | 3633 | [17 empty] | 3633 | 3633
BQ-166 | CEPZ | كاميرا متحركة خارجية ( CEPZ ) External PTZ Camera | [52 empty] | 0 | 0
BQ-167 | SGMD | بوابة منزلقة آلية ( SGMD ) Motorized Swing Gate | [22 empty] | 76769 | [5 empty] | 32901 | [18 empty] | 19940 |  |  |  |  | 129610 | 129610
BQ-168 | RAB | حاجز الذراع الكهربائي ( RAB ) Raise Arm Barrier | [28 empty] | 20900 | [23 empty] | 20900 | 20900
BQ-169 | SLP | حساس استشعار أرضي ( SLP ) Safety Loop | [50 empty] | 11880 |  | 11880 | 11880
BQ-170 | ROBK | مصدات طريق ( ROBK ) Road blocker | [38 empty] | 124416 | [9 empty] | 290304 | 82944 |  |  | 497664 | 497664
BQ-171 | TLTS | إشارات مرور Traffic Lights | [42 empty] | 7040 | [7 empty] | 3520 |  | 10560 | 10560
BQ-172 | VSHM | مطبات التحكم في السرعة Speed Humps | [38 empty] | 5060 | [13 empty] | 5060 | 5060
BQ-173 | RBCP | لوحة تحكم في مصدات الطريق ( RBCP ) Road Blocker Cabinet Panel | [48 empty] | 15840 |  |  |  | 15840 | 15840
BQ-174 | RBCS | مفتاح تحكم في مصدات الطريق ( RBCS ) Road Blocker Control Switch | [52 empty] | 0 | 0
BQ-175 | CRPK | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | [24 empty] | 8690 | [27 empty] | 8690 | 8690
BQ-176 | ICCP | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intecom Call Panel | [52 empty] | 0 | 0
BQ-177 | ISSW | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻠﻧﻅﺎﻡ الأﻣﻧﻲ ISS ISS Work Station | [30 empty] | 4340 | [21 empty] | 4340 | 4340
BQ-178 | ALPW | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Workstation | [24 empty] | 4340 | [27 empty] | 4340 | 4340
BQ-179 | ICMU | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺭﺋﻳﺳﻳﺔ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intercom Master Unit | [24 empty] | 3080 | [27 empty] | 3080 | 3080
BQ-180 | CTKB | ﻟﻭﺣﺔ ﻣﻔﺎﺗﻳﺢ ﺍﻟﺩﻭﺍﺋﺭ ﺍﻟﺗﻠﻔﺯﻳﻭﻧﻳﺔ ﺍﻟﻣﻐﻠﻘﺔ ( CTKB ) CCTV Keyboard | [50 empty] | 1017.5 |  | 1017.5 | 1017.5
BQ-181 | SPAS | ﺟﻬﺎﺯ ﺇﻧﺫﺍﺭ ﺻﻭﺗﻲ ﺿﻭﺋﻲ ( SPAS ) Flashing Sounder | [26 empty] | 1485 | [25 empty] | 1485 | 1485
BQ-182 | EAB | ﺯﺭ ﺇﻧﺫﺍﺭ ﺍﻟﻁﻭﺍﺭﺉ ( EAB ) Emergency Alarm Button | [26 empty] | 154 | [25 empty] | 154 | 154
BQ-183 | UPS | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required | [48 empty] | 20790 |  |  |  | 20790 | 20790
BQ-184 | HHED | ﺟﻬﺎﺯ ﻛﺷﻑ ﻣﺗﻔﺟﺭﺍﺕ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ Hand-Held Explosive Detector | [40 empty] | 92400 | [11 empty] | 92400 | 92400
BQ-185 | EPB | ﺯﺭ ﺍﻟﺿﻐﻁ ﻟﻠﺧﺭﻭﺝ ( EPB ) Exit Push Button | [26 empty] | 88 | [25 empty] | 88 | 88
BQ-186 | GEL | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Electric Lock | [26 empty] | 660 | [25 empty] | 660 | 660
BQ-187 | EBGU | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) Emergency Break Glass Unit | [26 empty] | 132 | [25 empty] | 132 | 132
BQ-188 | DMC | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | [26 empty] | 104.5 | [25 empty] | 104.5 | 104.5
BQ-189 | TEL | ﻫﺎﺗﻑ ( TEL ) Telephone | [52 empty] | 0 | 0
BQ-190 | HTL | ﺍﻟﺧﻁ ﺍﻟﺳﺎﺧﻥ Hot Line | [52 empty] | 0 | 0
BQ-191 | HHR | ﺭﺍﺩﻳﻭ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ ( HHR ) Hand Held Radio | [52 empty] | 0 | 0
BQ-192 | CIDX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺩﺍﺧﻠﻳﺔ ﻋﻠﻰ ﺷﻛﻝ ﻗﺑﺔ ( CIDX ) Internal Fixed Mini Dome Camera | [24 empty] | 1430 | [27 empty] | 1430 | 1430
BQ-193 | ALPC | ﻛﺎﻣﻳﺭﺍ ﻣﻊ ﺍﻻﻧﺎﺭﺓ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Camera | [28 empty] | 61820 | [23 empty] | 61820 | 61820
BQ-194 | ALPB | ﺟﻬﺎﺯ ﺍﻧﺫﺍﺭ ﺿﻭﺋﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Beacon | [50 empty] | 2310 |  | 2310 | 2310
BQ-195 | ALPS | ﺟﻬﺎﺯ ﺍﻧﺫﺍﺭ ﺻﻭﺗﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Sounder | [52 empty] | 0 | 0
BQ-196 | ALPL | ﺣﺳﺎﺱ ﺍﺳﺗﺷﻌﺎﺭ ﺍﺭﺿﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Loop Sensor | [28 empty] | 1980 | [23 empty] | 1980 | 1980
BQ-197 | AUCS | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | [22 empty] | 1595 | [29 empty] | 1595 | 1595
BQ-198 | PBRAB | ﻟﻭﺣﺔ ﺗﺣﻛﻡ ﻓﻲ ﺣﺎﺟﺯ ﺍﻟﺫﺭﺍﻉ ﺍﻟﻛﻬﺭﺑﺎﺋﻲ ( RAB ) Raise Arm Barrier Control Switch | [52 empty] | 0 | 0
BQ-199 | PBSG | ﻣﻔﺗﺎﺡ ﺍﻟﺗﺣﻛﻡ ﻓﻲ ﺍﻟﺑﻭﺍﺑﺔ ﺍﻟﻣﻧﺯﻟﻘﺔ Swing Gate Control Switch | [52 empty] | 0 | 0
BQ-200 | PVS | الموجات الدقيقة ( المايكروويف ) Microwaves | [28 empty] | 3552 | [23 empty] | 3552 | 3552
BQ-201 | SBD | ﻋﻣﻭﺩ ﺛﺎﺑﺕ ﻟﻣﻧﻊ ﺩﺧﻭﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ - ﺗﺻﻧﻳﻑ -ASTM M50-P1 Crash Rated Static Bollard (ASTM M50-P1 Rated) | [34 empty] | 266090 | [11 empty] | -3245 | 147647.5 |  |  |  |  | 410492.5 | 410492.5
BQ-202 | CGH | بناء ﻭﺗﺟﻬﻳﺯﻏﺭﻓﺔ ﺍﻟﺣﺭﺍﺳﺔ ﻣﻊ مظلة ونظام الإنارة لنقاط التفتيش Construction of Gatehouse with sunshade and checkpoint lighting system | [41 empty] | 279136 |  | 116688 |  | 51480 |  | 41184 | 264000 | 43758 |  | 39897 | 836143 | 836143
BQ-203 | CIDX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺩﺍﺧﻠﻳﺔ ﻋﻠﻰ ﺷﻛﻝ ﻗﺑﺔ ( CIDX ) Internal Fixed Mini Dome Camera | [24 empty] | 8580 | [27 empty] | 8580 | 8580
BQ-204 | CEFX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ ( CEFX ) External Fixed Camera | [24 empty] | 5280 | [27 empty] | 5280 | 5280
BQ-205 | TVPL | عمود كاميرا CCTV Pole | [44 empty] | 2722.5 | [7 empty] | 2722.5 | 2722.5
BQ-206 | WAFC | ﻛﺎﻣﻳﺭﺍﺕ ﺛﺎﺑﺗﺔ ﺑﺯﺍﻭﻳﺔ ﻭﺍﺳﻌﺔ Wide Angle Fixed Cameras | [46 empty] | 7975 | [5 empty] | 7975 | 7975
BQ-207 | CRPK | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | [24 empty] | 8690 | [27 empty] | 8690 | 8690
BQ-208 | DMC | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | [26 empty] | 627 | [25 empty] | 627 | 627
BQ-209 | GEL | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Electric Lock | [26 empty] | 1320 | [25 empty] | 1320 | 1320
BQ-210 | EBGU | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) Emergency Break Glass Unit | [26 empty] | 264 | [25 empty] | 264 | 264
BQ-211 | EPB | ﺯﺭ ﺍﻟﺿﻐﻁ ﻟﻠﺧﺭﻭﺝ ( EPB ) Exit Push Button | [26 empty] | 88 | [25 empty] | 88 | 88
BQ-212 | WTMD | ﺟﻬﺎﺯ ﺍﻟﻛﺷﻑ ﻋﻥ ﺍﻟﻣﻌﺎﺩﻥ ﺑﺎﻟﻣﺭﻭﺭ ( WTMD ) Walk Through Metal Detector | [22 empty] | 16800 | [29 empty] | 16800 | 16800
BQ-213 | FHTS | ﺑﺎﺏ ﺩﻭﺍﺭ ﻛﺎﻣﻝ ﺍﻻﺭﺗﻔﺎﻉ ( FHTS ) Full Height Turnstile | [46 empty] | 27720 | [5 empty] | 27720 | 27720
BQ-214 | TEL | ﻫﺎﺗﻑ ( TEL ) Telephone | [52 empty] | 0 | 0
BQ-215 | HTL | ﺍﻟﺧﻁ ﺍﻟﺳﺎﺧﻥ Hot Line | [52 empty] | 0 | 0
BQ-216 | HHR | ﺭﺍﺩﻳﻭ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ ( HHR ) | [52 empty] | 0 | 0
BQ-217 | IDW | ﻣﺣﻁﺔ ﻋﻣﻝ ﺑﻁﺎﻗﺔ ﺍﻟﻬﻭﻳﺔ ID Workstation | [30 empty] | 4340 | [21 empty] | 4340 | 4340
BQ-218 | IDC | ﻛﺎﻣﻳﺭﺍ ﺭﻗﻣﻳﺔ ﻟﺑﻁﺎﻗﺔ ﺍﻟﻬﻭﻳﺔ ID Digital Camera | [52 empty] | 0 | 0
BQ-219 | ER | ﻗﺎﺭﺉ ﺍﻟﺗﺳﺟﻳﻝ Enrollment Reader | [26 empty] | 1155 | [25 empty] | 1155 | 1155
BQ-220 | CP | ﻁﺎﺑﻌﺔ ﺍﻟﺑﻁﺎﻗﺔ Card Printer | [24 empty] | 13580 | [27 empty] | 13580 | 13580
BQ-221 | BXRY | ﻣﺎﺳﺣﺔ ﺍﻷﻣﺗﻌﺔ ﺑﺎﻷﺷﻌﺔ ﺍﻟﺳﻳﻧﻳﺔ X-Ray Baggage Scanner | [18 empty] | 106400 | [33 empty] | 106400 | 106400
BQ-222 | HHED | ﺟﻬﺎﺯ ﻛﺷﻑ ﻣﺗﻔﺟﺭﺍﺕ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ Hand-Held Explosive Detector | [41 empty] | 92400 | [10 empty] | 92400 | 92400
BQ-223 | HHMD | ﺟﻬﺎﺯ ﻛﺷﻑ ﺍﻟﻣﻌﺎﺩﻥ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ Hand-Held Metal detector | [22 empty] | 910 | [29 empty] | 910 | 910
BQ-224 | UPS | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required | [49 empty] | 20790 |  |  | 20790 | 20790
BQ-225 | DLSD | ﺑﺎﺏ ﺣﺩﻳﺩﻱ ﻣﻔﺻﻠﻲ ﺫﻭ ﺩﺭﻓﺗﻳﻥ ﻣﺗﻭﺍﻓﻖ ﻣﻊDouble Leaf Steel Door (Compliant with SEC-09 "Doors") DLSD ) SEC-09 ) | [32 empty] | 12490.5 | [14 empty] | 2271 |  | 5677.5 |  |  | 20439 | 20439
BQ-226 | CSB | بناء ﻣﺑﻧﻰ ﺍﻟﺗﻔﺗﻳﺵ ﻭﻣﺭﻛﺯ ﺍﻟﺯﻭﺍﺭ Construction of Search Facility & Vistor Center | [41 empty] | 509535 | 175500 | 228150 |  | 114075 | 68445 | 108371.25 | 19305 | 74148.75 | 59670 | 266175 | 1623375 | 1623375
BQ-227 | CEFXVA | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ ﻣﻊ ﺗﺣﻠﻳﻼﺕ ﺍﻟﻔﻳﺩﻳﻭ (CEFXVA) External Fixed Camera with Video Analytics | [52 empty] | 0 | 0
BQ-228 | TVPL | عمود كاميرا CCTV Pole | [44 empty] | 907.5 | [7 empty] | 907.5 | 907.5
BQ-229 | SWMO | ﺑﻭﺍﺑﺔ ﻣﻔﺻﻠﻳﺔ ﻳﺩﻭﻳﺔManually Operated Swing Gate | [52 empty] | 0 | 0
BQ-230 | VSHM | ﻣﻁﺑﺎﺕ ﺍﻟﺗﺣﻛﻡ ﻓﻲ ﺍﻟﺳﺭﻋﺔ Speed Humps | [42 empty] | 2530 | [9 empty] | 2530 | 2530
BQ-231 | RBD | ﺫﺭﺍﻉ ﻫﻳﺩﺭﻭﻟﻳﻛﻲ ﻣﺿﺎﺽ ﻟﻠﻣﺭﻛﺑﺎﺕ (ﺗﺻﻧﻳﻑ ASTM M50-P1) Crash Rated Arm Barrier (ASTM M50-P1 Rated) | [52 empty] | 0 | 0
BQ-232 | CIDX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺩﺍﺧﻠﻳﺔ ﻋﻠﻰ ﺷﻛﻝ ﻗﺑﺔ ( CIDX ) Camera Internal Fixed Dome | [24 empty] | 1430 | [24 empty] | 390 |  |  | 1820 | 1820
BQ-233 | AUCS | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | [22 empty] | 14355 | [26 empty] | 3915 |  |  | 18270 | 18270
BQ-234 | CRPK | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | [24 empty] | 17380 | [24 empty] | 5530 |  |  | 22910 | 22910
BQ-235 | GEL | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Electric Lock | [26 empty] | 3300 | [22 empty] | 1050 |  |  | 4350 | 4350
BQ-236 | EBGU | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) Emergency Break Glass Unit | [26 empty] | 660 | [22 empty] | 168 |  |  | 828 | 828
BQ-237 | DMC | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | [26 empty] | 1254 | [22 empty] | 365.75 |  |  | 1619.75 | 1619.75
BQ-238 | EPB | ﺯﺭ ﺍﻟﺿﻐﻁ ﻟﻠﺧﺭﻭﺝ ( EPB ) Exit Push Button | [26 empty] | 88 | [22 empty] | 28 |  |  | 116 | 116
BQ-239 | UPS | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required | [52 empty] | 0 | 0
BQ-240 | EAB | ﺯﺭ ﺇﻧﺫﺍﺭ ﺍﻟﻁﻭﺍﺭﺉ ( EAB ) Emergency Alarm Button | [49 empty] | 15.4 | 154 |  | 169.4 | 169.4
BQ-241 | SBD | ﻋﻣﻭﺩ ﺛﺎﺑﺕ ﻣﺿﺎﺽ ﻟﻠﻣﺭﻛﺑﺎﺕ- M50 P1 ﺗﺻﻧﻳﻑ (SBD) Crash Rated Static Bollard (ASTM M50-P1 Rated) | [52 empty] | 0 | 0
BQ-242 | DLSD | ﺑﺎﺏ ﺣﺩﻳﺩﻱ ﻣﻔﺻﻠﻲ ﺫﻭ ﺩﺭﻓﺗﻳﻥ ﻣﺗﻭﺍﻓﻖ ﻣﻊ DLSD ) SEC-09 ) | [52 empty] | 0 | 0

## Sum Inovices (hidden)
TORTAL INVOICES SAR = | [6 empty] | 45265253.0028 |  |  | Total BOQ = |  |  |  |  | Pro.Completation % = |  |  | 65.98%
TORTAL PROCUMENT SAR = | [6 empty] | 24457524.1078 |  |  | 68605360 |  |  |  |  | Procument % = |  |  | 35.65%
TORTAL IMPLEMENTATION SAR = | [6 empty] | 20807728.895 | [7 empty] | Implementation % = |  |  | 30.33%
Invoice #1 |  | Invoice #2 |  | Invoice #3 |  | Invoice #4 |  | Invoice #5 |  | Invoice #6 |  | Invoice #7 |  | Invoice #8 |  | Invoice #9 |  | Invoice #10
Total Invoice #1 = |  | Total Invoice #2 = |  | Total Invoice #3 = |  | Total Invoice #4 = |  | Total Invoice #5 = |  | Total Invoice #6 = |  | Total Invoice #7 = |  | Total Invoice #8 = |  | Total Invoice #9 = |  | Total Invoice #10 =
1704000 |  | 3785100 |  | 4349252 |  | 792022 |  | 437934.88 |  | 1244507.8864 |  | 660913.07 |  | 1040368.18 |  | 1341043.05 |  | 655184.09
PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple
0 | 1704000 | 3785100 | 0 | 3497252 | 852000 | 792022 | 0 | 0 | 437934.88 | 559878 | 684629.8864 | 0 | 660913.07 | 0 | 1040368.18 | 891080.55 | 449962.5 | 242050 | 413134.09
Invoice #11 |  | Invoice #12 |  | Invoice #13 |  | Invoice #14 |  | Invoice #15 |  | Invoice #16 |  | Invoice #17 |  | Invoice #18 |  | Invoice #19 |  | Invoice #20
Total Invoice #11 = |  | Total Invoice #12 = |  | Total Invoice #13= |  | Total Invoice #14= |  | Total Invoice #5 = |  | Total Invoice #16 = |  | Total Invoice #17 = |  | Total Invoice #18 = |  | Total Invoice #19 = |  | Total Invoice #20 =
1968855.525 |  | 805396.3455 |  | 2512042.775 |  | 1018412.01 |  | 4848061.7273 |  | 1557649.625 |  | 1260121.245 |  | 542487.02 |  | 345906.46 |  | 772965.3509
PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple
918689.045 | 1050166.48 | 395106.8 | 410289.5455 | 1486363.275 | 1025679.5 | 430746.34 | 587665.67 | 4431889 | 416172.7273 | 928930.375 | 628719.25 | 460456.12 | 799665.125 | 392035.52 | 150451.5 | 40797.46 | 305109 | 382499.11 | 390466.2409
Invoice #21 |  | Invoice #22 |  | Invoice #23 |  | Invoice #24 |  | Invoice #25 |  | Invoice #26 |  | Invoice #27 |  | Invoice #28 |  | Invoice #29 |  | Invoice #30
Total Invoice #21 = |  | Total Invoice #22 = |  | Total Invoice #23= |  | Total Invoice #24= |  | Total Invoice #25 = |  | Total Invoice #26 = |  | Total Invoice #27 = |  | Total Invoice #28 = |  | Total Invoice #29 = |  | Total Invoice #30 =
1610118.9 |  | 1361919.9 |  | 1502642.48 |  | 3630224.75 |  | 2621847.425 |  | 2896276.3078 |  | #REF! |  | #REF! |  | #REF! |  | #REF!
PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple
307005.75 | 1303113.15 | 552815.9 | 809104 | 834143.73 | 668498.75 | 1515762.9 | 2114461.85 | 934723.5 | 1687123.925 | 678176.7328 | 2218099.575 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Tracker (hidden)
الرقم | اختصار البند | البنود | الكمية | الوحدة | السعر | كميات مستخلص #01 |  | كميات مستخلص #02 |  | كميات مستخلص #03 |  | كميات مستخلص #04 |  | كميات مستخلص #05 |  | كميات مستخلص #06 |  | كميات مستخلص #07 |  | كميات مستخلص #08 |  | كميات مستخلص #09 |  | كميات مستخلص #10 |  | كميات مستخلص #11 |  | كميات مستخلص #12 |  | كميات مستخلص #13 |  | كميات مستخلص #14 |  | كميات مستخلص #15 |  | كميات مستخلص #16 |  | كميات مستخلص #17 |  | كميات مستخلص #18 |  | كميات مستخلص #19 |  | كميات مستخلص #20 |  | كميات مستخلص #21 |  | كميات مستخلص #22 |  | كميات مستخلص #23 |  | كميات مستخلص #24 |  | كميات مستخلص #25 |  | كميات مستخلص #26
[6 empty] | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple | PROCU | imple
D-001 | DD | التصاميم التفصيلية وتصاميم المرحلة الثالثة Stage 3 Design Package | 1 | عدد | 2840000 |  | 1*60% |  |  |  | 1*30% |  |  | 1*10%
D-002 | E&D | الهندسة والتصميم IFC, Shop drawings and Stage 4 drawings | 1*264 | عدد | 2630000 | [8 empty] | 26.4*60%*80% |  |  | 68*60%*80% |  | 100*60%*80% |  | 10*60%*80% |  |  |  | 16*60%*80% |  | 7*60%*80% |  | 8*60%*80% |  |  |  | 5.6 |  | 18*60%
D-003 | TRA | تدريب المشغلين وموظفي الصيانة Training of Operators and Maintenance Personnel | 1 | عدد | 110000
BQ-001 | CRNCS | محمول شبكة مركزي مع جميع الكابلات ذات الصلة والملحقات والأجهزة التمهيدية وأجهزة الشبكة Central Redundant Network Core Switch with all related cabling, accessories, prepherals and network devices | 4 | عدد | 130000 | [24 empty] | 4
BQ-002 | GNS | محول شبكة جيجابايت مع جميع الكابلات ذات الصلة والملحقات والأجهزة التمهيدية وأجهزة الشبكة Gigabit Network Switch with all related cabling, accessories, prepherals and network devices | 10 | عدد | 19600 | [24 empty] | 3 |  |  |  | 7
BQ-003 | FEC | كابينة المعدات الميدانية بما في ذلك جميع إمدادات الطاقة وكابلات الطاقة والبيانات إلى FEC وجميع المعدات الأمنية والمفاتيح الصناعية ولوحات التصحيح و CBs و TB وجميع الملحقات الكهربائية والاتصالات ذات الصلة وجميع الأعمال اللازمة لإكمال البند. Field Equipment cabinets including all power supplies, power and data cabling to the FEC and all security equipment, Industrial switches, patch panels, CBs, TBs, and all related electrical and communications accessories and all necessary work to complete the item. | 66 | عدد | 23700
BQ-004 | FBB | توريد وتركيب واختبار جميع أعمال الألياف الضوئية للشبكة الرئيسية والتوزيع (بما في ذلك جميع كابلات Fo ، الملحقات ، OSP ، معدات شبكة توزيع الألياف ، الخزائن ، الرفوف ، لوحات التصحيح ، توزيع الطاقة ، حفر الخنادق ، أعمال الحفر ، الأعمال المدنية ، التركيب ، الإنهاء ، الاختبار والتشغيل) وجميع الأعمال اللازمة لإكمال البند Supply and installation, testing and commissioning of Fiber back bone and distribution (including all Fo cabling, accessories, OSP, fiber distribution network equipment, Cabinets, Racks, patch panels, power distribution, trenching, earthwork, civilworks, installation, termination, testing and commissioning) and all necessary work to complete the item | 9953 | م.ط | 320 | [24 empty] | 8868*80%
BQ-005 | APF (4) | سياج مضاد للأفراد من الفئة 4 Category 4 Anti-personnel Fence | 1085 | م.ط | 720
BQ-006 | ASL | الإنارة الأمنية للمنطقة (بما في ذلك جميع كابلات الطاقة وتركيبات الإضاءة وشبكات التوزيع والألواح والملحقات وجميع الأعمال الكهربائية والتحكمية والمدنية والأرضية ذات الصلة وجميع الأعمال اللازمة لإكمال هذا العنصر) Area Security Lighting (including all power cabling, lighting fixtures, distribution network, panels, accessories and all related electrical, control, civil and earth work and all necessary work to complete this item) | 27 | عدد | 8900
BQ-007 | CEFXVA | كاميرا ثابتة خارجية مع خاصية تحليل الفيديو ( CEFXVA ) Fixed Camera with Video Analytics | 19 | عدد | 3500
BQ-008 | CEPZ | كاميرا متحركة خارجية ( CEPZ ) Camera External PTZ | 3 | عدد | 8400
BQ-009 | TVPL | عمود كاميرا CCTV Pole | 19 | عدد | 1650
BQ-010 | CEFX | كاميرا ثابتة خارجية ( CEFX ) External Fixed Camera | 8 | عدد | 3200
BQ-011 | TVPL | عمود كاميرا CCTV Pole | 6 | عدد | 1650
BQ-012 | CEPZ | كاميرا متحركة خارجية ( CEPZ ) External PTZ Camera | 2 | عدد | 8400
BQ-013 | SGMD | بوابة منزلقة آلية ( SGMD ) Motorized Sliding Gate | 2 | عدد | 49850
BQ-014 | RAB | حاجز الذراع الكهربائي ( RAB ) Raise Arm Barrier | 4 | عدد | 9500
BQ-015 | SLP | حساس استشعار أرضي ( SLP ) Safety Loop | 12 | عدد | 1800
BQ-016 | ROBK | مصدات طريق ( ROBK ) Road blocker | 4 | عدد | 172800
BQ-017 | TLTS | إشارات مرور Traffic Lights | 6 | عدد | 3200
BQ-018 | VSHM | مطبات التحكم في السرعة Speed Humps | 4 | عدد | 2300
BQ-019 | RBCP | لوحة تحكم في مصدات الطريق ( RBCP ) Road Blocker Cabinet Panel | 4 | عدد | 7200
BQ-020 | RBCS | مفتاح تحكم في مصدات الطريق ( RBCS ) Road Blocker Control Switch | 4 | عدد | 1400
BQ-021 | CRPK | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | 5 | عدد | 3160
BQ-022 | ICCP | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intecom Call Panel | 1 | عدد | 4950
BQ-023 | ISSW | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻠﻧﻅﺎﻡ الأﻣﻧﻲ ISS ISS Work Station | 1 | عدد | 6200
BQ-024 | ALPW | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Workstation | 1 | عدد | 6200
BQ-025 | UVSW | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻧﻅﺎﻡ ﻟﻔﺣﺹ ﺍﺳﻔﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ UVSS UVSW Workstation | 1 | عدد | 6200
BQ-026 | ICMU | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺭﺋﻳﺳﻳﺔ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intercom Master Unit | 1 | عدد | 5600
BQ-027 | CTKB | ﻟﻭﺣﺔ ﻣﻔﺎﺗﻳﺢ ﺍﻟﺩﻭﺍﺋﺭ ﺍﻟﺗﻠﻔﺯﻳﻭﻧﻳﺔ ﺍﻟﻣﻐﻠﻘﺔ ( CTKB ) CCTV Keyboard | 1 | عدد | 1850
BQ-028 | SPAS | ﺟﻬﺎﺯ ﺇﻧﺫﺍﺭ ﺻﻭﺗﻲ ﺿﻭﺋﻲ ( SPAS ) CCTV Keyboard | 2 | عدد | 1350
BQ-029 | EAB | ﺯﺭ ﺇﻧﺫﺍﺭ ﺍﻟﻁﻭﺍﺭﺉ ( EAB ) Emergency Alarm Button | 1 | عدد | 220
BQ-030 | UPS | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required work and materials to complete this item | 1 | عدد | 29700
BQ-031 | HHED | ﺟﻬﺎﺯ ﻛﺷﻑ ﻣﺗﻔﺟﺭﺍﺕ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ Hand-Held Explosive Detector | 1 | عدد | 132000
BQ-032 | EPB | ﺯﺭ ﺍﻟﺿﻐﻁ ﻟﻠﺧﺭﻭﺝ ( EPB ) | 1 | عدد | 0
BQ-033 | GEL | Exit Push Buttonﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) | 1 | عدد | 1200
BQ-034 | EBGU | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) | 1 | عدد | 240
BQ-035 | DMC | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | 1 | عدد | 190
BQ-036 | TEL | ﻫﺎﺗﻑ ( TEL ) Telephone | 2 | عدد | 2300
BQ-037 | HTL | ﺍﻟﺧﻁ ﺍﻟﺳﺎﺧﻥ Hot Line | 1 | عدد | 2300
BQ-038 | HHR | ﺭﺍﺩﻳﻭ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ ( HHR ) Hand Held Radio | 1 | عدد | 3800
BQ-039 | CIDX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺩﺍﺧﻠﻳﺔ ﻋﻠﻰ ﺷﻛﻝ ﻗﺑﺔ ( CIDX ) Internal Fixed Mini Dome Camera | 1 | عدد | 2600
BQ-040 | ALPC | ﻛﺎﻣﻳﺭﺍ ﻣﻊ ﺍﻻﻧﺎﺭﺓ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Camera | 2 | عدد | 56200
BQ-041 | ALPB | ﺟﻬﺎﺯ ﺍﻧﺫﺍﺭ ﺿﻭﺋﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Beacon | 2 | عدد | 2100
BQ-042 | ALPS | ﺟﻬﺎﺯ ﺍﻧﺫﺍﺭ ﺻﻭﺗﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Sounder | 2 | عدد | 1600
BQ-043 | ALPL | ﺣﺳﺎﺱ ﺍﺳﺗﺷﻌﺎﺭ ﺍﺭﺿﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Loop Sensor | 2 | عدد | 1800
BQ-044 | UVSC | ﻛﺎﻣﻳﺭﺍ ﻟﻧﻅﺎﻡ ﻓﺣﺹ ﺍﺳﻔﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ UVSS UVSS Camera | 2 | عدد | 58000
BQ-045 | AUCS | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | 1 | عدد | 2900
BQ-046 | PBRAB | ﻟﻭﺣﺔ ﺗﺣﻛﻡ ﻓﻲ ﺣﺎﺟﺯ ﺍﻟﺫﺭﺍﻉ ﺍﻟﻛﻬﺭﺑﺎﺋﻲ ( RAB ) Raise Arm Barrier Control Switch | 4 | عدد | 1400
BQ-047 | PBSG | ﻣﻔﺗﺎﺡ ﺍﻟﺗﺣﻛﻡ ﻓﻲ ﺍﻟﺑﻭﺍﺑﺔ ﺍﻟﻣﻧﺯﻟﻘﺔ Sliding Gate Control Switch | 2 | عدد | 1400
BQ-048 | SBD | ﻋﻣﻭﺩ ﺛﺎﺑﺕ ﻟﻣﻧﻊ ﺩﺧﻭﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ - ﺗﺻﻧﻳﻑ -ASTM M50-P1 Crash Rated Static Bollard (ASTM M50-P1 Rated) | 48 | عدد | 5900
BQ-049 | OVW | ﻧﻘﻁﺔ ﺍﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﻌﺳﻛﺭﻳﺔ Over Watch | 1 | عدد | 116000
BQ-050 | CGH | بناء ﻭﺗﺟﻬﻳﺯﻏﺭﻓﺔ ﺍﻟﺣﺭﺍﺳﺔ ﻣﻊ مظلة ونظام الإنارة لنقاط التفتيش Construction of Gatehouse with sunshade and checkpoint lighting system | 1 | عدد | 1760000
BQ-051 | AUCS | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | 2 | عدد | 2900
BQ-052 | CRPK | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | 2 | عدد | 3160
BQ-053 | GEL | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Generic Electric Lock | 1 | عدد | 1200
BQ-054 | EBGU | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) Emergency Break Glass Unit | 1 | عدد | 240
BQ-055 | DMC | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | 2 | عدد | 190
BQ-056 | UPS | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required | 1 | عدد | 29700
BQ-057 | DLSD | ﺑﺎﺏ ﺣﺩﻳﺩﻱ ﻣﻔﺻﻠﻲ ﺫﻭ ﺩﺭﻓﺗﻳﻥ ﻣﺗﻭﺍﻓﻖ ﻣﻊ DLSD ) SEC-09 ) Double Leaf Steal Door (compliant with SEC 09 "Doors") | 1 | عدد | 11355
BQ-058 | CS | بناء ﻣﺑﻧﻰ ﺍﻟﺩﻋﻡ Construction of Support Building | 1 | عدد | 376800
BQ-059 | CIDX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺩﺍﺧﻠﻳﺔ ﻋﻠﻰ ﺷﻛﻝ ﻗﺑﺔ ( CIDX ) Internal Fixed Mini Dome Camera | 1 | عدد | 2600 | [24 empty] | 1
BQ-060 | CEFX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ ( CEFX ) External Fixed Camera | 2 | عدد | 3200 | [24 empty] | 2
BQ-061 | AUCS | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | 14 | عدد | 2900 | [22 empty] | 14
BQ-062 | ICCP | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intecom Call Panel | 1 | عدد | 4950
BQ-063 | CRPK | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | 14 | عدد | 3160 | [24 empty] | 14
BQ-064 | GEL | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Generic Electric Lock | 7 | عدد | 1200 | [26 empty] | 7
BQ-065 | EBGU | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) Emergency Break Glass Unit | 7 | عدد | 240 | [26 empty] | 7
BQ-066 | DMC | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | 9 | عدد | 190 | [26 empty] | 9
BQ-067 | UPS | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required | 1 | عدد | 97600
BQ-068 | ISSW | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻠﻧﻅﺎﻡ ﺍﻻﻣﻧﻲ ISS Work Station | 3 | عدد | 6200 | [30 empty] | 3
BQ-069 | ICMU | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺭﺋﻳﺳﻳﺔ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intercom Master Unit | 3 | عدد | 5600 | [24 empty] | 3
BQ-070 | CTKB | ﻟﻭﺣﺔ ﻣﻔﺎﺗﻳﺢ ﺍﻟﺩﻭﺍﺋﺭ ﺍﻟﺗﻠﻔﺯﻳﻭﻧﻳﺔ ﺍﻟﻣﻐﻠﻘﺔ ( CTKB ) CCTV Keyboard | 3 | عدد | 1850
BQ-071 | TEL | ﻫﺎﺗﻑ ( TEL ) Telephone | 2 | عدد | 2300
BQ-072 | HTL | ﺍﻟﺧﻁ ﺍﻟﺳﺎﺧﻥ Hot Line | 2 | عدد | 2300
BQ-073 | HHR | ﺭﺍﺩﻳﻭ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ ( HHR ) Hand Held Radio | 2 | عدد | 3800
BQ-074 | SBD | ﻋﻣﻭﺩ ﺛﺎﺑﺕ ﻟﻣﻧﻊ ﺩﺧﻭﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ - ﺗﺻﻧﻳﻑ -ASTM M50-P1 Crash Rated Static Bollard (ASTM M50-P1 Rated) | 15 | عدد | 5900 | [32 empty] | 14
BQ-075 | SLSD | ﺑﺎﺏ ﺣﺩﻳﺩﻱ ﻣﻔﺻﻠﻲ ﺫﻭ ﺩﺭﻓﺔ ﻭﺍﺣﺩﺓ ﻣﺗﻭﺍﻓﻖ ﻣﻊ SLSD ) SEC-09 ) | 1 | عدد | 28500 | [32 empty] | 1 |  |  | Door sub frames &Door & frames
BQ-076 | DLSD | ﺑﺎﺏ ﺣﺩﻳﺩﻱ ﻣﻔﺻﻠﻲ ﺫﻭ ﺩﺭﻓﺗﻳﻥ ﻣﺗﻭﺍﻓﻖ ﻣﻊ DLSD ) SEC-09 ) Double Leaf Steal Door (compliant with SEC 09 "Doors") | 2 | عدد | 11355 | [32 empty] | 2 |  |  | Door sub frames &Door & frames
BQ-077 | EAB | ﺯﺭ ﺇﻧﺫﺍﺭ ﺍﻟﻁﻭﺍﺭﺉ ( EAB ) Emergency Alarm Button | 1 | عدد | 220 | [26 empty] | 1
BQ-078 | CSCC | يشمل إنشاء مبنى جديد لمركز التحكم الأمني ​​، كل ما يلزم من أعمال مدنية وإنشائية و MEP والكهربائية والمعمارية والإضاءة وتكييف الهواء والأثاث ونظام الحماية من الحرائق والاتصالات والعمل وما إلى ذلك وجميع الأعمال اللازمة المطلوبة لإكمال هذا العنصر. Construction of new security control center building include, all necessary Civil, structural, MEP, Electrical, architectural, lighting, AC, furniture , fire protection system, communication, work etc. and all necessary work required to complete this item. | 1 | عدد | 2890000 | [11 empty] | Site prep-Stacking-Excavation |  |  |  | Stacking&Excavation&Substructure Concrete |  |  |  |  | Substructure Concrete &Super Structure | Super Structure |  |  | Construction of Ballistic Wall | Construction of Ballistic Wall | Roof insulation and Toilet&Electrical foundation*40%&Security foundation*40%&Exterior plastering&Exterior paint&Doors and Windows | Roof insulation and Toilet&Electrical foundation*40%&Security foundation*40%&Exterior plastering&Exterior paint&Doors and Windows |  |  |  |  | Plumbing foundation&Doors and Windows | HVAC foundation |  | Doors and Windows
BQ-079 | 0 | ﺷﺎﺷﺔ ﺟﺩﺍﺭﻳﺔ (ﻓﻳﺩﻳﻭ ﻭﻭﻝ) Operator Dual Screens | 3 | عدد | 7300
BQ-080 | 0 | شاشة جدارية ونظام المراقبة بما في ذلك جميع حوامل الشاشات ، وأجهزة التحكم ، وعصا التحكم ، ولوحات مفاتيح الدوائر التلفزيونية المغلقة ، وما إلى ذلك ... (كمية العناصر بناءً على تصميم المقاول وفقًا لـ HCIS) ، Video Wall and monitoring System including all screens brackets, Controllers, Joysticks, CCTV keyboards, etc... (QTY of items based on contractor's design as per HCIS), | 1 | عدد | 126400 | [28 empty] | 1
BQ-081 | 0 | الخوادم والبرمجيات لإدارة ﺍﻟﻧﻅﺎﻡ ﺍﻷﻣﻧﻲ المركزي Fully redundant Central SMS (servers & software) | 1 | عدد | 1116400 | [28 empty] | 1
BQ-082 | 0 | الخوادم والبرمجيات ﻟﻧﻅﺎﻡ ﺍﻟﺩﺍﺭﺍﺕ ﺍﻟﺗﻠﻔﻳﺯﻳﻭﻧﺔ ﺍﻟﻣﻐﻠﻘﺔ ﺍﻟﻣﺭﻛﺯﻱ Fully redundant Central CCTV (servers & software) | 1 | عدد | 835200 | [28 empty] | 1
BQ-083 | 0 | الخوادم والبرمجيات ﻟﻧﻅﺎﻡ ﺍﻟﺗﺣﻛﻡ ﻓﻲ ﺍﻟﺩﺧﻭﻝ ﺍﻟﻣﺭﻛﺯﻱ Fully redundant Central ACS (servers & software) | 1 | عدد | 498000 | [28 empty] | 1
BQ-084 | 0 | الخوادم والبرمجيات ﻟﻧﻅﺎﻡ ﺍﻧﺫﺍﺭ ﺍﻻﺧﺗﺭﺍﻕ ﺍﻟﻣﺣﻳﻁﻲ ﺍﻟﻣﺭﻛﺯﻱ Fully redundant Central PIDS (servers & software) | 1 | عدد | 376500 | [28 empty] | 1
BQ-085 | 0 | نظام تسجيل فيديو مكرر بالكامل ( أجهزة وبرامج ) وفقًا لمتطلبات تسجيل HCIS Fully redundant Video Recording system (Hardware & Software) as per HCIS recording requirements | 1 | عدد | 532000 | [28 empty] | 1
BQ-086 | APF (1) | ﺳﻳﺎﺝ ﻣﺿﺎﺩ ﻟﻸﻓﺭﺍﺩ ﺍﻟﻔﺋﺔ 1 Category 1 Anti-personnel Fence | 8868 | م.ط | 1480 |  |  | 4650 |  | 2602 |  | 973 |  |  |  | 9 | [8 empty] | Excavation=950&Shuttering=710 & Rebar&Beam Casting=710&Panels=500 | 620.768 | Excavation=850&Shuttering & Rebar=10907&Beam Casting=1090&Panels =290 |  | Excavation=1140&Shuttering & Rebar=1030&Beam Casting=1030&Panels =1050 |  | Excavation=690&Shuttering & Rebar=557&Beam Casting=557&Panels =557&Concertina=850 |  | Excavation=1094&Shuttering & Rebar=1090&Beam Casting=850&Panels =875 |  | Excavation=850&Shuttering & Rebar=900&Beam Casting=900&Panels =842 |  | Excavation=307&Shuttering & Rebar=504&Beam Casting=744&Panels =1510 |  | Excavation300=&Shuttering & Rebar=300&Beam Casting=300&Panels =200
BQ-087 | AVB | Anti Vehcile Barrier حاجز مضاد المركبات | 3136 | م.ط | 1120 |  |  |  |  | 2239 | [5 empty] | 897 | [22 empty] | Excavation=462&Casting Foundations=462&AVB post Instl.=462&BF & Compaction=462
BQ-088 | IPR | ﻁﺭﻳﻖ ﺍﻟﺩﻭﺭﻳات الداخلية Inner Patrol Road | 4370 | م.ط | 650 | [9 empty] | Site prep=1311 |  | 1300 |  |  |  | Site prep.=2650-Backfilling/ Levelling=700-Sub Grade=2550-Base Course=1000 | Subase=3250&Base Coarse=2650 | Subase=825&Base Coarse=1650 | Subbase=750&Base Course=600 | Sub Grade=750&Base Course=600 | Subase=65&Base Coarse=815 | Siteprep=65&Backfilling/ Levelling=65&Sub Grade=65%Base coure=815 |  |  | Asphalt 1st=3915 | Site prep=344&Backfilling/ Levelling=355&Asphalt Layer 1=3915 | subbase=305 | subbase=305 |  |  | Base Coarse=305&Asphalt 2nd =3200 | Base Coarse=305&Asphalt 2nd =3200 | Asphalt Layer 1=455&Asphalt Layer 2=1170 | Asphalt Layer 1=455&Asphalt Layer 2=1170
BQ-089 | OPR | ﻁﺭﻳﻖ ﺍﻟﺩﻭﺭﻳﺎﺕ الخارجية Outer Patrol Road | 3190 | م.ط | 650 | [13 empty] | Backfilling/ Levelling=1950-Sub Grade=700
BQ-090 | LRTC | ﻛﺎﻣﻳﺭﺍ ﺣﺭﺍﺭﻳﺔ ﻁﻭﻳﻠﺔ ﺍﻟﻣﺩﻯ ( LRTC ) Long Range Thermal Camera | 4 | عدد | 196800 | [30 empty] | 1
BQ-091 | RAD | الرادار Radar | 2 | عدد | 543200 | [30 empty] | 2
BQ-092 | CEFX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ External Fixed Camera | 138 | عدد | 3199 | [22 empty] | 84 |  | 54
BQ-093 | CEPZ | ﻛﺎﻣﻳﺭﺍ ﻣﺗﺣﺭﻛﺔ ﺧﺎﺭﺟﻳﺔ Camera External PTZ | 24 | عدد | 8400 | [22 empty] | 4 |  | 13
BQ-094 | PSL | ﺍﻻﻧﺎﺭﺓ ﺍﻷﻣﻧﻳﺔ ﺍﻟﻣﺣﻳﻁﺔ Perimeter Security Lighting system (including all power cabling, lighting fixtures, distribution network, panels, accessories and all related electrical, control, civil and earth work and all necessary work to complete this item) | 443 | عدد | 8700 | [16 empty] | FIXTURE=443 | [9 empty] | cable=310.10 | [5 empty] | FOUNDATION BASE=99
BQ-095 | TVPL | عمود كاميرا CCTV Pole | 162 | عدد | 1649 | [32 empty] | FOUNDATION BASE=34
BQ-096 | PVS | الموجات الدقيقة ( المايكروويف ) Microwaves | 125 | عدد | 1479.2 | [28 empty] | 125
BQ-097 | PFS | مستشعرات الألياف الضوئية Sensorized Fiber | 8868 | م.ط | 360 | [28 empty] | 8868
BQ-098 | CEFX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ ( CEFX ) External Fixed Camera | 8 | عدد | 3200 | [24 empty] | 8
BQ-099 | TVPL | عمود كاميرا CCTV Pole | 6 | عدد | 1650 | [32 empty] | FOUNDATION BASE=5
BQ-100 | CEPZ | كاميرا متحركة خارجية ( CEPZ ) External PTZ Camera | 2 | عدد | 8400
BQ-101 | SGMD | بوابة منزلقة آلية ( SGMD ) Motorized Swing Gate | 4 | عدد | 49850 | [22 empty] | 4 | [5 empty] | 4*30%
BQ-102 | RAB | حاجز الذراع الكهربائي ( RAB ) Raise Arm Barrier | 4 | عدد | 9500 | [28 empty] | 4
BQ-103 | SLP | حساس استشعار أرضي ( SLP ) Safety Loop | 12 | عدد | 1800
BQ-104 | ROBK | مصدات طريق ( ROBK ) Road blocker | 4 | عدد | 172800
BQ-105 | TLTS | إشارات مرور Traffic Lights | 6 | عدد | 3200
BQ-106 | VSHM | مطبات التحكم في السرعة Speed Humps | 4 | عدد | 2300
BQ-107 | RBCP | لوحة تحكم في مصدات الطريق ( RBCP ) Road Blocker Cabinet Panel | 4 | عدد | 7200
BQ-108 | RBCS | مفتاح تحكم في مصدات الطريق ( RBCS ) Road Blocker Control Switch | 4 | عدد | 1400
BQ-109 | CRPK | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | 5 | عدد | 3160 | [24 empty] | 5
BQ-110 | ICCP | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intecom Call Panel | 1 | عدد | 4950
BQ-111 | ISSW | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻠﻧﻅﺎﻡ الأﻣﻧﻲ ISS ISS Work Station | 1 | عدد | 6200 | [30 empty] | 1
BQ-112 | ALPW | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Workstation | 1 | عدد | 6200 | [24 empty] | 1
BQ-113 | UVSW | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻧﻅﺎﻡ ﻟﻔﺣﺹ ﺍﺳﻔﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ UVSS | 1 | عدد | 6200 | [24 empty] | 1
BQ-114 | ICMU | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺭﺋﻳﺳﻳﺔ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intercom Master Unit | 1 | عدد | 5600 | [24 empty] | 1
BQ-115 | CTKB | ﻟﻭﺣﺔ ﻣﻔﺎﺗﻳﺢ ﺍﻟﺩﻭﺍﺋﺭ ﺍﻟﺗﻠﻔﺯﻳﻭﻧﻳﺔ ﺍﻟﻣﻐﻠﻘﺔ ( CTKB ) CCTV Keyboard | 1 | عدد | 1850
BQ-116 | SPAS | ﺟﻬﺎﺯ ﺇﻧﺫﺍﺭ ﺻﻭﺗﻲ ﺿﻭﺋﻲ ( SPAS ) Flashing Sounder | 2 | عدد | 1350 | [26 empty] | 2
BQ-117 | EAB | ﺯﺭ ﺇﻧﺫﺍﺭ ﺍﻟﻁﻭﺍﺭﺉ ( EAB ) Emergency Alarm Button | 1 | عدد | 220 | [26 empty] | 1
BQ-118 | UPS | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required work and materials to complete this item | 1 | عدد | 29700
BQ-119 | HHED | ﺟﻬﺎﺯ ﻛﺷﻑ ﻣﺗﻔﺟﺭﺍﺕ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ Hand-Held Explosive Detector | 1 | عدد | 132000
BQ-120 | EPB | ﺯﺭ ﺍﻟﺿﻐﻁ ﻟﻠﺧﺭﻭﺝ ( EPB ) Exit Push Button | 1 | عدد | 160 | [26 empty] | 1
BQ-121 | GEL | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Electric Lock | 1 | عدد | 1200 | [26 empty] | 1
BQ-122 | EBGU | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) Emergency Break Glass Unit | 1 | عدد | 240
BQ-123 | DMC | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | 1 | عدد | 190 | [26 empty] | 1
BQ-124 | TEL | ﻫﺎﺗﻑ ( TEL ) Telephone | 2 | عدد | 2300
BQ-125 | HTL | ﺍﻟﺧﻁ ﺍﻟﺳﺎﺧﻥ Hot Line | 1 | عدد | 2300
BQ-126 | HHR | ﺭﺍﺩﻳﻭ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ ( HHR ) Hand Held Radio | 1 | عدد | 3800
BQ-127 | CIDX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺩﺍﺧﻠﻳﺔ ﻋﻠﻰ ﺷﻛﻝ ﻗﺑﺔ ( CIDX ) Internal Fixed Mini Dome Camera | 1 | عدد | 2600 | [24 empty] | 1
BQ-128 | ALPC | ﻛﺎﻣﻳﺭﺍ ﻣﻊ ﺍﻻﻧﺎﺭﺓ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Camera | 2 | عدد | 56200 | [28 empty] | 2
BQ-129 | ALPB | ﺟﻬﺎﺯ ﺍﻧﺫﺍﺭ ﺿﻭﺋﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Beacon | 2 | عدد | 2100 | [28 empty] | 2
BQ-130 | ALPS | ﺟﻬﺎﺯ ﺍﻧﺫﺍﺭ ﺻﻭﺗﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Sounder | 2 | عدد | 1600 | [28 empty] | 2
BQ-131 | ALPL | ﺣﺳﺎﺱ ﺍﺳﺗﺷﻌﺎﺭ ﺍﺭﺿﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR | 2 | عدد | 1800 | [28 empty] | 2
BQ-132 | UVSC | ﻛﺎﻣﻳﺭﺍ ﻟﻧﻅﺎﻡ ﻓﺣﺹ ﺍﺳﻔﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ UVSS | 2 | عدد | 58000
BQ-133 | AUCS | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | 1 | عدد | 2900 | [22 empty] | 1
BQ-134 | PBRAB | ﻟﻭﺣﺔ ﺗﺣﻛﻡ ﻓﻲ ﺣﺎﺟﺯ ﺍﻟﺫﺭﺍﻉ ﺍﻟﻛﻬﺭﺑﺎﺋﻲ ( RAB ) Raise Arm Barrier Control Switch | 4 | عدد | 1400
BQ-135 | PBSG | ﻣﻔﺗﺎﺡ ﺍﻟﺗﺣﻛﻡ ﻓﻲ ﺍﻟﺑﻭﺍﺑﺔ ﺍﻟﻣﻧﺯﻟﻘﺔ Swing Gate Control Switch | 2 | عدد | 1400
BQ-136 | PVS | الموجات الدقيقة ( المايكروويف ) Microwaves | 4 | عدد | 1480 | [28 empty] | 4
BQ-137 | SBD | ﻋﻣﻭﺩ ﺛﺎﺑﺕ ﻟﻣﻧﻊ ﺩﺧﻭﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ - ﺗﺻﻧﻳﻑ - Crash Rated Static Bollard (ASTM M50-P1 Rated)ASTM M50-P1 | 88 | عدد | 5900 | [32 empty] | 82
BQ-138 | CGH | بناء ﻭﺗﺟﻬﻳﺯﻏﺭﻓﺔ ﺍﻟﺣﺭﺍﺳﺔ ﻣﻊ مظلة ونظام الإنارة لنقاط التفتيش Construction of Gatehouse with sunshade and checkpoint lighting system | 1 | عدد | 1760000 | [32 empty] | Site Prep&Stacking&Excavation&Substructure & Concrete&Super&Foundation Excavation&Foundation concreting works structure
BQ-139 | OVW | ﻧﻘﻁﺔ ﺍﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﻌﺳﻛﺭﻳﺔ Over Watch | 1 | عدد | 116000
BQ-140 | CIDX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺩﺍﺧﻠﻳﺔ ﻋﻠﻰ ﺷﻛﻝ ﻗﺑﺔ ( CIDX ) Internal Fixed Mini Dome Camera | 6 | عدد | 2600 | [24 empty] | 6
BQ-141 | CEFX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ ( CEFX ) External Fixed Camera | 3 | عدد | 3200 | [24 empty] | 3
BQ-142 | TVPL | عمود كاميرا CCTV Pole | 3 | عدد | 1650
BQ-143 | WAFC | ﻛﺎﻣﻳﺭﺍﺕ ﺛﺎﺑﺗﺔ ﺑﺯﺍﻭﻳﺔ ﻭﺍﺳﻌﺔ Wide Angle Fixed Cameras | 9 | عدد | 2900
BQ-144 | CRPK | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | 9 | عدد | 3160 | [24 empty] | 5
BQ-145 | DMC | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | 6 | عدد | 190 | [26 empty] | 6
BQ-146 | GEL | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Electric Lock | 2 | عدد | 1200 | [26 empty] | 2
BQ-147 | EBGU | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) Emergency Break Glass Unit | 2 | عدد | 240 | [26 empty] | 2
BQ-148 | EPB | ﺯﺭ ﺍﻟﺿﻐﻁ ﻟﻠﺧﺭﻭﺝ ( EPB ) Exit Push Button | 1 | عدد | 160 | [26 empty] | 1
BQ-149 | WTMD | ﺟﻬﺎﺯ ﺍﻟﻛﺷﻑ ﻋﻥ ﺍﻟﻣﻌﺎﺩﻥ ﺑﺎﻟﻣﺭﻭﺭ ( WTMD ) Walk Through Metal Detector | 1 | عدد | 24000 | [22 empty] | 1
BQ-150 | FHTS | ﺑﺎﺏ ﺩﻭﺍﺭ ﻛﺎﻣﻝ ﺍﻻﺭﺗﻔﺎﻉ ( FHTS ) Full Height Turnstile | 3 | عدد | 50400
BQ-151 | TEL | ﻫﺎﺗﻑ ( TEL ) Telephone | 2 | عدد | 2300
BQ-152 | HTL | ﺍﻟﺧﻁ ﺍﻟﺳﺎﺧﻥ Hot Line | 1 | عدد | 2300
BQ-153 | HHR | ﺭﺍﺩﻳﻭ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ ( HHR ) Hand Held Radio | 1 | عدد | 3800
BQ-154 | IDW | ﻣﺣﻁﺔ ﻋﻣﻝ ﺑﻁﺎﻗﺔ ﺍﻟﻬﻭﻳﺔ ID Workstation | 1 | عدد | 6200
BQ-155 | IDC | ﻛﺎﻣﻳﺭﺍ ﺭﻗﻣﻳﺔ ﻟﺑﻁﺎﻗﺔ ﺍﻟﻬﻭﻳﺔ ID Digital Camera | 1 | عدد | 1800
BQ-156 | ER | ﻗﺎﺭﺉ ﺍﻟﺗﺳﺟﻳﻝ Enrollment Reader | 1 | عدد | 1650 | [26 empty] | 1
BQ-157 | CP | ﻁﺎﺑﻌﺔ ﺍﻟﺑﻁﺎﻗﺔ Card Printer | 1 | عدد | 19400 | [24 empty] | 1
BQ-158 | BXRY | ﻣﺎﺳﺣﺔ ﺍﻷﻣﺗﻌﺔ ﺑﺎﻷﺷﻌﺔ ﺍﻟﺳﻳﻧﻳﺔ X-Ray Baggage Scanner | 1 | عدد | 152000 | [18 empty] | 1
BQ-159 | HHED | ﺟﻬﺎﺯ ﻛﺷﻑ ﻣﺗﻔﺟﺭﺍﺕ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ Hand-Held Explosive Detector | 1 | عدد | 132000
BQ-160 | HHMD | ﺟﻬﺎﺯ ﻛﺷﻑ ﺍﻟﻣﻌﺎﺩﻥ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ Hand-Held Metal detector | 1 | عدد | 1300 | [22 empty] | 1
BQ-161 | UPS | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required | 1 | عدد | 29700
BQ-162 | DLSD | ﺑﺎﺏ ﺣﺩﻳﺩﻱ ﻣﻔﺻﻠﻲ ﺫﻭ ﺩﺭﻓﺗﻳﻥ ﻣﺗﻭﺍﻓﻖ ﻣﻊ DLSD ) SEC-09 ) Double Leaf Steel Door (Compliant with SEC-09 "Doors")8 | 2 | عدد | 11355 | [32 empty] | 2
BQ-163 | CSB | بناء ﻣﺑﻧﻰ ﺍﻟﺗﻔﺗﻳﺵ ﻭﻣﺭﻛﺯ ﺍﻟﺯﻭﺍﺭ Construction of Search Facility & Vistor Center | 1 | عدد | 2340000 | [15 empty] | Stacking&Excavation |  |  |  |  | Substructure Concrete&Super Structure | Super Structure |  |  | Construction of Ballistic Wall | Construction of Ballistic Wall | Roof insulation and Toilet&Electrical foundation&Hvac foundation&Exterior plastering&Exterior paint | Roof insulation and Toilet&Electrical foundation&Hvac foundation&Exterior plastering&Exterior paint | Security foundation | Security foundation |  |  | Plumbing foundation&Doors and Windows | Plumbing foundation
BQ-164 | CEFX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ ( CEFX ) External Fixed Camera | 8 | عدد | 3200 | [24 empty] | 8
BQ-165 | TVPL | عمود كاميرا CCTV Pole | 4 | عدد | 1650
BQ-166 | CEPZ | كاميرا متحركة خارجية ( CEPZ ) External PTZ Camera | 2 | عدد | 8400
BQ-167 | SGMD | بوابة منزلقة آلية ( SGMD ) Motorized Swing Gate | 4 | عدد | 49850 | [22 empty] | 4 | [5 empty] | 4*30%
BQ-168 | RAB | حاجز الذراع الكهربائي ( RAB ) Raise Arm Barrier | 4 | عدد | 9500 | [28 empty] | 4
BQ-169 | SLP | حساس استشعار أرضي ( SLP ) Safety Loop | 12 | عدد | 1800
BQ-170 | ROBK | مصدات طريق ( ROBK ) Road blocker | 4 | عدد | 172800
BQ-171 | TLTS | إشارات مرور Traffic Lights | 6 | عدد | 3200
BQ-172 | VSHM | مطبات التحكم في السرعة Speed Humps | 4 | عدد | 2300
BQ-173 | RBCP | لوحة تحكم في مصدات الطريق ( RBCP ) Road Blocker Cabinet Panel | 4 | عدد | 7200
BQ-174 | RBCS | مفتاح تحكم في مصدات الطريق ( RBCS ) Road Blocker Control Switch | 4 | عدد | 1400
BQ-175 | CRPK | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | 5 | عدد | 3160 | [24 empty] | 5
BQ-176 | ICCP | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intecom Call Panel | 1 | عدد | 4950
BQ-177 | ISSW | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻠﻧﻅﺎﻡ الأﻣﻧﻲ ISS ISS Work Station | 1 | عدد | 6200 | [30 empty] | 1
BQ-178 | ALPW | ﻣﺣﻁﺔ ﻋﻣﻝ ﻁﺭﻓﻳﺔ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Workstation | 1 | عدد | 6200 | [24 empty] | 1
BQ-179 | ICMU | ﻭﺣﺩﺓ ﺍﺗﺻﺎﻝ ﺩﺍﺧﻠﻲ ﺭﺋﻳﺳﻳﺔ ﺍﻧﺗﺭﻛﻭﻡ ( ICCP ) Intercom Master Unit | 1 | عدد | 5600 | [24 empty] | 1
BQ-180 | CTKB | ﻟﻭﺣﺔ ﻣﻔﺎﺗﻳﺢ ﺍﻟﺩﻭﺍﺋﺭ ﺍﻟﺗﻠﻔﺯﻳﻭﻧﻳﺔ ﺍﻟﻣﻐﻠﻘﺔ ( CTKB ) CCTV Keyboard | 1 | عدد | 1850
BQ-181 | SPAS | ﺟﻬﺎﺯ ﺇﻧﺫﺍﺭ ﺻﻭﺗﻲ ﺿﻭﺋﻲ ( SPAS ) Flashing Sounder | 2 | عدد | 1350 | [26 empty] | 2
BQ-182 | EAB | ﺯﺭ ﺇﻧﺫﺍﺭ ﺍﻟﻁﻭﺍﺭﺉ ( EAB ) Emergency Alarm Button | 1 | عدد | 220 | [26 empty] | 1
BQ-183 | UPS | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required | 1 | عدد | 29700
BQ-184 | HHED | ﺟﻬﺎﺯ ﻛﺷﻑ ﻣﺗﻔﺟﺭﺍﺕ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ Hand-Held Explosive Detector | 1 | عدد | 132000
BQ-185 | EPB | ﺯﺭ ﺍﻟﺿﻐﻁ ﻟﻠﺧﺭﻭﺝ ( EPB ) Exit Push Button | 1 | عدد | 160 | [26 empty] | 1
BQ-186 | GEL | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Electric Lock | 1 | عدد | 1200 | [26 empty] | 1
BQ-187 | EBGU | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) Emergency Break Glass Unit | 1 | عدد | 240 | [26 empty] | 1
BQ-188 | DMC | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | 1 | عدد | 190 | [26 empty] | 1
BQ-189 | TEL | ﻫﺎﺗﻑ ( TEL ) Telephone | 2 | عدد | 2300
BQ-190 | HTL | ﺍﻟﺧﻁ ﺍﻟﺳﺎﺧﻥ Hot Line | 1 | عدد | 2300
BQ-191 | HHR | ﺭﺍﺩﻳﻭ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ ( HHR ) Hand Held Radio | 1 | عدد | 3800
BQ-192 | CIDX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺩﺍﺧﻠﻳﺔ ﻋﻠﻰ ﺷﻛﻝ ﻗﺑﺔ ( CIDX ) Internal Fixed Mini Dome Camera | 1 | عدد | 2600 | [24 empty] | 1
BQ-193 | ALPC | ﻛﺎﻣﻳﺭﺍ ﻣﻊ ﺍﻻﻧﺎﺭﺓ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Camera | 2 | عدد | 56200 | [28 empty] | 2
BQ-194 | ALPB | ﺟﻬﺎﺯ ﺍﻧﺫﺍﺭ ﺿﻭﺋﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Beacon | 2 | عدد | 2100
BQ-195 | ALPS | ﺟﻬﺎﺯ ﺍﻧﺫﺍﺭ ﺻﻭﺗﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Sounder | 2 | عدد | 1600
BQ-196 | ALPL | ﺣﺳﺎﺱ ﺍﺳﺗﺷﻌﺎﺭ ﺍﺭﺿﻲ ﻟﻧﻅﺎﻡ ﺍﻟﺗﻌﺭﻑ ﻋﻠﻰ ﻟﻭﺣﺎﺕ ﺍﻟﻣﺭﻛﺑﺎﺕ ﺍﻻﻟﻛﺗﺭﻭﻧﻲ ALPR ALPR Loop Sensor | 2 | عدد | 1800 | [28 empty] | 2
BQ-197 | AUCS | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | 1 | عدد | 2900 | [22 empty] | 1
BQ-198 | PBRAB | ﻟﻭﺣﺔ ﺗﺣﻛﻡ ﻓﻲ ﺣﺎﺟﺯ ﺍﻟﺫﺭﺍﻉ ﺍﻟﻛﻬﺭﺑﺎﺋﻲ ( RAB ) Raise Arm Barrier Control Switch | 4 | عدد | 1400
BQ-199 | PBSG | ﻣﻔﺗﺎﺡ ﺍﻟﺗﺣﻛﻡ ﻓﻲ ﺍﻟﺑﻭﺍﺑﺔ ﺍﻟﻣﻧﺯﻟﻘﺔ Swing Gate Control Switch | 4 | عدد | 1400
BQ-200 | PVS | الموجات الدقيقة ( المايكروويف ) Microwaves | 4 | عدد | 1480 | [28 empty] | 4
BQ-201 | SBD | ﻋﻣﻭﺩ ﺛﺎﺑﺕ ﻟﻣﻧﻊ ﺩﺧﻭﻝ ﺍﻟﻣﺭﻛﺑﺎﺕ - ﺗﺻﻧﻳﻑ -ASTM M50-P1 Crash Rated Static Bollard (ASTM M50-P1 Rated) | 82 | عدد | 5900
BQ-202 | CGH | بناء ﻭﺗﺟﻬﻳﺯﻏﺭﻓﺔ ﺍﻟﺣﺭﺍﺳﺔ ﻣﻊ مظلة ونظام الإنارة لنقاط التفتيش Construction of Gatehouse with sunshade and checkpoint lighting system | 1 | عدد | 1760000
BQ-203 | CIDX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺩﺍﺧﻠﻳﺔ ﻋﻠﻰ ﺷﻛﻝ ﻗﺑﺔ ( CIDX ) Internal Fixed Mini Dome Camera | 6 | عدد | 2600 | [24 empty] | 6
BQ-204 | CEFX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ ( CEFX ) External Fixed Camera | 3 | عدد | 3200 | [24 empty] | 3
BQ-205 | TVPL | عمود كاميرا CCTV Pole | 3 | عدد | 1650
BQ-206 | WAFC | ﻛﺎﻣﻳﺭﺍﺕ ﺛﺎﺑﺗﺔ ﺑﺯﺍﻭﻳﺔ ﻭﺍﺳﻌﺔ Wide Angle Fixed Cameras | 9 | عدد | 2900
BQ-207 | CRPK | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | 9 | عدد | 3160 | [24 empty] | 5
BQ-208 | DMC | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | 6 | عدد | 190 | [26 empty] | 6
BQ-209 | GEL | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Electric Lock | 2 | عدد | 1200 | [26 empty] | 2
BQ-210 | EBGU | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) Emergency Break Glass Unit | 2 | عدد | 240 | [26 empty] | 2
BQ-211 | EPB | ﺯﺭ ﺍﻟﺿﻐﻁ ﻟﻠﺧﺭﻭﺝ ( EPB ) Exit Push Button | 1 | عدد | 160 | [26 empty] | 1
BQ-212 | WTMD | ﺟﻬﺎﺯ ﺍﻟﻛﺷﻑ ﻋﻥ ﺍﻟﻣﻌﺎﺩﻥ ﺑﺎﻟﻣﺭﻭﺭ ( WTMD ) Walk Through Metal Detector | 1 | عدد | 24000 | [22 empty] | 1
BQ-213 | FHTS | ﺑﺎﺏ ﺩﻭﺍﺭ ﻛﺎﻣﻝ ﺍﻻﺭﺗﻔﺎﻉ ( FHTS ) Full Height Turnstile | 3 | عدد | 50400
BQ-214 | TEL | ﻫﺎﺗﻑ ( TEL ) Telephone | 2 | عدد | 2300
BQ-215 | HTL | ﺍﻟﺧﻁ ﺍﻟﺳﺎﺧﻥ Hot Line | 1 | عدد | 2300
BQ-216 | HHR | ﺭﺍﺩﻳﻭ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ ( HHR ) | 1 | عدد | 3800
BQ-217 | IDW | ﻣﺣﻁﺔ ﻋﻣﻝ ﺑﻁﺎﻗﺔ ﺍﻟﻬﻭﻳﺔ ID Workstation | 1 | عدد | 6200 | [30 empty] | 1
BQ-218 | IDC | ﻛﺎﻣﻳﺭﺍ ﺭﻗﻣﻳﺔ ﻟﺑﻁﺎﻗﺔ ﺍﻟﻬﻭﻳﺔ ID Digital Camera | 1 | عدد | 1800
BQ-219 | ER | ﻗﺎﺭﺉ ﺍﻟﺗﺳﺟﻳﻝ Enrollment Reader | 1 | عدد | 1650 | [26 empty] | 1
BQ-220 | CP | ﻁﺎﺑﻌﺔ ﺍﻟﺑﻁﺎﻗﺔ Card Printer | 1 | عدد | 19400 | [24 empty] | 1
BQ-221 | BXRY | ﻣﺎﺳﺣﺔ ﺍﻷﻣﺗﻌﺔ ﺑﺎﻷﺷﻌﺔ ﺍﻟﺳﻳﻧﻳﺔ X-Ray Baggage Scanner | 1 | عدد | 152000 | [18 empty] | 1
BQ-222 | HHED | ﺟﻬﺎﺯ ﻛﺷﻑ ﻣﺗﻔﺟﺭﺍﺕ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ Hand-Held Explosive Detector | 1 | عدد | 132000
BQ-223 | HHMD | ﺟﻬﺎﺯ ﻛﺷﻑ ﺍﻟﻣﻌﺎﺩﻥ ﻣﺣﻣﻭﻝ ﺑﺎﻟﻳﺩ Hand-Held Metal detector | 1 | عدد | 1300 | [22 empty] | 1
BQ-224 | UPS | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required | 1 | عدد | 29700
BQ-225 | DLSD | ﺑﺎﺏ ﺣﺩﻳﺩﻱ ﻣﻔﺻﻠﻲ ﺫﻭ ﺩﺭﻓﺗﻳﻥ ﻣﺗﻭﺍﻓﻖ ﻣﻊDouble Leaf Steel Door (Compliant with SEC-09 "Doors") DLSD ) SEC-09 ) | 2 | عدد | 11355 | [32 empty] | 2
BQ-226 | CSB | بناء ﻣﺑﻧﻰ ﺍﻟﺗﻔﺗﻳﺵ ﻭﻣﺭﻛﺯ ﺍﻟﺯﻭﺍﺭ Construction of Search Facility & Vistor Center | 1 | عدد | 2340000
BQ-227 | CEFXVA | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ ﻣﻊ ﺗﺣﻠﻳﻼﺕ ﺍﻟﻔﻳﺩﻳﻭ (CEFXVA) External Fixed Camera with Video Analytics | 1 | عدد | 3500
BQ-228 | TVPL | عمود كاميرا CCTV Pole | 1 | عدد | 1650
BQ-229 | SWMO | ﺑﻭﺍﺑﺔ ﻣﻔﺻﻠﻳﺔ ﻳﺩﻭﻳﺔManually Operated Swing Gate | 1 | عدد | 49850
BQ-230 | VSHM | ﻣﻁﺑﺎﺕ ﺍﻟﺗﺣﻛﻡ ﻓﻲ ﺍﻟﺳﺭﻋﺔ Speed Humps | 2 | عدد | 2300
BQ-231 | RBD | ﺫﺭﺍﻉ ﻫﻳﺩﺭﻭﻟﻳﻛﻲ ﻣﺿﺎﺽ ﻟﻠﻣﺭﻛﺑﺎﺕ (ﺗﺻﻧﻳﻑ ASTM M50-P1) Crash Rated Arm Barrier (ASTM M50-P1 Rated) | 1 | عدد | 207915
BQ-232 | CIDX | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺩﺍﺧﻠﻳﺔ ﻋﻠﻰ ﺷﻛﻝ ﻗﺑﺔ ( CIDX ) Camera Internal Fixed Dome | 1 | عدد | 2600 | [24 empty] | 1
BQ-233 | AUCS | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | 9 | عدد | 2900 | [22 empty] | 9
BQ-234 | CRPK | ﻗﺎﺭﺉ ﺑﻁﺎﻗﺎﺕ ﻣﻊ ﻟﻭﺣﺔ ﺍﻟﻣﻔﺎﺗﻳﺢ ( CRPK ) Card Reader w/ Keypad | 10 | عدد | 3160 | [24 empty] | 10
BQ-235 | GEL | ﻗﻔﻝ ﻛﻬﺭﺑﺎﺋﻲ ( GEL ) Electric Lock | 5 | عدد | 1200 | [26 empty] | 5
BQ-236 | EBGU | ﻭﺣﺩﺓ ﻛﺳﺭ ﺍﻟﺯﺟﺎﺝ ﻟﻠﻁﻭﺍﺭﺉ ( EBGU ) Emergency Break Glass Unit | 5 | عدد | 240 | [26 empty] | 5
BQ-237 | DMC | ﺣﺳﺎﺱ ﺗﻼﻣﺳﻲ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻻﺑﻭﺍﺏ ( DMC ) Door Monitoring Contact | 12 | عدد | 190 | [26 empty] | 12
BQ-238 | EPB | ﺯﺭ ﺍﻟﺿﻐﻁ ﻟﻠﺧﺭﻭﺝ ( EPB ) Exit Push Button | 1 | عدد | 160 | [26 empty] | 1
BQ-239 | UPS | نظام إمداد الطاقة غير المنقطع مع جميع الأعمال والمواد المطلوبة لإكمال نظام هذا العنصر بجميع الأعمال والمواد المطلوبة لإكمال هذا العنصر Uninterruptible Power Supply system with all required work and materials to complete this item system with all required | 1 | عدد | 29700
BQ-240 | EAB | ﺯﺭ ﺇﻧﺫﺍﺭ ﺍﻟﻁﻭﺍﺭﺉ ( EAB ) Emergency Alarm Button | 1 | عدد | 220
BQ-241 | SBD | ﻋﻣﻭﺩ ﺛﺎﺑﺕ ﻣﺿﺎﺽ ﻟﻠﻣﺭﻛﺑﺎﺕ- M50 P1 ﺗﺻﻧﻳﻑ (SBD) Crash Rated Static Bollard (ASTM M50-P1 Rated) | 8 | عدد | 5900
BQ-242 | DLSD | ﺑﺎﺏ ﺣﺩﻳﺩﻱ ﻣﻔﺻﻠﻲ ﺫﻭ ﺩﺭﻓﺗﻳﻥ ﻣﺗﻭﺍﻓﻖ ﻣﻊ DLSD ) SEC-09 ) | 2 | عدد | 11355

## Sum Traker (hidden)
ITEM | DESCRIPTION | PROC | [6 empty] | ITEM | DESCRIPTION | imple | [7 empty] | TESTING & COMMISSIONING |  | Handover
BQ-061 | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | #INVOICE | Camera | [5 empty] | BQ-061 | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | #INVOICE | Camera Mounting | Configuration | Cabling | Termination | Testing |  |  | RFI / Config. | Acceptance
|  | #12 | 14
ITEM | DESCRIPTION | PROC | [6 empty] | ITEM | DESCRIPTION | imple
BQ-086 | ﺳﻳﺎﺝ ﻣﺿﺎﺩ ﻟﻸﻓﺭﺍﺩ ﺍﻟﻔﺋﺔ 1 Category 1 Anti-personnel Fence | #INVOICE | PROC | [5 empty] | BQ-086 | ﺳﻳﺎﺝ ﻣﺿﺎﺩ ﻟﻸﻓﺭﺍﺩ ﺍﻟﻔﺋﺔ 1 Category 1 Anti-personnel Fence | #INVOICE | Excavation | Shuttering & Rebar |  | Beam Casting | Panels | Concertina
|  | #02 | 4650 | [7 empty] | #10 | 950 | 710 |  | 710 | 500
|  | #03 | 2602 | [7 empty] | #11 | 850 | 1090 |  | 1090 | 290
|  | #04 | 973 | [7 empty] | #12 | 1140 | 1030 |  | 1030 | 1050
|  | #06 | 9 | [7 empty] | #13 | 690 | 557 |  | 557 | 785 | 850
|  | #11 | 620.768 | [7 empty] | #14 | 1094 | 1090 |  | 850 | 875 |  |  | 1094 | 1090 | 850 | 875 | 875
|  | #12 | [8 empty] | #15 | 850 | 900 |  | 900 | 842
[11 empty] | #16 | 307 | 504 |  | 744 | 1510
[11 empty] | #17 | 300 | 300 |  | 300 | 200
[11 empty] | #18 | 71 | 71 |  | 71 | 171 | 700
ITEM | DESCRIPTION | PROC | [6 empty] | ITEM | DESCRIPTION | imple
BQ-087 | Anti Vehcile Barrier حاجز مضاد المركبات | #INVOICE | PROC | [5 empty] | BQ-087 | Anti Vehcile Barrier حاجز مضاد المركبات | #INVOICE | Excavation | Casting Foundations |  | AVB post Instl. | Beam/Rope Installation | BF & Compaction
|  | #03 | 2602 | [7 empty] | #17 | 462 | 462 |  | 462 |  | 462
|  | #06 | 897 | [7 empty] | #18 | 490 | 250 |  | 250 |  | 250
ITEM | DESCRIPTION | PROC | [6 empty] | ITEM | DESCRIPTION | imple | [6 empty] | TESTING & COMMISSIONING |  | Handover
BQ-088 | ﻁﺭﻳﻖ ﺍﻟﺩﻭﺭﻳات الداخلية Inner Patrol Road | #INVOICE | Subase | Base Coarse | Asphalt 1st | Asphalt 2nd |  |  | BQ-088 | ﻁﺭﻳﻖ ﺍﻟﺩﻭﺭﻳات الداخلية Inner Patrol Road | #INVOICE | Site prep. | Backfilling/ Levelling | Sub Base | Base Course | Asphalt Layer 1 | Asphalt Layer 2 | RFI / Config. | Acceptance
|  | #09 | 3250 | 2650 | [6 empty] | #05 | 1311
|  | #10 | 750 | 600 | [6 empty] | #06 |  | 1300
|  | #11 | 65 | 815 | [6 empty] | #07 |  | 1950 | 700
|  | #13 |  |  | 3915 | [5 empty] | #08 | 2650 | 700 | 2550 | 1000
|  | #14 | 305 | [7 empty] | #09 |  |  |  | 1650
|  | #16 |  | 305 |  | 3200 |  |  |  |  | #10 |  |  | 750 | 600
|  | #17 |  |  | 455 | 1170 |  |  |  |  | #11 | 65 | 65 | 65 | 815
#12
[11 empty] | #13 | 344 | 355 |  |  | 3915
|  |  | 4370 | 4370 | 4370 | 4370 |  |  |  |  | #14 |  |  | 305
[11 empty] | #16 |  |  |  | 305 |  | 3200
[11 empty] | #17 |  |  |  |  | 455 | 1170
[11 empty] | #24 | [6 empty] | ✓ | ✓ | ✓
[12 empty] | 4370 | 4370 | 4370 | 4370 | 4370 | 4370
BQ-089 | ﻁﺭﻳﻖ ﺍﻟﺩﻭﺭﻳﺎﺕ الخارجية Outer Patrol Road | #INVOICE | Subase | Base Coarse | Asphalt 1st | Asphalt 2nd |  |  | BQ-089 | ﻁﺭﻳﻖ ﺍﻟﺩﻭﺭﻳﺎﺕ الخارجية Outer Patrol Road | #INVOICE | Site prep. | Backfilling/ Levelling | Sub Base | Base Course | Asphalt Layer 1 | Asphalt Layer 2 | RFI / Config. | Acceptance
|  | #23 | 200 | [7 empty] | #23 | 200 | 200
|  | #24 | 2000 | 2000 | 1300 | [5 empty] | #24 | 2000 | 2000 | 2000 | 1500 | 1300
|  | #25 | 990 | 650 | 1350 | [5 empty] | #25 | 990 | 990 | 650 | 1150 | 1350
|  | #26 |  | 540 | 540 | 3190 |  |  |  |  | #26 |  |  | 540 | 540 | 540 | 3190 | ✓ | ✓ | ✓
|  | #27 | [8 empty] | #27
|  | #28 | [8 empty] | #28
|  | #29 | [8 empty] | #29
#30
#31
|  |  | 3190 | 3190 | 3190 | 3190 |  |  |  |  | #32
#33
#34
[12 empty] | 3190 | 3190 | 3190 | 3190 | 3190 | 3190
ITEM | DESCRIPTION | PROC | [6 empty] | ITEM | DESCRIPTION | imple | [7 empty] | TESTING & COMMISSIONING |  | Handover
BQ-078 | إنشاء مبنى جديد لمركز التحكم الأمني ​​. | #INVOICE | Substructure & Concrete | Super Structure | Construction of Ballistic Wall | Finishing |  |  | BQ-078 | إنشاء مبنى جديد لمركز التحكم الأمني ​​. | #INVOICE | Site prep. | Stacking | Excavation | Substructure & Concrete | Super structure | Construction of Ballistic Wall | Finishng Building | RFI / Config. | Acceptance
|  | #11 | ✓ | ✓ | [6 empty] | #06 | ✓ | ✓ | ✓
|  | #13 |  |  | ✓ | [5 empty] | #08 |  | ✓ | ✓ | ✓
[11 empty] | #11 |  |  |  |  | ✓
[11 empty] | #13 | [5 empty] | ✓
|  | #14 | #17 | [7 empty] | #14 | #17
| Roof insulation and Toilet | ✓ | [7 empty] | Roof insulation and Toilet | ✓
| Plumbing foundation |  | ✓ | [6 empty] | Plumbing foundation
| Electrical foundation | ✓*40% | [7 empty] | Electrical foundation | ✓
| Hvac foundation | [8 empty] | Hvac foundation |  | ✓
| Security foundation | ✓*40% | [7 empty] | Security foundation | ✓
| Fire alarm foundation | [8 empty] | Fire alarm foundation
| Interior plastering | [8 empty] | Interior plastering
| Exterior plastering | ✓ | [7 empty] | Exterior plastering | ✓
| Ceiling | [8 empty] | Ceiling
| Interior paint | [8 empty] | Interior paint
| Exterior paint | ✓ | [7 empty] | Exterior paint | ✓
| Doors and Windows | ✓ | ✓ | [6 empty] | Doors and Windows
| Tiles | [8 empty] | Tiles
| Epoxy | [8 empty] | Epoxy
| Raised floor | [8 empty] | Raised floor | ✓
| Kerbstone and interlock | [8 empty] | Kerbstone and interlock
| Handrail | [8 empty] | Handrail
| plumbing finishing | [8 empty] | plumbing finishing
| Electrical finishing | [8 empty] | Electrical finishing
| Hvac finishing | [8 empty] | Hvac finishing
| Security finishing | [8 empty] | Security finishing
| Fire alarm finishing | [8 empty] | Fire alarm finishing
| Building furniture | [8 empty] | Building furniture
ITEM | DESCRIPTION | PROC | [6 empty] | ITEM | DESCRIPTION | imple | [7 empty] | TESTING & COMMISSIONING |  | Handover
BQ-133 | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | #INVOICE | Camera | [5 empty] | BQ-133 | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | #INVOICE | Camera Mounting | Configuration | Cabling | Termination | Testing |  |  | RFI / Config. | Acceptance
|  | #12 | 1
ITEM | DESCRIPTION | PROC | [6 empty] | ITEM | DESCRIPTION | imple | [7 empty] | TESTING & COMMISSIONING |  | Handover
BQ-163 | بناء ﻣﺑﻧﻰ ﺍﻟﺗﻔﺗﻳﺵ ﻭﻣﺭﻛﺯ ﺍﻟﺯﻭﺍﺭ Construction of Search Facility & Vistor Center | #INVOICE | Substructure & Concrete | Super Structure | Construction of Ballistic Wall | Finishing |  |  | BQ-163 | بناء ﻣﺑﻧﻰ ﺍﻟﺗﻔﺗﻳﺵ ﻭﻣﺭﻛﺯ ﺍﻟﺯﻭﺍﺭ Construction of Search Facility & Vistor Center | #INVOICE | Site prep. | Stacking | Excavation | Substructure & Concrete | Super structure | Construction of Ballistic Wall | Finishng Building | RFI / Config. | Acceptance
|  | #11 | ✓ | ✓ | [6 empty] | #06
|  | #13 |  |  | ✓ | [5 empty] | #08 |  | ✓ | ✓
[11 empty] | #11 |  |  |  |  | ✓
[11 empty] | #13 | [5 empty] | ✓
|  | #14 | #15 | #17 | [6 empty] | #14
| Roof insulation and Toilet | ✓ | [7 empty] | Roof insulation and Toilet | ✓
| Plumbing foundation |  |  | ✓ | [5 empty] | Plumbing foundation
| Electrical foundation | ✓ | [7 empty] | Electrical foundation | ✓
| Hvac foundation | ✓ | [7 empty] | Hvac foundation | ✓
| Security foundation |  | ✓ | [6 empty] | Security foundation
| Fire alarm foundation | [8 empty] | Fire alarm foundation
| Interior plastering | [8 empty] | Interior plastering
| Exterior plastering | ✓ | [7 empty] | Exterior plastering | ✓
| Ceiling | [8 empty] | Ceiling
| Interior paint | [8 empty] | Interior paint
| Exterior paint | ✓ | [7 empty] | Exterior paint | ✓
| Doors and Windows |  |  | ✓ | [5 empty] | Doors and Windows
| Tiles | [8 empty] | Tiles
| Epoxy | [8 empty] | Epoxy
| Raised floor | [8 empty] | Raised floor
| Kerbstone and interlock | [8 empty] | Kerbstone and interlock
| Handrail | [8 empty] | Handrail
| plumbing finishing | [8 empty] | plumbing finishing
| Electrical finishing | [8 empty] | Electrical finishing
| Hvac finishing | [8 empty] | Hvac finishing
| Security finishing | [8 empty] | Security finishing
| Fire alarm finishing | [8 empty] | Fire alarm finishing
| Building furniture | [8 empty] | Building furniture
ITEM | DESCRIPTION | PROC | [6 empty] | ITEM | DESCRIPTION | imple | [7 empty] | TESTING & COMMISSIONING |  | Handover
BQ-092 | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ External Fixed Camera | #INVOICE | Camera | [5 empty] | BQ-092 | ﻛﺎﻣﻳﺭﺍ ﺛﺎﺑﺗﺔ ﺧﺎﺭﺟﻳﺔ External Fixed Camera | #INVOICE | Camera Mounting | Configuration | Cabling | Termination | Testing |  |  | RFI / Config. | Acceptance
|  | #12 | 84
ITEM | DESCRIPTION | PROC | [6 empty] | ITEM | DESCRIPTION | imple | [7 empty] | TESTING & COMMISSIONING |  | Handover
BQ-093 | ﻛﺎﻣﻳﺭﺍ ﻣﺗﺣﺭﻛﺔ ﺧﺎﺭﺟﻳﺔ Camera External PTZ | #INVOICE | Camera | [5 empty] | BQ-093 | ﻛﺎﻣﻳﺭﺍ ﻣﺗﺣﺭﻛﺔ ﺧﺎﺭﺟﻳﺔ Camera External PTZ | #INVOICE | Camera Mounting | Configuration | Cabling | Termination | Testing |  |  | RFI / Config. | Acceptance
|  | #12 | 4
ITEM | DESCRIPTION | PROC | [6 empty] | ITEM | DESCRIPTION | imple | [7 empty] | TESTING & COMMISSIONING |  | Handover
BQ-094 | ﺍﻻﻧﺎﺭﺓ ﺍﻷﻣﻧﻳﺔ ﺍﻟﻣﺣﻳﻁﺔ | #INVOICE | FIXTURE | POLE | CABLE | CONTROL PANEL | FUSE AND BREAKER | FOUNDATION BASE | BQ-094 | ﺍﻻﻧﺎﺭﺓ ﺍﻷﻣﻧﻳﺔ ﺍﻟﻣﺣﻳﻁﺔ | #INVOICE | Excavation | Casting Foundations | Pole Installation | Lighting Fixtures | Component Installation | Cabling & Termination | BF & Compaction | RFI / Config. | Acceptance
|  | #09 | 443
|  | #14 |  |  | 310.1
|  | #17 | [5 empty] | 99
|  | #18 | [5 empty] | 70
ITEM | DESCRIPTION | PROC | [6 empty] | ITEM | DESCRIPTION | imple | [7 empty] | TESTING & COMMISSIONING |  | Handover
BQ-095 | عمود كاميرا CCTV Pole | #INVOICE | POLE | FOUNDATION BASE |  |  |  |  | BQ-095 | عمود كاميرا CCTV Pole | #INVOICE | Precasting Foundations | Excavation | Lean Conc. | Foundation Installation | Pole Installation | BF & Compaction | Pole Alignment | RFI / Config. | Acceptance
|  | #17 |  | 34
|  | #18 |  | 9
ITEM | DESCRIPTION | PROC | [6 empty] | ITEM | DESCRIPTION | imple | [7 empty] | TESTING & COMMISSIONING |  | Handover
BQ-099 | عمود كاميرا CCTV Pole | #INVOICE | POLE | FOUNDATION BASE |  |  |  |  | BQ-099 | عمود كاميرا CCTV Pole | #INVOICE | Precasting Foundations | Excavation | Lean Conc. | Foundation Installation | Pole Installation | BF & Compaction | Pole Alignment | RFI / Config. | Acceptance
|  | #17 |  | 5
ITEM | DESCRIPTION | PROC |  |  | 55% |  |  |  | ITEM | DESCRIPTION | imple | [6 empty] | TESTING & COMMISSIONING |  | Handover
BQ-101 | بوابة منزلقة آلية ( SGMD ) Motorized Swing Gate | #INVOICE | Gate | Motor | Padlock |  |  |  | BQ-101 | بوابة منزلقة آلية ( SGMD ) Motorized Swing Gate | #INVOICE | Excavation | Casting Foundations | Gate Installation | Backfilling | Cabling & Termination | Testing | RFI / Config. | Acceptance
|  |  | 70% | 20% | 10% | [6 empty] | 25% | 15% | 20% | 20% | 10% | 10%
|  | #12 | 4
ITEM | DESCRIPTION | PROC |  |  | 55% |  |  |  | ITEM | DESCRIPTION | imple | [6 empty] | TESTING & COMMISSIONING |  | Handover
BQ-167 | بوابة منزلقة آلية ( SGMD ) Motorized Swing Gate | #INVOICE | Gate | Motor | Padlock |  |  |  | BQ-167 | بوابة منزلقة آلية ( SGMD ) Motorized Swing Gate | #INVOICE | Excavation | Casting Foundations | Gate Installation | Backfilling | Cabling & Termination | Testing | RFI / Config. | Acceptance
|  |  | 70% | 20% | 10% | [6 empty] | 25% | 15% | 20% | 20% | 10% | 10%
|  | #12 | 4
ITEM | DESCRIPTION | PROC | [6 empty] | ITEM | DESCRIPTION | imple | [7 empty] | TESTING & COMMISSIONING |  | Handover
BQ-197 | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | #INVOICE | Camera | [5 empty] | BQ-197 | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | #INVOICE | Camera Mounting | Configuration | Cabling | Termination | Testing |  |  | RFI / Config. | Acceptance
|  | #12 | 1
ITEM | DESCRIPTION | PROC | [6 empty] | ITEM | DESCRIPTION | imple | [7 empty] | TESTING & COMMISSIONING |  | Handover
BQ-233 | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | #INVOICE | Camera | [5 empty] | BQ-233 | ﻛﺎﻣﻳﺭﺍ ﺑﺯﺍﻭﻳﺔ ﻋﺭﻳﺿﺔ ﻟﻣﺭﺍﻗﺑﺔ ﺍﻟﺩﺧﻭﻝ Wide Angle ACS Users Surveillance Camera | #INVOICE | Camera Mounting | Configuration | Cabling | Termination | Testing |  |  | RFI / Config. | Acceptance
|  | #12 | 9

## HASR (hidden)
5350
AVB |  | Inner Patrol Road |  |  | Outer Patrol Road |  |  | Propasl Patrol Road
SHARE DEFENSE | 273.75 | West | 3215 | 546 | BEFORE GATE 02 | 2775 |  | West Sbm | 3600 | m2 | 340.4354
SOUTH BEFORE EMERGENCY GATE | 24.62 | BEFORE GATE 02 | 866 | 459 | AFTER GATE 02 | 760 |  |  | 782.61 | m.L |  | 9% |  | 26%
SOUTH FROM EMERGENCY TO GATE 01 | 226.82 | Connection to Gate 02 left | 49.5 |  | Emergency Gate | 60.63 |  |  | 547.827 |  | 15% |  | 65% |  |  | 10% | 10%
SOUTH FROM GATE 01 TO GATE 02 | 2760.74 | Connection to Gate 02 right | 37.34 |  | CONECTION RC TO GATE 02 | 43.12 |  |  |  |  | Base Coarse | Asphalt 1st | Site prep. | Base Coarse | Asphalt 1st | T&C / Configuration | Handover
SOUTH GATE 02 TO CHANNEL | 744.53 | AFTER GATE 02 | 723 |  | Total | 3638.75 |  |  |  |  | 25% | 35% | 5% | 10% | 25% | 70% | 70%
FROM CHANNEL TO THE END | 282.1 | WEST SBM | 340 |  |  | 43.12 | 3535 |  |  |  | 70% | 70% | 70% | 70% | 70%
Total | 4312.56 | Total | 5230.84 |  |  | 60.63 |  |  |  |  | 13353.2831 | 18694.5964 | 11572.8454 | 23145.6908 | 57864.2269 | 35608.755 | 35608.755
| 85 |  | 49.5 |  |  | 3535
| 282.1 |  | 37.34 | [7 empty] | 195848.1525
3945.46
FENCE ( CLASS 1 ) |  |  | 340
EAST | 506.6 |  | 4804 |  | 4804
NOURTH | 2098.22
West | 3356.33 | 5961.15 | [5 empty] | 8339 | 782.6087
SHARE DEFENSE | 273.75
SOUTH BEFORE EMERGENCY GATE | 24.62 | 11.15
SOUTH FROM EMERGENCY TO GATE 01 | 226.82
GATE 01 | 14.96
SOUTH FROM GATE 01 TO GATE 02 | 2760.74
GATE 02 | 16.35
SOUTH GATE 02 TO CHANNEL | 744.53
CHANNEL | 32.45
FROM CHANNEL TO THE END | 282.1
Total | 10337.47
50
37.46
| 32.45 | 402.01
282.1
9935.46

## MISTAKE (hidden)
82368
1089
5677.5
15210
3633
266090
82368
1089
5677.5 |  |  | 315600 | 315600 | 0
| 15210 |  | 117315 | 117315 | 0
|  |  | 412721.6 | 412721.6 | 0
3630 |  |  | 68320 | 68320 | 0
|  |  | 3885 | 3885 | 0
|  |  | 118345.5 | 118345.5 | 0
|  |  | 10770.08 | 10769.22 | 0.86
|  |  | 7308 | 763571.25 | -756263.25
|  |  | 763571.25 | 202797.87 | 560773.38
|  |  | 202797.87 | 17223.805 | 185574.065
|  |  | 17223.805 | 238975.2 | -221751.395
|  |  | 238975.2 | 11880 | 227095.2
|  |  | 11880 | 145152
|  |  | 145152 | 3520
|  |  | 3520 | 7920 |  | 0 | 75325412
|  |  | 7920 | 1017.5
|  |  | 1017.5 | 132
|  |  | 132 | -18585
|  |  | -18585 | -34749 |  |  | 897.7999
|  |  | -34749 | 4340 |  |  | 26933.9971
|  |  | 4340 | 114192
|  |  | 114192 | 11880
|  |  | 11880 | 3520
|  |  | 3520 | 1017.5
|  |  | 1017.5 | 2310
|  |  | 2310 | 39897
|  |  | 39897 | 325845
|  |  | 325845 | 154
154
2896276.305
266090